C0NSUMER  GRIEVANCE  REDRESSAL FORUM,

AKOLA ZONE,  AKOLA.

“ Vidyut Bhavan” Ratanlal Plot ,Akola.   Tel No 0724.2434475

O R D E R .

Complaint No. :-  02,03,04/ 2018

In the matter pertaining grievance of New Agriculture connection and payment of SOP compensation for delay.

Quorum

Dr.V.N.Bapat- Chairman

Shri.D.M.Deshpande, Member (CPO)

Shri. R.A.Ramteke, Member – Secretary

1.  Sou. Dewakabai Ramdas Hage	         :-    Complainant

At & Po Eklara (Banoda)

TQ-Khamgaon, Dist: Buldhana

2.  Shri. Purnaji Omkar Hage

Post Eklara Tq Sangrampur

Dist: Buldhana 444204

3.   Shri. Gajanan Namdev Dhage

Post: Warwat Bakal

Tq: Sangrampur

Dist: Buldhana 444202

….Vrs……

Ex. Engineer MSEDCL                                :-      Respondent.

O.& M , Division Khamgaon,

Dist: Buldhana

Appearances:  -

Complainant Representative                  :-       Shri. Dipak Balkrushna Tade

Respondent  Represent                           :-        Shri. Nawalkar Dy EE

MSEDCL Sangrampur

- By this common order grievance of common nature pertaining to release of new Ag connection and payment of SOP compensation for delay is resolved by this Forum.

- On being aggrieved by the decision of IGRC Buldhana issued vide order (i) IGRC/84 dt.03.01.2018 (ii) IGRC/82 dt 03.01.2018 (iii) IGRC/4712 dt 12.12.2017 complainant shri. Dewakabai Ramdash Hage , shri.Purnaji Omkar Hage from Eklara and shri. Gajanan Namdar Dhage from warwat Bakal approached this Forum as ‘Applicant’ for new Agriculture connection under clause 6.4 of MERC (CGRF and OMBudsman) regulation 2006 for resolving the grievance.

- Complainant’s case in brief is that complainant applied for new Agriculture connection in their field and paid the required charges on issue of payment advice from N.A.MSEDCL. According to complainant’s N.A.MSEDCL failed in standard of performances giving reference of EA 2003 section 43 and supply code regulation 2005 read with SOP regulation 2014 and did not release Agriculture connection within specified period of 3 months and prayed for release of electric supply to their respective Ag form within 8 days and claimed compensation as per SOP regulation 2014 till release of Agriculture connection by N.A.MSEDCL towards incidental damages and cost Detail chart depicting date of application, and completion of formalities in respect of complaint no 2,3 and 4 is reproduced below.

| Sr No | Complaint No | Name of Complainant | Place | Completion of formalities | Amt Paid |
| --- | --- | --- | --- | --- | --- |
| 1 | 2/2018 | Sou. Dewakabai Ramdas Hage | Eklara | R No.7205838 Dt. 21.1.2017 | Rs. 6100=00 |
| 2 | 3/2018 | Shri. Purnaji Omkar Hage | Eklara | R.No.6290650 Dt. 8.8.2017 | Rs.6100=00 |
| 3 | 4/2018 | Shri. Gajanan Namdav Dhage | Warwat Bakal | R.No.5835750 Dt. 31.3.2017 | Rs.20600=00 |

- Reply came to be filed by NA MSEDCL on reccpt of 15 days notice from Forum on 03.02.2018. According to NA MSEDCL, it is fact on record that Complainant No. 2,3 and 4 have applied for Agriculture connection and Completed the formalities of payment on 21.01.2017, 08.08.2017 and 31.03.2017 respectively. According to NA MSEDCL work for releasing connection to complainant No.2 and 4 is already taken in hand and work order are issued vide no. 507 dt. 12.02.2017 for complaint no. 2 and work order No. 222 dt. 17.01.2018 for Complainant No 4 and will be Completed as per chronology. According to NA MSEDCL work for releasing the connection to Ag pump of Complaint No.3 will be taken up after completion of release of connection for those who have paid before 31.03.2017. According to NA MSEDCL claim for SOP Compensation and cost may not be accepted by Hon’ble Forum since work will be completed in due course.

- Shri. Dipak Balkrishna Tade representative for Complainant No. 2,3 and 4 and Shri. Nawalkar Dy. EE Sangrampur, were present for the hearing scheduled on 06.03.2018. Shri. Dipak Tade representative for Complainant’s 2,3 and 4 explained the facts on record by referring section 43 of EA.2003 and Supply Code regulation 2005 read with SOP regulation 2014 and brought to the notice of Forum, failure on the part of NA MSEDCL to abide SOP regulation 2014 and requested Forum to direct MSEDCL to release the connection within 8 days and claimed SOP Compensation till release of  agriculture  connection.

- Shri, Nawalkar Dy EE. Sangrampur authorized learned representative for NA MSEDCL brought to the notice of Forum about work in progress for releasing the Agriculture connection to the pump of Complainant No.2 and 4 within 15 days and appose for payment of SOP Compensation, cost and damages as claimed by Complainant. Shri Nawalkar Dy. EE howerer could not assure the Forum about Completion of work for Complainant No.3.

- Having heard the parties and Considering the documents on record, Forum is of the view that no excuse or exception on law point is admissible under section 43 of EA.2003 read with supply code regulation 2005 and SOP regulation 2014 to Complete the work and release of connection within specified period mentioned in the regulation 2014 and payment of Compensation in case of dely as per Appendix ‘A’ of regulation 2014. Forum is of the view that SOP Compensation is payable despite assurance from NA MSEDCL to release Ag connection within 15 days in respect of Complainant No.2 and 4. Forum is also of the view that Ag connection to the pump of Complaint No.3 should also be released within 30 days and SOP Compensation is also payable to complainant no.3 for delay till release of connection. Forum is of the view that Complainants are not entitle for liquidated damages in absence of actual loss and provisions as per regulation 2006 for payment of incidental damages. The Forum is of the view that parties to bear their own cost. As per amendment in SOP regulation 2014, Sop Compensation is admissible if claimed within 60 days of cause of action, Forum is of the view that since these are the Complaints of continuing a cause of action, SOP Compensation of Rs 100/- per week of delay in releasing Ag connection is admissible from 60 days prior to its claim. Since Complainant No 2 and 3 have first claimed SOP Compensation on 04.12.2017 and 12.12.2017 respectively, they are entitled for SOP compensation from 4.10.2017 and 9.11.2017 respectively. Complaint No.4 Shri. Gajanan Namdave Dhage however claimed SOP from 31.05.2017 but SOP is admissible from 01.07.2017 till release of connection. With these observations, Forum proceeds to pass following unanimous order.

Order

- That Complaint No. 2,3 and 4 are herby partly allowed.

- The NA MSEDCL is directed to release the new Agriculture connection to pumpset of Complaint No 2,3 and 4 within 30 days of this order.

- The NA MSEDCL is directed to Compensate Complaint No.2 Sou. Dewakabai Ramdas Hage with SOP Compensation of Rs 100/- week from 4.10.2017 till release of connection and adjust in the first bill to be issued within 90 days.

- The NA MSEDCL is directed to Compensate Complaint No.3 Shri. Purnaji Omkar Hage with SOP Compensation of Rs 100/-week from 9.11.2017 till release of connection and adjust in the first bill to be issued within 90 days.

- The NA MSEDCL is directed to Compensate Complaint No.4 Shri. Gajanan Namdev Dhage with SOP Compensation of Rs 100/-week from 01.07.2017 till release of connection and adjust in the first bill to be issued within 90 days.

- Parties to bear their own cost.

- The NA MSEDCL is directed to submit the compliance report to this Forum with 90 days.

R.A.Ramteke	 D.M.Deshpande	V.N.Bapat

Member/Secretary                  Member (CPO)                    Chairman

Contact details of Electricity Ombudsman appointed by MERC (CGRF&EO) Regulations 2006 under Regulation 10:

THE ELECTRICITY OMBUDSMAN,

Office of Electricity Ombudsman (Nagpur)

Plot No.12, Shrikrupa, Vijaynagar, Chhaoni,

Nagpur-440 013.Phone:- 0712-2596670

No. CGRF / AKZ/ Akola/  	Dt:-

To,

The Nodal Officer,

Executive Engineer

MSEDCL, O&M Division

Khamgaon, Dist: Buldhana.

The order passed on               in the Complaint No.02,03,04/2018 is enclosed herewith for further compliance and necessary action.

Secretary,

Consumer Grievance Redressal Forum,

MSEDCL, Akola Zone, Akola.

Copy fwcs to:

1.   The Superintending Engineer, MSEDCL, O&M Circle, Akola

2.   Sou. Dewakabai Ramdas Hage, At & Po Eklara ( Banodda) Tq- Sangrampur,

Dist- Buldhana.

3.   Shri. Purnji Omkar Hage, At & Po Eklara ( Banoda) Tq- Sangrampur,

Dist- Buldhana.

4.    Shri. Gajanan Namdev Dhage, At & Po Warwat ( Bakal) Tq. Sangrampur,

Dist- Buldhana.