C0NSUMER  GRIEVANCE  REDRESSAL FORUM,

AKOLA ZONE,  AKOLA.

“ Vidyut Bhavan” Ratanlal Plot ,Akola.   Tel No 0724.2434475

O R D E R             Dt:- 24.08.2018

Complaint No :-  27/2018

In the matter of grievance pertaining to refund of new residential electric connection and SOP for delay and cost.

Quorum

Dr.V.N.Bapat- Chairman

Shri.D.M.Deshpande, Member (CPO)

Shri. R.A.Ramteke, Member – Secretary

1.     Shri. Shyam Deshmukh                               :- Complainant

Applicant For new residential connection

c/o Shri. Ashish Subhash Chandarana

Flat no. 302, Satguru Villa Apartment

Gorakshan Road Sahkarnagar

Akola-444004

….Vrs……

Nodal officer Executive Engineer	:-  	Respondent.

MSEDCL, Akot Division

Appearances

Complainant                                                     :-     Shri. Ashish .S. Chandarana

Respondent              	                                    :-     Shri. Tushar Vijay Murhekar

A.E

1.             On being aggrieved by the decision of IGRC Akola issued vide order no. 2149 dated 31.05.2018 complainant Shri. Shyam Deshmukh from Popatkhed Tq- Akot approached this Forum through their authorized representative Shri. Ashish S.Chandarana under clause 6.4 of MERC CGRF ( Ombudsman) regulation 2006 for resolving the grievance.

2.                   Complainant’s case in brief is that Shri. Shyam Deshmukh from Popatkhed who is applicant for new residential connection having applied for residential connection on 01.10.2016 for which demand note for payment is issued by N.A.MSEDCL on 17.07.2017 and even after payment of necessary charges on 20.09.2017 the connection has not been released by N.A.MSEDCL violating the SOP regulation 2014. According to complainant the demand note dated 17.07.2017 is issued only after complaint to M.D of MSEDCL on whatsApp. According to complainant they approached IGRC Akola on 31.03.2018 and IGRC violated the provisions of SOP regulation 2014 and did not resolve the grievance, complainant prays for release of connection within 7 days, SOP compensation for delay in connection at Rs 100/- per week and cost Rs 5000/-. Complainant Annexed copy of letter dated 21.04.2018 addressed to IGRC by Dy. EE MSEDCL Akot, copy of demand note with paid receipts and copy of IGRC order.

3.                   Reply came to be filed by N.A.MSEDCL belatedly on the date of hearing on 10.08.2018. According to N.A.MSEDCL release of residential connection of complainant at Popatkhed involved requirement of infrastructure such as high voltage feeder  with transformer, delayed due to deficit of funds and after getting DPDC funds work order for infrastructure work was issued vide letter no 1332 dated 12.06.2018 and work is in progress. According to N.A.MSEDCL residential connection will be released on completion of infrastructure work. No document is submitted with reply by N.A.MSEDCL.

4.             Shri. Ashish  Chandarana learned representative for complainant and Shri. Tushar Murhekar A.E learned representative for respondent were present for the hearing held on 10.08.2018. Shri. Ashish Chandarana learned representative for complainant reiterated the grievance on record and urged Forum to direct MSEDCL to release residential connection giving reference of E.A.2003, Supply Code regulation and SOP regulation 2014 and claimed SOP compensation of Rs 100/- per week for delay in releasing connection with cost.

5.             Shri. Tushar Murhekar A.E. and learned represent for N.A.MSEDCL submitted that infrastructure work for releasing the connection is in progress and will be completed up to 31.08.2018 and urged that deficit of fund allocation as the reason for delay.

6.           Having heard the parties and after considering material placed on record Forum is of the view that there is duty cast on N.A.MSEDCL as per E.A. Act 2003 read with Supply Code 2005 and SOP regulation 2014 according to which N.A.MSEDCL should have released residential connection up to 19.12.2017 and since N.A.MSEDCL failed to abide standard of performance as per SOP regulation 2014 the complainant is entitled for compensation at Rs 100/- per week from 20.12.2017 till release of connection. But as provided in regulation 2014 the SOP compensation is admissible from 01.01.2018 till release of connection since claimed on 31.03.2018 as cause of grievance of non-release of connection is continuing cause. The reason given by N.A.MSEDCL as deficit of funds is not accepted by Forum as E.A act 2003 or supply code regulation 2005 with SOP regulation does not provide any excuse for release of connection within specified time limit of SOP regulation 2014. Since N.A.MSEDCL during hearing have not disputed to release the connection and submitted on record to complete the work before 31.08.2018 Forum is of the view that residential connection to complainant be released by N.A.MSEDCL within 15 days of the issue of order and complainant be compensated by SOP compensation at Rs 100/- per week from 01.01.2018 till date of release and amount be adjusted in first energy bill payable by complainant. Forum is of the view that parties to bear their own cost. With these observations Forum proceeds to pass following unanimous order.

ORDER

1)    That the complaint no. 27 of 2018 is hereby partly allowed.

2)    That the N.A.MSEDCL is directed to release the residential connection of complainant within 15 days of order.

3)    That the N.A.MSEDCL is directed to compensate complainant by SOP compensation at Rs 100/- per week or part thereof from 01.01.2018 till release of connection and adjust the amount in the first energy bill payable by complainant.

4)    Parties to bear their own cost.

5)    That the N.A.MSEDCL is directed to submit the compliance report to this Forum within one month.

Sd/-                                  Sd/-                                 Sd/-

Member/Secretary         Member (CPO)            	Chairman

Contact details of Electricity Ombudsman appointed by MERC (CGRF&EO)    Regulations 2006 under Regulation 10:

THE ELECTRICITY OMBUDSMAN,

Office of Electricity Ombudsman (Nagpur)

Plot No.12, Shrikrupa, Vijaynagar, Chhaoni,

Nagpur-440 013.Phone:- 0712-2596670

No. CGRF/AKZ/Akola/308                                                 Dt:- 24.08.2018

To

The Nodal Officer,

Executive Engineer

MSEDCL, O&M Division Akot

The order passed on 24.08.2018 in the Complaint No.27/2018 is enclosed herewith for further compliance and necessary action.

Secretary,

Consumer Grievance Redressal Forum,

MSEDCL, Akola Zone, Akola.

Copy fwcs to:-

1.  Superintending Engineer, MSEDCL, Akola Circle, Akola.

2. Shri. Shyam Deshmukh, Applicant For new residential connection

c/o Shri. Ashish Subhash Chandarana, Flat no. 302, Satguru Villa Apartment, Gorakshan Road, Sahkarnagar Akola-444004