C0NSUMER  GRIEVANCE  REDRESSAL FORUM,

AKOLA ZONE,  AKOLA.

“ Vidyut Bhavan” Ratanlal Plot ,Akola.   Tel No 0724.2434475

O R D E R                  Dt:- 22.10.2018

Complaint No: - 46/2018

In the matter of grievance pertaining to New connection of poultry Farm and SOP compensation.

Quorum

Dr.V.N.Bapat- Chairman

Shri.D.M.Deshpande, Member (CPO)

Shri. R.A.Ramteke, Member – Secretary

1.     Shri. Narsingrao Vinayakrao Bakal    	    :-       Complainant

At-Post Warwat Bakal Tq-Sangrampur

Dist-Buldhana

….Vrs……

Nodal Officer, Executive Engineer               :-  	    Respondent

MSEDCL, O&M, Khamgaon Division.

Appearances

Complainant                                                        :-       Shri.DipiakTade

Representative

Respondent                                                         :-	   S.B.Navalkar

Dy.EE

1.                                           On being aggrieved by the decision of IGRC Buldhana issued vide IGRC/BLD/2095 dated 17.07.2018 complainant Shri. Narsingrao V.Bakal approached this Forum under regulation 6.4 of MERC (CGRF & Ombudsman) Regulation 2006 for resolving the grievance.

2.                                          In brief the complainant is applicant for new connection for the purpose of ‘Poultry Farm’ at Warwat Bakal having applied to N.A.MSEDCL on 16.04.2018. According to complainant said application for new connection was sent to N.A.MSEDCL by registered post which is acknowledged on 19.04.2018 by N.A.MSEDCL. According to complainant as demand note for payment was not issued by N.A.MSEDCL within 30 days, SOP compensation was claimed on 23.05.2018 and complaint was lodged with IGRC Buldhana on 19.06.2018. Complainant prays to release connection immediately, SOP compensation and cost.

3.                                        Reply came to be filed on 04.10.2018 by N.A.MSEDCL. According to N.A.MSEDCL estimate for giving supply to Poultry Farm of  complainant is sanctioned vide DPDC/ND/18-19/29 dated 02.08.2018 and demand note for payment of charges is issued on 02.08.2018. According to N.A.MSEDCL complainant has paid the charges on 18.08.2018 and work against estimate for 0.12 km 11kv and 10KVA transformer will be taken up on getting funds from DPDC. According to N.A.MSEDCL payment of SOP compensation as per IGRC order Rs 100/- per week is under process.

4.                                           Shri. D.B.Tade learned representative for complainant and Shri.S.B.Navalkar Dy.EE MSEDCL were present for the hearing held on 12.10.2018. Shri. D.B.Tade learned representative of the complainant brought to the notice of Forum that N.A.MSEDCL have not complied the IGRC order issued on 17/07/2018 and SOP compensation for delay in issue of quotation is still unpaid and urged Forum to direct N.A.MSEDCL to release connection within 3 months of payment and sop compensation should be paid thereafter and claimed cost Rs 3000/-.

5.                                           Shri.S.B.Nawalkar Dy.EE MSEDCL brought to the notice of Forum that IGRC order will be complied in due course and connection will also be released up to 17.11.2018 within permissible period of three months as work involved is HT 0.12 km and erection of transformer.

6.                                              Having heard the parties and considering the material placed on record Forum is of the view that N.A.MSEDCL have delayed the issue of demand note and IGRC Buldhana rightly awarded SOP compensation for the delay and since estimate is sanctioned as brought on record and considering submission of N.A.MSEDCL to complete the work within permissible limit, Forum is of the opinion that the prayer of complainant for SOP compensation for delay in releasing connection is premature and unjustified as grievance of SOP compensation does not constitute at this stage. Forum is of the view that IGRC Buldhana order dated 17.07.2018 should be modified to the extent of releasing connection by N.A.MSEDCL within three months of payment and  readiness of installation by complainant, on intimation of line ready.

With these observations Forum proceeds to pass following unanimous order.

ORDER

1)    That the complaint No 46 of 2018 is hereby partly allowed.

2)    That the IGRC order No 2095 dated 17.07.2018 is modified and N.A.MSEDCL is directed to release connection to poultry farm of complainant within three months of payment and completed installation.

3)    No order as to the cost.

4)    That the N.A.MSEDCL is directed to submit compliance report to this Forum after three months.

Sd/-                              Sd/-                        Sd/-

Member/Secretary       Member (CPO)	     Chairman

Contact details of Electricity Ombudsman appointed by MERC  (CGRF&EO)  Regulations 2006 under Regulation 10:

THE ELECTRICITY OMBUDSMAN,

Office of Electricity Ombudsman (Nagpur)

Plot No.12, Shrikrupa, Vijaynagar, Chhaoni,

Nagpur-440 013.Phone:- 0712-2596670

No. CGRF/AKZ/Akola/368                                               Dt:- 22.10.2018

To

The Nodal Officer,

Executive Engineer

MSEDCL, O&M

Khamgaon Division.

The order passed on 22.10.2018 in the Complaint No.46/2018 is enclosed herewith for further compliance and necessary action.

Secretary,

Consumer Grievance Redressal Forum,

MSEDCL, Akola Zone, Akola.

Copy fwcs to:-

- Superintending Engineer MSEDCL, Buldhana Circle, Buldhana.

2. Shri. Narsingrao Vinayakrao Bakal,   At-Post Warwat Bakal    Tq-   Sangrampur, Dist-Buldhana