C0NSUMER  GRIEVANCE  REDRESSAL FORUM,

AKOLA ZONE,  AKOLA.

“Vidyut Bhavan” Ratanlal Plot ,Akola.   Tel No 0724.2434475

O R D E R               	   Dt:- 15.11.2018

Complaint No: - 45/2018

In the matter of grievance pertaining to fuse off call complaint and SOP compensation.

Quorum

Dr.V.N.Bapat- Chairman

Shri.D.M.Deshpande, Member (CPO)

Shri. R.A.Ramteke, Member – Secretary

1.  Sou. Madhuri Arun Rathi                        :-	Complainant

L/S No. 53/3 At- Dabki

Consumer No – Ag-310431121874

LT-310431122889, ℅ Siddhivinayak

Hospital, Behind New bus stand Akola-444001

….Vrs……

Nodal Officer, Executive Engineer           :-  	Respondent

MSEDCL, O&M Akola Rural Division.

Appearances

Complainant                                                 :- 	Shri.DipiakTade

Representative

Respondent                                                  :-      G.K.Gadekar

Executive Engineer,

MSEDCL, With Shri.

S.P.Kenekar. Dy EE

1.                                                         On being aggrieved by the decision of IGRC Akola issued vide IGRC/Kkola/3538 dated 07.09.2018 complainant Sou. Madhuri Rathi approached this Forum under regulation 6.4 of MERC (CGRF & Ombudsman) regulation 2006 for resolving the grievance.

2.                                                           In brief, complainant is Agriculture and residential consumer of N.A.MSEDCL at Gat No 151 at Dabki under sub division Rural with date of connection for Ag as 01.09.2017 and 04.04.2018 for residential. According to complainant electric supply to Ag pump and residence was disrupted on 01.06.2018 and fuse off call complaint was lodged with Assistant Engineer MSEDCL fuse off call center 2 on 13.06.2018 as per copy enclosed and to Dy EE subdivision Rural on 22.06.2018. According to complainant as fuse off call complaint remained unattended, filed SOP claim with Dy EE Rural MSEDCL Akola on 10.07.2018. According to complainant N.A.MSEDCL failed to restore electric supply within 48 Hrs and complainant prays for SOP compensation at Rs 50/- Hrs for both the connection from 01.06.2018 to 12.08.2018 till restoration of supply, and cost Rs 2000/- complainant Annexed copy of complaint dated 13.06.2018, 22.06.2018 and 10.07.2018 and IGRC order along with grievance.

3.                                                                Reply came to be filed belatedly by N.A.MSEDCL on 06.10.2018. According to N.A.MSEDCL 2 No PSC pole extending power supply to Ag Pump and residence of  complainant were found broken due to natural storms on 05.06.2018 and supply was disrupted. According to N.A.MSEDCL damages of electric pole of the area was in huge quantum due to natural calamity, and rectification work hampered due to continued rainfall and after getting space in the farm for erection of pole the supply was restored on 09.08.2018. According to N.A.MSEDCL delay was not the result of negligence on the part of MSEDCL but MSEDCL employees were prevented by natural calamity to restore the supply beyond the control of MSEDCL.

4.                                                           Shri.D.B.Tade learned representative of the complainant and Shri. S.B.Gadekar Nodal officer and Executive Engineer Rural MSEDCL were present for the hearing held on 12.10.2018. Shri.D.B.Tade learned representative for complainant reiterated the grievance on record and urged that breakdown occurred on 01.06.2018 due to inferior quality of work and not due to storm as brought on record by N.A.MSEDCL and prays to allow the complaint with SOP compensation and cost Rs 2000/-.

5.                                                      Shri. S.B.Gadekar Executive Engineer MSEDCL brought on record that the quantum of damages to electric pole were so huge to rectify the erection of pole within 48 Hours and MSEDCL employees were prevented by natural calamity of storms from meeting their obligations and sought time to file on record the certificate of revenue authority up to 22.10.2018.

6.                                                     Nodal officer, Executive Engineer (Rural) Akola have filed on record as per direction of Forum, the revenue authority certificate regarding occurrence of heavy storm with rains signed by Talathi Bhaurad dated 22.10.2018 and loss to the MSEDCL property report due to heavy storm, heavy rains, flood, unseasonal rain and hailstorm submitted to higher authorities of MSEDCL on 11.06.2018 and filed on record on 29.10.2018.

7.                                                     Having heard the parties and after considering Material placed on record, Forum is of the view that there is substance in the plea taken by N.A.MSEDCL before IGRC and this Forum that due to force majeure such as heavy storm with rains prevented N.A.MSEDCL from meeting their obligation under SOP regulation 2014. Forum have gone through the loss to the boards property report dated 11.06.2018 filed on record according to which Akola Rural Sub-division area was mostly affected due to heavy storm, rains and hailstorm damaging 208 No of PSC poles, 2.04 km of HT line and 4.58 km of L.T line causing similar damages in Akola (Rural) division area and Forum is of  the view that considering procurement of huge quantity material and its execution, was beyond the control of the distribution licensee to abide time period as mentioned in SOP regulation 2014 and N.A.MSEDCL is exempted from abiding levels of compensation payable to consumer for failure to meet standards of performance as per regulation 11 of MERC SOP regulation 2014.  Forum do not find any reason to interfere with the order passed by IGRC Akola vide 3538 dated 07.09.2018 and upheld the order passed by IGRC Akola.

With these observations Forum proceeds to pass following unanimous order.

ORDER

1)    That the complaint No 45 of 2018 is hereby rejected.

2)   No order as to the cost.

Sd/-                                  Sd/-                            Sd/-

Member Secretary            Member (CPO)           Chairman

Contact details of Electricity Ombudsman appointed by MERC  (CGRF&EO)  Regulations 2006 under Regulation 10:

THE ELECTRICITY OMBUDSMAN,

Office of Electricity Ombudsman (Nagpur)

Plot No.12, Shrikrupa, Vijaynagar, Chhaoni,

Nagpur-440 013.Phone:- 0712-2596670

No. CGRF/AKZ/Akola/                                                    	   Dt:-

To

The Nodal Officer,

Executive Engineer

MSEDCL O&M,

Rural Division, Akola

The order passed on 15.11.2018  in the Complaint No.45/2018 is enclosed herewith for further compliance and necessary action.

Secretary,

Consumer Grievance Redressal Forum,

MSEDCL, Akola Zone, Akola.

Copy fwcs to:-

1.  Superintending Engineer MSEDCL, Akola  Circle, Akola.

2. Sou. Madhuri Arun Rathi L/S No. 53/3 At- Dabki. Siddhivinayak Hospital Behind New bus stand Akola-444001.