## Query 98 a (hidden)
Project Details
[6 empty] | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
| DPR /Non-DPR | Sr.No | Project Code | MERC Approval No. | Status | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | Total
Dist |  | 1 | AG Policy -2020 | MERC/Capex/MSEDCL/2023-24/100 |  | 570.2837 | 1882.4412 | 1882.4412 | 0 | 0 | 0 | 0 | 0 | 4335.1661
Dist |  | 2 | Ag Special Package for Vidabhrba /maratwada & maha | MERC/Capex/MSEDCL/2019-20/026 |  | 1.1093 | 45.0213 | 45.0213 | 0 | 0 | 0 | 0 | 0 | 91.1519
Dist |  | 3 | DPDC / Non-Tribal | MERC /CAPEX/2019-20/for DPDC 2019-20 |  | 464.1519 | 560.8365 | 560.8365 | 851.851 | 937.0361 | 1030.7397 | 1133.8137 | 1247.195 | 6786.4605
Dist |  | 4 | DPDC / SCP (Loan up to 2012-13) | MERC /CAPEX/2019-20/for DPDC 2019-20 |  | 147.2012 | 156.2629 | 156.2629 | 206.657 | 227.3227 | 250.055 | 275.0605 | 302.5665 | 1721.3887
Dist |  | 5 | DPDC / TSP + OTSP | MERC /CAPEX/2019-20/for DPDC 2019-20 |  | 111.0165 | 155.9602 | 155.9602 | 130.867 | 143.9537 | 158.3491 | 174.184 | 191.6024 | 1221.893
Dist |  | 6 | Evacuation of Power from EHV Substation | MERC/Capex/2021-22/312 |  | 14.592 | 1.047 | 1.047 | 83 | 0 | 0 | 0 | 0 | 99.6859
Dist |  | 7 | Evacuation of Power from EHV Substation (Phase-III) | MERC/Capex/2022-23/673 |  | 0 | 0 | 0 | 130.81 | 0 | 0 | 0 | 0 | 130.81
Dist |  | 8 | High Loss Feeder | MERC/Capex/2018-19/1258 |  | 39.5935 | 4.2069 | 4.2069 | 0 | 0 | 0 | 0 | 0 | 48.0073
Dist |  | 9 | MIDC Network Strengthening | MERC/Capex/2021-22/315 |  | 22.7205 | 35.7189 | 35.7189 | 100 | 0 | 0 | 0 | 0 | 194.1583
Dist |  | 10 | New consumers | MERC/Capex/2021-22/086 |  | 290.3977 | 469.5499 | 469.5499 | 0 | 0 | 0 | 0 | 0 | 1229.4976
Dist |  | 11 | RDSS-Loss Reduction Part B | MERC/Capex/MSEDCL/2023-24/0179 |  | 0 | 395.6397 | 395.6397 | 3892.99 | 0 | 0 | 0 | 0 | 4684.2695
Dist |  | 12 | RDSS-Raynagar Colony Solapur -PMAY | MERC/Capex/MSEDCL/2023-24/179 |  | 0 | 11.9844 | 11.9844 | 25.92 | 0 | 0 | 0 | 0 | 49.8888
Dist |  | 13 | Shet Tale | MERC/Capex/MSEDCL/2019-20/078 |  | 1.2942 | 6.377 | 6.377 | 0 | 0 | 0 | 0 | 0 | 14.0482
Dist |  | 14 | System strengthening work in Metropolitain Area | MERC/Capex/2019-20/917 |  | 28.4261 | 16.4147 | 16.4147 | 29 | 0 | 0 | 0 | 0 | 90.2555
Dist |  | 15 | RDSS-Cyclone Resilient Network NCRMP Works | MERC/Capex/MSEDCL/2023-24/0179 |  | 0 | 51.2985 | 51.2985 | 0 | 0 | 0 | 0 | 0 | 102.5971
Dist |  | 16 | Agriculture Metering | Providing 100% meters to Ag consumers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Dist |  | 17 | DTC Metering Phase-III | - |  | 0 | 0.14854 | 0.14854 | 0 | 0 | 0 | 0 | 0 | 0.29708
Dist |  | 18 | Evacuation of Power from EHV Substation (Phase-IV) | Proposal is under process |  | 0 | 0 | 0 | 75 | 75 | 0 | 0 | 0 | 150
Dist |  | 19 | Nagpur OH to UG | Not applicable |  | 0 | 0 | 0 | 36.3 | 100 | 100 | 135 | 156 | 527.3
Dist |  | 20 | New Consumers 2025-2030 | Proposal is under process |  | 0 | 0 | 0 | 750 | 750 | 750 | 750 | 750 | 3750
Dist |  | 21 | P:IE | Districtwise approval List attached is received |  | 0.060244 | 0.16931 | 0.16931 | 0 | 0 | 0 | 0 | 0 | 0.39887
Dist |  | 22 | P:SI | Districtwise approval List attached |  | 0.059443 | 1.3867 | 1.3867 | 0 | 0 | 0 | 0 | 0 | 2.8329
Dist |  | 23 | RDSS (PMA) | GoI Approval No. 02:10:RDSS:2021:I:MSEDCL dtd. 22.09.2022 |  | 2.1809 | 7.2139 | 7.2139 | 5.9552 | 0 | 0 | 0 | 0 | 22.5639
Dist |  | 24 | RDSS-Dvp of Particular Vulnerable Tribal Grp(PVTG) | Proposal is under process |  | 0 | 0.25431 | 0.25431 | 0 | 0 | 0 | 0 | 0 | 0.50862
Dist |  | 25 | RDSS-System Strenghtening & Modernization | - |  | 0 | 0.24816 | 0.24816 | 6190.084 | 9285.126 | 6190.084 | 6190.084 | 0 | 27855.8743
Dist |  | 26 | SIDBI Cluster Development Fund (CDF) | Proposal is under process |  | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 200
Dist |  | 27 | SPA:PE | Districtwise approval List attached |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Dist |  | 28 | Special Assistance-Nagpur & Pune System Strengthening | Proposal is under process |  | 0 | 0 | 0 | 135.73 | 0 | 0 | 0 | 0 | 135.73
Dist |  | 29 | Sukanu Samiti for 2019-20 | Not applicable |  | 0 | 0.24939 | 0.24939 | 0 | 0 | 0 | 0 | 0 | 0.49877
Dist |  | 30 | System Improvement Scheme | - |  | 0 | 0.9885 | 0.9885 | 0 | 0 | 0 | 0 | 0 | 1.977
Dist |  | 31 | System Strengthening (MSKVY 2.0) | Applied for approval vide letter no. 32549 Dtd: 15.10.2024 |  | 0 | 158.6402 | 158.6402 | 893 | 70 | 70 | 70 | 0 | 1420.2804
Dist |  | 32 | TSP Grant substation scheme | Proposal is under process |  | 0 | 11.3489 | 11.3489 | 139 | 153 | 168 | 185 | 204 | 871.6978
Dist |  | 33 | Underground works of extended area of Baramati Municipal Corporation | Not applicable |  | 5.7381 | 13.237 | 13.237 | 0 | 0 | 0 | 0 | 0 | 32.212
Dist |  | 34 | Back log | - |  | 32.1827 | 17.317 | 17.317 | 0 | 0 | 0 | 0 | 0 | 66.8167
Dist |  | 35 | DDF/NON DDF | Not applicable |  | 582.5166 | 924.5775 | 924.5775 | 600 | 600 | 600 | 600 | 600 | 5431.6715
Dist |  | 36 | Rural Electrification | - |  | 4.4e-08 | 0.039654 | 0.039654 | 0 | 0 | 0 | 0 | 0 | 0.079309
Dist |  | 37 | MIDC Interest free Loan Scheme | MERC/Capex/2017-18/4783 |  | 2.2497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2497
0
Project |  | 1 | DDUGJY | MERC /CAPEX/2017-18/0152 |  | 0.21817 | 1.9572 | 1.9572 | 0 | 0 | 0 | 0 | 0 | 4.1325
Project |  | 2 | Elimination of 66 KV Line | MERC/CAPEX/2009-10/238 |  | -8.1315e-18 | 0.06169 | 0.06169 | 0 | 0 | 0 | 0 | 0 | 0.12338
Project |  | 3 | HVDS Scheme | MERC/CAPEX/2018-19/1216 |  | 28.3955 | 49.7168 | 49.7168 | 0 | 0 | 0 | 0 | 0 | 127.8292
Project |  | 4 | Infra Plan Works - II | MERC/CAPEX/20132014/00860 MERC/CAPEX/20132014/00260 MERC/CAPEX/20132014/00259 MERC/Desk III /CAPEX/20132014/01492 MERC/Desk III /CAPEX/2012201/02693 MERC/Desk III /CAPEX/20132014/01491 MERC/Desk III /CAPEX/20132014/00473 MERC/Desk III /CAPEX/20122013/02488 MERC/Desk III /CAPEX/20122013/02322 MERC/Desk III /CAPEX/20122013/02488 MERC/CAPEX/20132014/00472 MERC/CAPEX/20132014/00939 MERC/CAPEX/20132014/01363 MERC/CAPEX/20122013/00607 MERC/CAPEX/20122013/01362 MERC/Desk III /CAPEX/20132014/01800 MERC/Desk III /CAPEX/00967 MERC/Desk III /CAPEX/00878 MERC/Desk III /CAPEX/34 MERC/Desk III /CAPEX/01887 MERC/Desk III /CAPEX/20142015/00020 MERC/Desk III /CAPEX/01888 MERC/Desk III /CAPEX/20132014/0351 MERC/Desk III /CAPEX/02189 MERC/Desk III /CAPEX/00968 MERC/Desk III /CAPEX/20132014/01884 MERC/Desk III /CAPEX/20132014/01935 MERC/Desk III /CAPEX/02192 MERC/Desk III /CAPEX/20132014/01934 MERC/Desk III /CAPEX/00350 MERC/Desk III /CAPEX/02303 MERC/Desk III /CAPEX/20132014/02003 MERC/Desk III /CAPEX/20132014/02002 MERC/Desk III /CAPEX/20132014/02000 MERC/Desk III /CAPEX/2178 MERC/Desk III /CAPEX/2190 MERC/Desk III /CAPEX/2191 MERC/Desk III /CAPEX/2302 MERC/Desk III /CAPEX/1886 MERC/Desk III /CAPEX/1883 MERC/Desk III /CAPEX/1885 MERC/Desk III /CAPEX/20132014/00138 MERC/Desk III /CAPEX/20132014/00139 MERC/Desk III /CAPEX/20132014/01365 MERC/Desk III /CAPEX/20132014/01751 MERC/Desk III /CAPEX/00967 MERC/Desk III /CAPEX/00878 MERC/Desk III /CAPEX/34 MERC/Desk III /CAPEX/1887 MERC/Desk III /CAPEX/20142015/00020 MERC/Desk III /CAPEX/01888 MERC/Desk III /CAPEX/20132014/00351 MERC/Desk III /CAPEX/2189 MERC/Desk III /CAPEX/00968 MERC/Desk III /CAPEX/20132014/01876 MERC/Desk III /CAPEX/20142015/00021 MERC/Desk III /CAPEX/20122013/02654 MERC/Desk III /CAPEX/20122013/02648 MERC/Desk III /CAPEX/20132014/01823 MERC/Desk III /CAPEX/20122013/02487 MERC/Desk III /CAPEX/20122013/02351 MERC/Desk III /CAPEX/20132014/02193 MERC/Desk III /CAPEX/20132014/1365 MERC/Desk III /CAPEX/20132014/01492 MERC/Desk III /CAPEX/20122013/02693 MERC/Desk III /CAPEX/20122013/02322 MERC/Desk III /CAPEX/20132014/00472 MERC/Desk III /CAPEX/20132014/01363 MERC/Desk III /CAPEX/20132014/02179 MERC/Desk III /CAPEX/00795 MERC/Desk III /CAPEX/00794 MERC/Desk III /CAPEX/00140 MERC/Desk III /CAPEX/20142015/00376 MERC/Desk III /CAPEX/20142015/00375 MERC/Desk III /CAPEX/20142015/00377 |  | 8.611 | 0.102 | 0.102 | 0 | 0 | 0 | 0 | 0 | 8.8151
Project |  | 5 | IPDS | MERC /CAPEX/201516/1464 MERC /CAPEX/2018-19 /113 |  | 0 | 0.91405 | 0.91405 | 0 | 0 | 0 | 0 | 0 | 1.8281
Project |  | 6 | RAPDRP B | MERC/CAPEX/20102011/01955 MERC/CAPEX/20112012/00071 MERC/CAPEX/20112012/1592 MERC/CAPEX/20102011/2158 MERC /CAPEX/20122013/00611 MERC /CAPEX/201516/1470 |  | 0 | 0.98577 | 0.98577 | 0 | 0 | 0 | 0 | 0 | 1.9715
Project |  | 7 | RDSS-Loss Reduction Part A Feeder Separation Works | MERC/CAPEX/MSEDCL/2023-24/0179 |  | 0 | 763.8228 | 763.8228 | 3008.3087 | 1000 | 0 | 0 | 0 | 5535.9544
Project |  | 8 | Reactive Power Management Scheme (PSDF) | MERC/CAPEX/MSEDCL/2023-24/101 |  | 0 | 102.3661 | 102.3661 | 0 | 0 | 0 | 0 | 0 | 204.7323
Project |  | 9 | Saubhagya Scheme | MERC /CAPEX/2019-20 /115 |  | 0.014174 | 1.4643 | 1.4643 | 0 | 0 | 0 | 0 | 0 | 2.9427
Project |  | 10 | SCADA Part A | MERC/CAPEX/20112012/02426 |  | 12.6465 | 4.9604 | 4.9604 | 0 | 0 | 0 | 0 | 0 | 22.5672
Project |  | 11 | Underground works under System Strengthening in Gondia, Bhandara and Nagpur 1st Phase | MERC/CAPEX/2021-22 /052 |  | 0 | 20.1446 | 20.1446 | 12 | 0 | 0 | 0 | 0 | 52.2891
Project |  | 12 | MAHARASHTRA POWER DISTRIBUTION ENHANCEMENT PROGRAM FOR FACILITATING SOLARISATION AND EXPANDING AGRICULTURAL CONNECTIONS (Funded by ADB) |  |  | 0 | 0 | 0 | 3040 | 2280 | 0 | 0 | 0 | 5320
Project |  | 13 | MSKVY 2.0 Under RDSS | Submitted to MERC for Inprinciple approval |  | 0 | 0 | 0 | 1489 | 1191.2 | 0 | 0 | 0 | 2680.2
Project |  | 14 | OFF-GRID SOLAR PHOTOVOLTAIC WATER PUMPING SYSTEMS & AGRICULTURAL FEEDER SOLARISATION PROJECT WITH CONVENTIONAL AG CONNECTIONS. (Funded by AIIB) Component AA | Submitted to MERC for Inprinciple approval |  | 0 | 0 | 0 | 764.34 | 611.472 | 0 | 0 | 0 | 1375.812
0
SPD,IT,RE,TEST |  | 1 | Approval for installation of Rooftop solar at MSEDCL owened Building such as offices, substations, stores, Rest house and CFC's for total pf 50MW |  |  | 0 | 0 | 0 | 142.25 | 0 | 0 | 0 | 0 | 142.25
SPD,IT,RE,TEST |  | 2 | DELP | - |  | 0 | 0.17207 | 0.17207 | 0 | 0 | 0 | 0 | 0 | 0.34414
SPD,IT,RE,TEST |  | 3 | Electric Vehicle Charging Stations | MERC/Capex/2021-22/548 dtd 15.12.2021 |  | 6.4833 | 3.2279 | 3.2279 | 0.1694 | 0.1694 | 0.1694 | 0.1694 | 0 | 13.6168
SPD,IT,RE,TEST |  | 4 | Implementation of of solar Roof top project for the Prakashgad Building Bandra | Preperation of DPR is in process |  | 0 | 0 | 0 | 0.355 | 0 | 0 | 0 | 0 | 0.355
SPD,IT,RE,TEST |  | 5 | Maharashtra Solar AG Pump Project | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPD,IT,RE,TEST |  | 6 | Mukhyamantri Sour Krushi Pump Yojana | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPD,IT,RE,TEST |  | 7 | OFF-GRID SOLAR PHOTOVOLTAIC WATER PUMPING SYSTEMS & AGRICULTURAL FEEDER SOLARISATION PROJECT WITH CONVENTIONAL AG CONNECTIONS. (Funded by AIIB) Component A: | Preperation of DPR is in process |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPD,IT,RE,TEST |  | 8 | GIS network analyasis | Proposal is in process of submission. |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPD,IT,RE,TEST |  | 9 | Implementation of Electric Vehicle Chargeing Infrastructure operation Center (IT) | Project Cost below 10 Crs |  | 0 | 0 | 0 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 1
SPD,IT,RE,TEST |  | 10 | Substation Monitoring System | project is in process |  | 0 | 0 | 0 | 62.12 | 62.12 | 0 | 0 | 0 | 124.24
SPD,IT,RE,TEST |  | 11 | Implementation of SD WAN | MERC/Capex/MSEDCL/2023-24/0179 dt 11.03.2024. | [9 empty] | 0
SPD,IT,RE,TEST |  | 12 | IT OT redevelopement | MERC/Capex/MSEDCL/2023-24/0179 dt 11.03.2024. | [9 empty] | 0
SPD,IT,RE,TEST |  | 13 | Cloud Infrastructure | Proposal is in process of submission. |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPD,IT,RE,TEST |  | 14 | SAP upgradation S4 hana | MERC/Capex/MSEDCL/2023-24/0179 dt 11.03.2024. | [9 empty] | 0
SPD,IT,RE,TEST |  | 15 | Business anaytics and demand forcasting | MERC/Capex/MSEDCL/2023-24/0179 dt 11.03.2024. | [9 empty] | 0
SPD,IT,RE,TEST |  | 16 | NBSP SIM services | Project in process |  | 0 | 0 | 0 | 8.91 | 8.91 | 8.91 | 8.91 | 8.91 | 44.55
SPD,IT,RE,TEST |  | 17 | Procurement of IT infra | LOA cost below the 10 crs. |  | 0 | 0 | 0 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 62.5
SPD,IT,RE,TEST |  | 18 | Mukhyamantri Saur Vahini Yojana Phase I | Capex no/18-19/035 |  | 23.4869 | 6.5641 | 6.5641 | 0 | 0 | 0 | 0 | 0 | 36.6151
SPD,IT,RE,TEST |  | 19 | Incomer Metering-IM | MERC /CAPEX/2019-20/801 |  | 0.71016 | 0.84091 | 0.84091 | 0 | 0 | 0 | 0 | 0 | 2.392
0
[6 empty] | 2396.3401 | 5885.8789 | 5885.8789 | 23016.3173 | 17508.0099 | 9339.0072 | 9534.9215 | 3472.9739 | 77039.3278

## 4.1 Dist
Project Details
(Rs. Crore)
Sr.No | Project Code | Project Title | MERC Approval No. | MERC Approval Date | Project Purpose | Project Start Date |  |  | Project Completion date (Scheduled) |  |  | Capital Cost
[6 empty] | Original | Revised | Actual | Original | Revised | Actual | Approved | Actual Capital Cost Incurred | Deviation = Approved - Actual on account of
[14 empty] | Change in Scope of Work (a) | Material Cost (b) | IDC (c) | Others (d) | Total Deviation (a+b+c+d)
1 | AG Policy -2020 | AG Policy -2020 | MERC/Capex/MSEDCL/2023-24/100 | 05.02.2024 | Developing infrastructure & providing power supply to Ag paid pending applications after 31 March 2018 | 15.01.2021 | - | 15.01.2021 | 31.03.2024 | - | WIP | 4212.63 | 2239 | - | - | - | Only Rs. 1849.41 Crs received from GoM against sanctioned amount of Rs. 4500 Crs. Rs. 702 Crs. Infused from internal resourse of MSEDCL and Rs. 1100 Crs. are utilized from ACF. | -
2 | Ag Special Package for Vidarbha & Marathwada | Ag Special Package for Vidarbha & Marathwada | MERC/Capex/MSEDCL/2019-20/026 | 17.01.2020 | GoM scheme to provide electricity supply to Ag consumers in Vidarbha & Marathwada region in light of economic crisis faced by the farmers due to frequent draught condition. | Phase-I 17.08.2015 Phase-II 31.10.2017 | Phase-I 17.08.2015 Phase-II 31.10.2017 | Phase-I 17.08.2015 Phase-II 31.10.2017 | 31.03.2019 | - | 31.03.2019 | Phase-I-819 Crs. Phase-II 910.73 Crs. | Phase-I-819 Crs. Phase-II 910.73 Crs. | - | - | - | - | NIL
3 | DPDC / Non-Tribal | DPDC / Non-Tribal | MERC /CAPEX/2019-20/for DPDC 2019-20 | 06.05.2020 | Release of 1 ph. & small industrial, PWW conns. & minor S.I. works | 01.04.2023 | 01.04.2023 | 01.07.2023 | 31.03.2025 | 30.06.2025 | WIP | 558.4 | 250.81 | - | - | - | - | -
4 | DPDC / SCP (Loan up to 2012-13) | DPDC / SCP (Loan up to 2012-13) | MERC /CAPEX/2019-20/for DPDC 2019-20 | 06.05.2020 | Release of 1 ph. & Ag. conns. To SC & NB beneficiaries & electrification of Dalit Basties | 01.04.2023 | 01.04.2023 | 01.09.2023 | 31.03.2025 | 31.08.2025 | WIP | 128.22 | 48.54 | - | - | - | - | -
5 | DPDC / TSP + OTSP | DPDC / TSP + OTSP | MERC /CAPEX/2019-20/for DPDC 2019-20 | 06.05.2020 | Release of 1 ph. & Ag. conns. To Tribal beneficiaries & electrification of Tribal wadies | 01.04.2023 | 01.04.2023 | 01.07.2023 | 31.03.2025 | 30.06.2025 | WIP | 76.4253 | 39.5874 | - | - | - | - | -
6 | Evacuation of Power from EHV Substation | Evacuation of Power from EHV Substation (Phase-I&II) Scheme | MERC/Capex/2021-22/312 | 13.07.2021 | Evacuation of Power from EHV Substations commissioned by MSETCL | 01.06.2019 | 23.12.2019 | 23.12.2019 | 31.3.2023 | 31.09.2025 | - | 222.01 | 89 | - | - | - | - | -
7 | Evacuation of Power from EHV Substation (Phase-III) | Evacuation of Power from EHV Substation Phase-III Scheme | MERC/Capex/2022-23/673 | 26.12.2022 | Evacuation of Power from EHV Substations commissioned by MSETCL | 26.12.2022 | 26.12.2022 | 26.12.2022 | 31.03.2024 | 31.09.2025 | - | 155.81 | 5.5 | - | - | - | - | -
8 | High Loss Feeder | High Loss Feeder (HLF) Scheme | MERC/Capex/2018-19/1258 | 11.10.2018 | System Improvement works for reduction of losses in High Loss feeders in Urban/Town areas | 11.06.2018 | 04.10.2018 | 04.10.2018 | 31.03.2020 | 31.03.2022 | - | 316.2 | 218 | - | - | - | - | -
9 | MIDC Network Strengthening | MIDC Network Strengthening Scheme | MERC/Capex/2021-22/315 | 22.07.2021 | System Strengthening in MIDC/Industrial areas (Phase-I) | 22.07.2021 | 09.12.2021 | 09.12.2021 | 31.03.2022 | 31.09.2025 | - | 267.37 | 58.44 | - | - | - | - | -
10 | New consumers | New Consumer/Connection (NC) Scheme | MERC/Capex/2021-22/086 | 02.03.2022 | Infrastructure Plan for release of 1 Phase and 3 Phase HT/LT new Service Connections for FY 2019-20 to FY 2024-25 | 01.04.2019 | 01.04.2019 | 01.04.2019 | 31.03.2025 | 31.03.2025 | - | 2738.79 | 1966 | - | - | - | - | -
11 | RDSS-Loss Reduction Part B | RDSS-Loss Reduction Part B | MERC/Capex/MSEDCL/2023-24/0179 | 11.03.2024 | Loss Reduction | 06.04.2023 | _ | _ | 31.03.2026 | _ | _ | 5494.2 | _ | NA | NA | NA | NA | NA
12 | RDSS-Raynagar Colony Solapur -PMAY | RDSS-Raynagar Colony Solapur -PMAY | MERC/Capex/MSEDCL/2023-24/179 | 11.03.2024 | Providing power supply to 30,000 EWS Households to be constructed under Pradhan Mantri Awas Yojana (PMAY) at Kumbhari, Taluka South Solapur, District Solapur | 17.01.2022 | 07.04.2022 | 07.04.2022 | 31.03.2025 | - | - | 57.9 | 11.98 | - | - | - | - | -
13 | Shet Tale | Shet Tale | MERC/Capex/MSEDCL/2019-20/078 | 28.01.2020 | East Vidarbha Scheme have been envisaged by GoM to extend electricity supply to Ag Consumers. | 27.02.2017 | - | 01.11.2018 | 31.12.2020 | 31.12.2020 | 31.12.2020 | 749.72 | 350 | - | - | - | Received only Rs. 350 Crs from GoM against sanctioned amount of Rs. 749.72 Crs | NIL
14 | System strengthening work in Metropolitain Area | System Strengthening in Metropolitan Region (SSMR) Scheme | MERC/Capex/2019-20/917 | 22.10.2019 | System Strengthening to provide reliable and quality power supply in Mumbai and Pune Metropolitan Region | 12.10.2018 | 06.11.2018 | 06.11.2018 | 31.03.2021 | 31.09.2025 | - | 438 | 369 | - | - | - | - | -
15 | RDSS-Cyclone Resilient Network NCRMP Works | RDSS-Cyclone Resilient Network NCRMP Works | MERC/Capex/MSEDCL/2023-24/0179 | 2024-03-11 | Loss Reduction | 2023-04-06 | _ | _ | 2026-03-31 | _ | _ | Rs. 423.93 Cr | _ | NA | NA | NA | NA | NA
16 | Agriculture Metering | Agriculture Metering | Providing 100% meters to Ag consumers | - | - | 2006-07 | - | - | 2009-20 | - | - | - | - | - | - | - | - | -
17 | DTC Metering Phase-III | DTC Metering Phase-III | - | - | - | - | - | - | 0 | - | - | - | - | - | - | - | - | -
18 | Evacuation of Power from EHV Substation Phase-IV Scheme | Evacuation of Power from EHV Substation (Phase-IV) Scheme | Proposal is under process | - | Evacuation of Power from EHV Substations commissioned by MSETCL | 13.09.2024 | 13.09.2024 | 13.09.2024 | 31.03.2028 | - | - | - | - | - | - | - | - | -
19 | Nagpur OH to UG Scheme | Nagpur OH to UG Scheme | Not applicable | Not Applicable | Conversion of Overhead (OH) network to Underground (UG) and strengthening of distribution network in Nagpur Zone | 04.10.2024 | 04.10.2024 | 04.10.2024 | 31.03.2030 | - | - | 537 | 0 | - | - | - | - | -
20 | New consumers 2025-30 | New Consumer/Connection (NC) (2025 to 2030) Scheme | Proposal is under process | - | Infrastructure Plan for release of 1 Phase and 3 Phase HT/LT new Service Connections for FY 2025-26 to FY 2029-30 | 01.04.2025 | - | - | 31.03.2030 | - | - | - | 0 | - | - | - | - | -
21 | P:IE | P:IE | Districtwise approval List attached is received | Districtwise approval List attached is received | Intensive electrification works in already electrified villages including release of residential, commercial, Industrial, Street light, PWW conns. | 01.04.2007 | 01.04.2007 | - | 31.03.2015 | 31.03.2015 | 31.03.2015 | 187.8 | 187.8 | - | - | - | - | Nil
22 | P:SI | P:SI | Districtwise approval List attached | Districtwise approval List attached | Establishment of new 33 kV s/s & Augmentation of existing 33 kV s/s. | 01.04.2007 | 01.04.2007 | - | 31.03.2015 | 31.03.2015 | 31.03.2015 | 627.81 | 627.81 | - | - | - | - | Nil
23 | RDSS (PMA) | RDSS (PMA) | GoI Approval No. 02:10:RDSS:2021:I:MSEDCL dtd. 22.09.2022 | 22.09.2022 | RDSS Project Management | 10.12.2021 | _ | _ | 21.09.2026 | _ | _ | 26.96 | _ | NA | NA | NA | NA | NA
24 | RDSS-Dvp of Particular Vulnerable Tribal Grp(PVTG) | PM JANMAN (Prime Minister Jan jatiya adivasi Nyay Maha Abhiyaan) | Proposal is under process | - | Electrification of unelectrified PVTG habitations and households | 15.12.2023 | - | 15.12.2023 | 31.03.2025 | - | WIP | 30.5 | 0.25 | - | - | - | - | -
25 | RDSS-System Strenghtening & Modernization | RDSS-System Strenghtening & Modernization | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
26 | SIDBI Cluster Development Fund (CDF) | SIDBI Cluster Development Fund (CDF) | Proposal is under process | - | System Strengthening in MIDC, Industrial and Extended Industrial areas | 14.08.2024 | 14.08.2024 | 14.08.2024 | 31.03.2026 | - | 0 | 250 | 0 | - | - | - | - | -
27 | SPA:PE | SPA:PE | Districtwise approval List attached | Districtwise approval List attached | Relese of Ag. conns. | 01.04.2007 | 01.04.2007 | - | 31.03.2010 | 31.03.2015 | 31.03.2015 | 2949 | 2949 | - | - | - | - | Nil
28 | Special Assistance-Nagpur & Pune System Strengthening | Proposal is under process | Proposal is under process | NA | Strengthening of distribution network in Nagpur & Pune Zone | 10.10.2024 |  |  | 31.03.2026 |  |  | 155.73 | - | - | - | - | - | -
29 | Sukanu Samiti for 2019-20 | Sukanu Samiti Scheme | Not applicable | Not Applicable | Provision of Express feeders for industrial consumers with funds sanctioned by District Industries Centre (DIC) | - | - | - | - | - | - | - | 0.25 | - | - | - | - | -
30 | System Improvement Scheme | System Improvement Scheme | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
31 | System Strengthening (MSKVY 2.0) | System Strengthening (MSKVY 2.0) | Applied for approval vide letter no. 32549 Dtd: 15.10.2024 | Awaiting | To provide day time and power supply to 30 % Ag Consumers before March-2025 and all the 45 lacks Ag consumers before March 2029 | 09.08.2023 | - | 15.11.2023 | 31.03.2029 | - | WIP | 2354.37 | 757.47 | - | - | - | - | -
32 | TSP Grant substation scheme | Substation Errection and allied works in Tribal Area under TSP | Proposal is under process | - | Substation errection at Toranmal Dist: Nandurbar | 13.03.2024 | - | 13.03.2024 | 31.03.2025 | - | WIP | 72 | 10.81 | - | - | - | - | -
33 | Underground works of extended area of Baramati Municipal Corporation | Conversion Overhead network to underground network and strengthening of distribution network in the extended area of Baramati Municipl Corporation | Not applicable | Not applicable | System Strengethening | 10.08.2020 | 10.08.2020 | 10.08.2020 | 31.03.2023 | 31.03.2025 | 0 | 103.62 | 75 | - | - | - | - | -
34 | Back log | Back log | - | - | Ag. pump energisation to remove backlog of Ag. pumps from 18 nos. of backlog districts (Akola, Washim, Amravati, Yavtmal, Wardha, Bhandara, Gondia, Chandrapur, Gadchiroli, Jalna, Parbhani, Hingoli, Beed, Nanded, Thane, Raigad, Sindhudurg and Ratnagiri) under the scheme of removal of regional imbalance of Ag. pump energisation.. | 2008-09 | - | 2008-09 | - | 2015-16 | 2021-22 | 40 | 40 | - | - | - | - | Nil
35 | DDF/NON DDF | Dedicated Distribution Facility (DDF) Scheme | Not applicable | Not Applicable | Providing Dedicated Distribution Facility (DDF) to applicants | - | - | - | - | - | - | - | 3532.31 | - | - | - | - | Work is always going to be in progress
36 | Rural Electrification | Rural Electrification | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
37 | MIDC Interest free Loan Scheme | MIDC Interest free Loan Scheme | MERC/Capex/2017-18/4783 | 28.11.2017 | Creating Infrastructure for release of power supoply to inductrial consumers in MIDC Area | 28.11.2017 | 28.11.2017 | 28.11.2017 | - | 06.04.2022 | - | 98.47 | 77.36 | - | - | - | - | -
Financing Plan
(Rs. Crore)
| Project Number | MERC Approval No. | MERC Approval Date | Grant | Source of Financing for Capital Expenditure
[5 empty] | Internal Accruals | GOM Equity | GOM/ GOI Grant | Debt
[8 empty] | Loan Amount | Interest Rate (% p.a.) | Tenure of Loan (years) | Moratorium Period (years) | Loan Source
| AG Policy -2020 | MERC/Capex/MSEDCL/2023-24/100 | 2024-02-05 |  | - | 100% GoM Equity | - | - | - | - | - | -
| Ag Special Package for Vidarbha & Marathwada | MERC/Capex/MSEDCL/2019-20/026 | 17.01.2020 |  | - | - | 100 % GoM Grant | - | - | - | - | -
| DPDC / Non-Tribal | MERC /CAPEX/2019-20/for DPDC 2019-20 | 06.05.2020 |  | - | - | 100% GOM Grant | - | - | - | - | -
| DPDC / SCP (Loan up to 2012-13) | MERC /CAPEX/2019-20/for DPDC 2019-20 | 06.05.2020 |  | - | - | 100% GOM Grant | - | - | - | - | -
| DPDC / TSP + OTSP | MERC /CAPEX/2019-20/for DPDC 2019-20 | 06.05.2020 |  | - | - | 100% GOM Grant | - | - | - | - | -
| Evacuation of Power from EHV Substation | MERC/Capex/2021-22/312 | 13.07.2021 |  | 44.47 | - | Nil | 177.54 | 10.25% | 10 | 3 | REC Limited
| Evacuation of Power from EHV Substation (Phase-III) | MERC/Capex/2022-23/673 | 26.12.2022 |  | 31.162 | - | - | 124.648 | 10.25% | 10 | 3 | REC Limited
| High Loss Feeder | MERC/Capex/2018-19/1258 | 11.10.2018 |  | 72.99 | Nil | Nil | 243.21 | 10.9% | 10 | 3 | REC Limited
| MIDC Network Strengthening | MERC/Capex/2021-22/315 | 22.07.2021 |  | 56.38 | - | - | 190 | Interest Free | 50 | Nil | Government of India/Maharashtra
| New consumers | MERC/Capex/2021-22/086 | 02.03.2022 |  | 121.04 | Nil | Nil | 2617.75 | 10.25% | 15 | - | PFC Limited
| RDSS-Loss Reduction Part B | MERC/Capex/MSEDCL/2023-24/0179 | 2024-03-11 |  | Nil | Nil | 3296.52 | 2197.68 | - | - | - | -
| RDSS-Raynagar Colony Solapur -PMAY | MERC/Capex/MSEDCL/2023-24/179 | 11.03.2024 |  | 23.16 (40% Equity) |  | 60% Grant | - | - | - | - | -
| Shet Tale | MERC/Capex/MSEDCL/2019-20/078 | 28.01.2020 |  | - | - | 100% Grant | - | - | - | - | -
| System strengthening work in Metropolitain Area | MERC/Capex/2019-20/917 | 22.10.2019 |  | 87.6 | Nil | Nil | 350.4 | 0.109 | 10 | 3 | REC Limited
| RDSS-Cyclone Resilient Network NCRMP Works | MERC/Capex/MSEDCL/2023-24/0179 | 2024-03-11 |  | Nil | Nil | 254.36 | 169.57
| Agriculture Metering | - | - |  | - | - | - | - | - | - | - | -
| DTC Metering Phase-III | - | - |  | - | - | - | - | - | - | - | -
| Evacuation of Power from EHV Substation Phase-IV Scheme | Proposal is under process | - |  | 31 | - | - | 124 | - | - | - | -
| Nagpur OH to UG Scheme | Not applicable | Not applicable |  | - | - | 100% | - | - | - | - | -
| New consumers 2025-30 | To be obtained | - |  | 121.04 | - | - | 2617.75 | 10.25% | 15 | - | PFC Limited
| P:IE | - | - |  | - | - | - | 187.8 | - | - | - | REC
| P:SI | - | - |  | - | - | - | 627.81 | - | - | - | REC
| RDSS (PMA) | GoI Approval No. 02:10:RDSS:2021:I:MSEDCL dtd. 22.09.2022 | 2022-09-22 |  | Nil | Nil | 26.96 | 16.18 | - | - | - | -
| RDSS-Dvp of Particular Vulnerable Tribal Grp(PVTG) | Proposal is under process | - |  | - | - | 100% Grant |  | - | - | - | -
| RDSS-System Strenghtening & Modernization | - | - |  |  | - | - | - | - | - | - | -
| SIDBI Cluster Development Fund (CDF) | Proposal is under process | - |  | - | - | 5% | 237.5 | - | - | Nil | SIDBI
| SPA:PE | - | - |  | - | - | - | 2949 |  | - |  | REC
| Special Assistance-Nagpur & Pune System Strengthening | Proposal is under process |  |  | - |  |  | 155.73 | Interest free loan | 50 | Nil | Government of India/Maharashtra
| Sukanu Samiti for 2019-20 | Not applicable | Not applicable |  | - | - | - | - | - | - | - | -
| System Improvement Scheme | - | - |  | - | - | - | - | - | - | - | -
| System Strengthening (MSKVY 2.0) | Applied for approval vide letter No 32549 dtd 15.10.2024 | Proposal is submitted and awaited from MERC |  | - | - | - | 2004.37 | Interest free | Not mentioned in approval | - | GOI
| TSP Grant substation scheme | Proposal is under process | - |  | - | - | 100% GOM Grant | - | - | - | - | -
| Underground works of extended area of Baramati Municipal Corporation |  |  |  | - |  | 100% Grant |  |  | -
| Back log | - | - |  | - | - | 100 % GoM Grant | - | - | - | - | -
| DDF/NON DDF | Not applicable | Not applicable |  | - | - | - | - | - | - | - | -
| Rural Electrification | - | - |  | - | - | - | - | - | - | - | -
| MIDC Interest free Loan Scheme | MERC/Capex/2017-18/4783 | 28.11.2017 |  | Nil | Nil | Nil | 98.47 | Interest Free | - | - | MIDC

## 4.2 Dist
Project Details
(Rs. Crore)
Project Details
Sr. No. | Project Code | Project Title | MERC Approval No. | MERC Approval Date | MERC Approved Cost | Debt Equity Ratio | Grant/Consumer Contribution | Approved Start Date | Actual Start Date | Approved Date of Completion | Actual Date of Completion | Benefits in Quantified Terms | Capital Expenditure | [6 empty] | Physical Progress (%) | [8 empty] | Reasons for Delay, if any
[13 empty] | Actual Capex till FY 2021-22 | Actual | Actual | Estimated | Projected | Projected | Projected | Actual Progress till FY 2021-22 | Actual | Actual | Estimated | Projected | Projected | Projected | Projected | Projected | Change in Scope of Work | Any other reason
[14 empty] | FY 2022-23 | FY 2023-24 | FY 2024-25 | FY 2025-26 | FY 2026-27 | FY 2027-28 |  | FY 2022-23 | FY 2023-24 | FY 2024-25 | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30
1 | AG Policy -2020 | AG Policy -2020 | MERC/Capex/MSEDCL/2023-24/100 | 2024-02-05 | 4212.63 | 100% Equity |  | 15.01.2021 | 15.01.2021 | 31.03.2024 | 31.03.2024 | Released connections to 354835 nos. of Ag consumers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30% | 32.5% | 23% | - | - | - | - | - | - | - | -
2 | Ag Special Package for Vidarbha & Marathwada | Ag Special Package for Vidabhrba /maratwada & maha | MERC/Capex/MSEDCL/2019-20/026 | 17.01.2020 | Phase-I-819 Crs. Phase-II 910.73 Crs. |  | 100% Grant | Phase-I 17.08.2015 Phase-II 31.10.2017 | Phase-I 17.08.2015 Phase-II 31.10.2017 | 31.03.2019 | 31.03.2019 | Released connections to 175056 nos. of Ag consumers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% |  | - | - | - | - | - | - | - | - | -
3 | DPDC / Non-Tribal | DPDC / Non-Tribal | MERC /CAPEX/2019-20/for DPDC 2019-20 | 06.05.2020 | 558.4 |  | 100% Grant | 2023-04-01 | 2023-07-01 | 2025-03-31 | WIP | Release of 1 ph. & small industrial, PWW conns. & minor S.I. works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | 87.05% | 59.44% | - | - | - | - | - | - | - | -
4 | DPDC / SCP (Loan up to 2012-13) | DPDC / SCP (Loan up to 2012-13) | MERC /CAPEX/2019-20/for DPDC 2019-20 | 06.05.2020 | 128.22 |  | 100% Grant | 2023-04-01 | 2023-09-01 | 2025-03-31 | WIP | Release of 1 ph. & Ag. conns. To SC & NB beneficiaries & electrification of Dalit Basties | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | 91.66% | 47.13% | - | - | - | - | - | - | - | -
5 | DPDC / TSP + OTSP | DPDC / TSP + OTSP | MERC /CAPEX/2019-20/for DPDC 2019-20 | 06.05.2020 | 76.4253 |  | 100% Grant | 2023-04-01 | 2023-07-01 | 2025-03-31 | WIP | Release of 1 ph. & Ag. conns. To Tribal beneficiaries & electrification of Tribal wadies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | 77.7% | 64.95% | - | - | - | - | - | - | - | -
6 | Evacuation of Power from EHV Substation | Evacuation of Power from EHV Substation (Phase-I&II) Scheme | Letter No. MERC/Capex/2021-22/312 | 13.07.2021 | 222.01 | 80% Debt, 20% Equity | Nil | 01.06.2019 | 01.06.2019 | 31.03.2023 | - | Loss reduction-464.06 MUs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39.18% | 39.6% | 40.06% | 62.6% | 100% | 0% | 0% | - | - | - | 1) Restrictions on movenment of manpower and materials due to COVID-19 1st and 2nd Wave 2) Delay in issue of permissions for laying of electric lines from NHAI, MIDC and Railway Crossings. 3) RoW Issues eg. farmers objections, local villagers, etc.
7 | Evacuation of Power from EHV Substation (Phase-III) | Evacuation of Power from EHV Substation Phase-III Scheme | Letter No. MERC/Capex/2022-23/673 | 26.12.2022 | 155.81 | 80% Debt, 20% Equity | Nil | 26.12.2022 | 26.12.2022 | 31.03.2024 | - | Loss Reduction-34.64 MUs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | - | - | 16.04% | 100% | - | - | - | - | - | Delay in financial tie up due to new prudential norms for lending to DISCOMs by Government of India.
8 | High Loss Feeder | High Loss Feeder (HLF) Scheme | Letter No. MERC/Capex/2018-19/1258 | 11.10.2018 | 316.2 | 76.91% Debt, 23.08% Equity | Nil | 11.06.2018 | 04.10.2018 | 31.03.2020 | - | Additional Sales-864.04 MUs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | - | - | - | - | - | - | - | - | 1) Poor response to tenders 2) Restrictions on movement of manpower and materials due to COVID-19 1st & 2nd Wave 3) Opposition from consumers for replacement of meters 4) RoW Issues eg. space constraints in providing poles for AB cables. 5) Delay in receipt of Road Digging permissions from local authorities
9 | MIDC Network Strengthening | MIDC Network Strengthening Scheme | Letter No. MERC/Capex/2021-22/315 | 22.07.2021 | 267.37 | 78.91% Debt, 21.08% Equity | Nil | 22.07.2021 | 22.07.2021 | 31.03.2022 | - | 1) Reduction in breakdowns and interruptions-15.11% 2) Additional Sales of Energy-1033.36 MUs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 21.08% | 21.85% | 56.1% | 100% | 0% | 0% | - | - | - | 1) Delay in financial tie up for scheme as grants were not sanctioned by MIDC and Government of Maharashtra. 2) Delay in financial tie up due to new prudential norms for lending to DISCOMs by Government of India. 3) Long Term Interest free loan sanctioned by Government of India (GoI) under Special Assistance to States for Capital Investment Scheme FY 2022-23
10 | New consumers | New Consumer/Connection (NC) Scheme | Letter No. MERC/Capex/2021-22/086 | 02.03.2022 | 2738.79 | 95.58% Debt, 4.42% Equity | - | 01.04.2019 | 01.04.2019 | 31.03.2025 | - | Incremental Sales-Rs 787.07 Crores to Rs 951.88 Crores | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44.07% | 54.65% | 71.77% | 100% | 0% | 0% | 0% | - | - | - | -
11 | RDSS-Loss Reduction Part B | 0 | MERC/Capex/MSEDCL/2023-24/0179 | 2024-03-11 | 5494.2 | 40% Debt & 60 % Grant | Rs. 3,296.52 Cr | 2023-04-06 | 2023-04-06 | 2026-03-31 | NA | 1. To reduce AT&C Loss to 13% by FY 2024-25 2. To reduce ACS-ARR Gap to zero by FY 2024-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | - | 4% | 30% | 76% | - | - | - | 0 | NA | NA
12 | RDSS-Raynagar Colony Solapur -PMAY | RDSS-Raynagar Colony Solapur -PMAY | Letter No. MERC/Capex/MSEDCL/2023-24/179 | 11.03.2024 | 57.9 | 40% Debt | 60% Grant | 17.01.2022 | 07.04.2022 | 31.03.2026 | - | Release of 30,000 EWS Household connections | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 20.69% | 55.26% | 100% | 0% | 0% | - | - | - | -
13 | Shet Tale | Shet Tale | MERC/Capex/MSEDCL/2019-20/078 | 28.01.2020 | 749.72 |  | 100% Grant | 27.02.2017 | 01.11.2018 | 31.12.2020 | 31.12.2020 | Commissioned 12 nos. of new Substations, 9 nos. of Add. Power Transformers & 5 nos. of Augmentation Power Transformers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | - | - | - | - | - | - | - | - | - | -
14 | System strengthening work in Metropolitain Area | System Strengthening in Metropolitan Region (SSMR) Scheme | Letter No. MERC/Capex/2019-20/917 | 22.10.2019 | 438 | 80% Debt, 20% Equity | Nil | - | 06.11.2018 | 31.03.2021 | WIP | 1) Breakdown Reduction-75% 2) Breakdown converted to additional Sales-110.33 MUs 3) Load Growth-50 MW, 401.50 MUs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90.05% | 90.35% | 95% | 97.44% | 100% | 0% | 0% | - | - | - | 1) Delay in acquisition of land for substations 2) Delay in receipt of RI permission from local authorities 3) RoW Issues due to objection from local people, etc 4) Restrictions on movement of manpower and material due to COVID-19 1st & 2nd Wave
15 | RDSS-Cyclone Resilient Network NCRMP Works | - | MERC/Capex/MSEDCL/2023-24/0179 | 2024-03-11 | Rs. 423.93 Cr | 60 % Grant & 40% Loan | Rs. 254.36 Cr | 2023-04-06 | 2023-04-06 | 2026-03-31 | NA | 1. To reduce AT&C Loss to 13% by FY 2024-25 2. To reduce ACS-ARR Gap to zero by FY 2024-25 | Nil | Nil | 12% | 100% | 0% | 0% | 0% | Nil | Nil | 12% | 100% | 0% | 0% | 0% | 0% | 0%
16 | Agriculture Metering | - | - | - | - | - | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | - | - | - | - | - | - | - | - | - | -
17 | DTC Metering Phase-III | - | - | - | - | - | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | - | - | - | - | - | - | - | - | - | -
18 | Evacuation of Power from EHV Substation Phase-IV Scheme | Evacuation of Power from EHV Substation Phase-IV Scheme | To be obtained | - | - | - | Nil | 13.09.2024 | 31.03.2028 | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | - | - | 3.22% | 51.61% | 100% | - | - | - | - | -
19 | Nagpur OH to UG Scheme | Nagpur OH to UG Scheme | To be obtained | Not Applicable | 537 |  | 100% Grant | 04.10.2024 | 31.03.2030 | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 1.86% | 8.56% | 27.18% | 45.81% | 70.94% | 100% | - | -
20 | New consumers 2025-30 | New Consumer/Connection (NC) 2025-2030 Scheme | To be obtained | - | - | 80% Debt, 20% Equity | - | - | - | 31.03.2030 | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 20% | 40% | 60% | 80% | 100% | - | -
21 | P:IE | P:IE | Districtwise approval List attached | - | 187.8 | - | - | 01.04.2007 | 01.04.2007 | 31.03.2015 | 31.03.2015 | Intensive electrification works in already electrified villages including release of residential, commercial, Industrial, Street light, PWW conns. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | - | - | - | - | - | - | - | - | - | -
22 | P:SI | P:SI | Districtwise approval List attached | - | 627.81 | - | - | 01.04.2007 | 01.04.2007 | 31.03.2015 | 31.03.2015 | Establishment of new 33 kV s/s & Augmentation of existing 33 kV s/s. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | - | - | - | - | - | - | - | - | - | -
23 | RDSS (PMA) | RDSS (PMA) | GoI Approval No. 02:10:RDSS:2021:I:MSEDCL dtd. 22.09.2022 | 22.09.2022 | 26.96 | 40% Debt & 60 % Grant | 16.18 | 10.12.2021 | 10.12.2021 | 21.09.2026 | - | RDSS Project Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 8.086% | 26.74% | 27.82% | 22.11% | 0% | 0% | - | - | - | -
24 | RDSS-Dvp of Particular Vulnerable Tribal Grp(PVTG) | RDSS-Dvp of Particular Vulnerable Tribal Grp(PVTG) | Approval is submitted and Awaited from MERC | - | 30.5 |  | 100 % Grant | 15.12.2023 | 15.12.2023 | 31.03.2025 | WIP | Electrification of unelectrified PVTG habitations and households | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | - | 10% | 90% | - | - | - | - | - | - | -
25 | RDSS-System Strenghtening & Modernization | - | - | - | - | - | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | - | - | - | - | - | - | - | - | - | -
26 | SIDBI Cluster Development Fund (CDF) | SIDBI Cluster Development Fund (CDF) | Proposal is under process | - | 250 | 95% Debt | 5% Grant | 14.08.2024 | 14.08.2024 | 31.03.2026 | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | - | - | 20% | 100% | - | - | - | - | - | -
27 | SPA:PE | SPA:PE | Districtwise approval List attached | - | 2949 | - | - | 01.04.2007 | 01.04.2007 | 31.03.2010 | 31.03.2015 | Relese of Ag. conns. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | - | - | - | - | - | - | - | - | - | -
28 | Special Assistance-Nagpur & Pune System Strengthening | Special Assistance Nagpur & Pune System Strengthening Scheme | Proposal is under process | - | 155.73 | 100% Debt | Nil | 10.10.2024 |  | 31.03.2026 | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 12.84% | 100% | 0% | 0% | - | - | - | -
29 | Sukanu Samiti for 2019-20 | Sukanu Samiti Scheme | Not applicable | Not Applicable | - | - | 100% Grant/Consumer Contribution | - | - | - | - | Provision of Express feeders for industrial consumers with funds sanctioned by District Industries Centre (DIC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | - | 100% | 0% | - | - | - | - | - | - | -
30 | System Improvement Scheme | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
31 | System Strengthening (MSKVY 2.0) | System Strengthening (MSKVY 2.0) | Applied for approval vide letter no. 32549 Dtd: 15.10.2024 | Awaiting | 2354.37 | Debt-Rs. 2004.37 Crs. | Grant- Rs. 350 Crs. | 09.08.2023 | 05.11.2023 | 31.03.2029 | WIP | To provide data and power supply to 30 % Ag Consumers before March-2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | - | 198.64 | 215.73 | - | - | - | - | - | WIP | No delay
32 | TSP Grant substation scheme | TSP Grant substation scheme | Proposal is under process | - | 72 |  | 100 % Grant | 13.03.2024 | 13.03.2024 | 31.03.2025 | WIP | Substation errection at Toranmal Dist: Nandurbar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | - | 20% | 100% | - | - | - | - | - | - | -
33 | Underground works of extended area of Baramati Municipal Corporation | Underground works of extended area of Baramati Municipal Corporation Scheme | Not applicable | Not applicable | 103.62 |  | 100% Grant | 10.08.2020 | 10.08.2020 | 31.03.2023 | WIP | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.36% | 59.52% | 72.37% | 100% | 0% | 0% | - | - | - | - | Poor progress of contractor M/s Dhanlaxmi Electricals JV M/s leading to termination of contract
34 | Back log | Back log | - | - | 40 |  | 100% Grant | 2018-19 | 2018-19 | 2021-22 | 2021-22 | Released connections to 3523 nos. of Ag consumers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | 100% | - | - | - | - | - | - | - | - | Yearly scheme
35 | DDF/NON DDF | Dedicated Distribution Facility (DDF) Scheme | Not applicable | Not Applicable | - | Nil | 100% Consumer Contribution | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | - | - | - | - | - | - | - | - | - | -
36 | Rural Electrification | Rural Electrification | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
37 | MIDC Interest free Loan Scheme | MIDC Interest free Loan Scheme | Letter No. MERC/Capex/2017-18/4783 | 28.11.2017 | 98.47 | 100% Debt | Nil | 28.11.2017 | 28.11.2017 | - | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 100% | - | - | - | - | - | - | - | - | -

## CBA_DIST
CAPEX SCHEME WISE DETAILS_ DATA GAP SET 1
Sr.No. | Name | Scheme Ref | Status of CBA Submission
DPR Schemes
1 | AG Policy -2020 | MERC/Capex/MSEDCL/2023-24/100 | Ag Policy 2020 Scheme by GoM has extended electricity supply to Ag Consumers which will ultimately improve the sustainability of MSEDCL & help farmers to improve their productivity. Ag consumer tariff is a subsidised tariff hence no financial returns are expected. This policy will benefit society by improving the living standard of farmers.
2 | Ag Special Package for Vidabhrba /maratwada & maha | MERC/Capex/MSEDCL/2019-20/026 | Ag Special Package Scheme by GoM has extended electricity supply to Ag Consumers which will ultimately improve living standard of beneficiaries. Scheme is driven by social developmental motives hence no monetary benefits are envisaged.
3 | DPDC / Non-Tribal | MERC /CAPEX/2019-20/for DPDC 2019-20 | DPDC Schemes by GoM has extended electricity supply to deprived sections of the society, which will ultimately improve living standard of beneficiaries
4 | DPDC / SCP (Loan up to 2012-13) | MERC /CAPEX/2019-20/for DPDC 2019-20 | DPDC Schemes by GoM has extended electricity supply to deprived sections of the society, which will ultimately improve living standard of beneficiaries
5 | DPDC / TSP + OTSP | MERC /CAPEX/2019-20/for DPDC 2019-20 | DPDC Schemes by GoM has extended electricity supply to deprived sections of the society, which will ultimately improve living standard of beneficiaries
6 | Evacuation of Power from EHV Substation | MERC/Capex/2021-22/312 | The scheme is implemented for following benefits • Utilization of EHV Substations commissioned by MSETCL. • Reducing overloading of existing network, improvement in reliability and meeting load of prospective consumers.
7 | Evacuation of Power from EHV Substation (Phase-III) | MERC/Capex/2022-23/673 | The scheme has achieved following benefits • Utilization of EHV Substations commissioned by MSETCL. • Reducing overloading of existing network, improvement in reliability and meeting load of prospective consumers.
8 | High Loss Feeder | MERC/Capex/2018-19/1258 | The scheme has achieved following benefits • Increase in revenue and reduction in losses. • Reduction of power supply interruptions and accidents. • Improvement in reliability of power supply due to introduction of HVDS. • Meeting Universal Supply Obligation The turnkey tenders for execution of the project were floated in FY 2018-19. After execution of the scheme, MSEDCL has achieved significant reduction of losses of few metro and urban feeders such as Thane, Navi Mumbai, Panvel, Osmanabad etc.
9 | MIDC Network Strengthening | MERC/Capex/2021-22/315 | The scheme has achieved following benefits • 24x7 reliable power supply to consumers in high revenue pocket areas. • Reduction of power supply interruptions and breakdowns. • Reducing overloading of existing network and meeting load of prospective consumers. • Meeting Universal Supply Obligation. The turnkey tenders for for execution of projects were floated in FY 2018-19. After Execution of scheme,
10 | New consumers | MERC/Capex/2021-22/086 | The scheme is implemented for following benefits • Increase in revenue. • Meeting Universal Supply Obligation.
11 | RDSS-Loss Reduction Part B | MERC/Capex/MSEDCL/2023-24/0179 | The scheme has achieved following benefits • Increase in revenue and reduction in losses. • Reduction of power supply interruptions and accidents. •Improvement in reliability of power supply due to introduction of HVDS. • Meeting Universal Supply Obligation.
12 | RDSS-Raynagar Colony Solapur -PMAY | MERC/Capex/MSEDCL/2023-24/179 | New Ag connections are released to meet statutory obligation of Electricity Act 2003.
13 | Shet Tale | MERC/Capex/MSEDCL/2019-20/078 | East Vidarbha Scheme (Shet-tale) by GoM is implemented to extend electricity supply to Ag Consumers which will ultimately improve living standard of beneficiaries. Scheme is driven by social developmental motives hence no monetary benefits are envisaged.
14 | System strengthening work in Metropolitain Area | MERC/Capex/2019-20/917 | The scheme is implemented delivering following benefits. • 24x7 reliable power supply to consumers in high revenue pocket areas. • Reduction of power supply interruptions and breakdowns. • Reducing overloading of existing network and meeting load of prospective consumers. • Meeting Universal Supply Obligation
15 | RDSS-Cyclone Resilient Network NCRMP Works | MERC/Capex/MSEDCL/2023-24/0179 | The scheme has following benefits: • Increase in revenue and reduction in losses. • Reduction of power supply interruptions and accidents due to Underground Cabling Works. • System Strengthening of Cyclone Prone Areas • Meeting Universal Supply Obligation.
16 | P:IE | Districtwise approval List attached is received | Scheme Closed long back.
17 | P:SI | Districtwise approval List attached | Scheme Closed long back
18 | RDSS (PMA) | GoI Approval No. 02:10:RDSS:2021:I:MSEDCL dtd. 22.09.2022 | Scheme Closed long back
19 | SPA:PE | Districtwise approval List attached | Scheme Closed long back.
DPR Schemes- Approval in Process
20 | Evacuation of Power from EHV Substation (Phase-IV) | Proposal is under process | The benefits of the scheme are as follows • Utilization of EHV Substations commissioned by MSETCL. • Reducing overloading of existing network, improvement in reliability and meeting load of prospective consumers.
21 | New Consumers 2025-2030 | Proposal is under process | The benefits of the scheme are as follows • Increase in revenue. • Meeting Universal Supply Obligation.
22 | RDSS-Dvp of Particular Vulnerable Tribal Grp(PVTG) | Proposal is under process | RDSS PVTG scheme by Government of India is implemented to extend electricity supply to deprived sections of the society, which will ultimately improve living standard of beneficiaries.
23 | SIDBI Cluster Development Fund (CDF) | Proposal is under process | The benefits of the scheme are as follows • Increase in sales. • Reduction in interruptions for consumers.
24 | Special Assistance-Nagpur & Pune System Strengthening | Proposal is under process | The scheme has following benefits. • Reduction of AT&C losses. • Reducing power supply interruption to existing consumers. • Increase in Revenue.
25 | Nagpur OH to UG | scheme not submitted to MERC for in principal approval | The benefits of the scheme are as follows • Reduction in AT&C losses. • Reduction in accidents in densely populated areas.
26 | System Strengthening (MSKVY 2.0) | Applied for approval vide letter no. 32549 Dtd: 15.10.2024 | The benefits of the scheme are as follows • 24X7 Power Supply to agriculture consumers. • To promote renewable energy and to reduce per unit cost of energy. Presently power supplied to the agricultural consumers is during day and night-time on rotational basis. The night-time power supply to farmers is creating a lot of inconvenience to them and there is a constant demand for long time to provide reliable electricity supply to farmers during the daytime. So total 2782 nos. of substations are identified for solarisation of Ag feeders for giving day time power supply to farmers under MSKVY 2.0. Applied for approval vide letter no. 32549 Dtd: 15.10.2024
27 | Underground works of extended area of Baramati Municipal Corporation |  | The benefits of the scheme are as follows • Increase in revenue and reduction in losses. • Reduction of power supply interruptions and accidents. • Improvement in reliability of power supply due to introduction of HVDS. • Meeting Universal Supply Obligation.
Non DPR Schemes
28 | Back log | Non DPR Scheme | Ag Special Package Scheme for Vidarbha and Marathwada has been implemented by GoM to extend electricity supply to Ag Consumers which will ultimately improve living standard of beneficiaries. Scheme is driven by social developmental motives hence no monetary benefits are envisaged.
29 | DDF/NON DDF | Non DPR Scheme | New Ag connections are released to meet statutory obligation of Electricity Act 2003.
30 | MIDC Interest free Loan Scheme | MERC/Capex/2017-18/4783 | The following benefits are achieved from the scheme • 24x7 reliable power supply to consumers in high revenue pocket areas. • Reduction of power supply interruptions and breakdowns.
31 | Sukanu Samiti
32 | Agriculture metering
33 | DTC Metering phase III
34 | System Strengthening & Modernization
35 | System Improvement Scheme
36 | TSP Grant Substation Scheme
37 | Rural Electrification Scheme

## TOR COR_DIST
CAPEX SCHEME WISE DETAILS_ DATA GAP SET 1
Sr.No. | Name | Details of Cost Over run if any |  |  | Details of Time Over run if any
|  | Approved Cost (Rs. Crs) | Revised Cost (Rs. Crs) | Justification for Cost Overrun | Original Completion | Revised Completion | Justification for Time Overrun etc.
DPR Schemes
1 | AG Policy -2020 | 4212.63 | - | - | 31.03.2024 | - | Due to non availability of sufficient fund from GOM and re-tendering of works as per new cost data.
2 | Ag Special Package for Vidabhrba /maratwada & maha | Phase-I-819 Crs. Phase-II 910.73 Crs. | - | - | 31.03.2019 | - | Scheme is funded by GoM, therefore, work is completed to the extent of Grants by GoM
3 | DPDC / Non-Tribal | 558.4 | - | Scheme is funded by GoM, therefore, work is completed to the extent of Grants by GoM | 31.03.2025 | - | Scheme is funded by GoM, therefore, work is completed to the extent of Grants by GoM
4 | DPDC / SCP (Loan up to 2012-13) | 128.22 | - | Scheme is funded by GoM, therefore, work is completed to the extent of Grants by GoM | 31.03.2025 | - | Scheme is funded by GoM, therefore, work is completed to the extent of Grants by GoM
5 | DPDC / TSP + OTSP | 76.4253 | - | Scheme is funded by GoM, therefore, work is completed to the extent of Grants by GoM | 31.03.2025 | - | Scheme is funded by GoM, therefore, work is completed to the extent of Grants by GoM
6 | Evacuation of Power from EHV Substation | 222.01 | 222.01 | No cost overrun | 31.03.2023 | 31.09.2025 | 1) Restrictions on movenment of manpower and materials due to COVID-19 1st and 2nd Wave 2) Delay in issue of permissions for laying of electric lines from NHAI, MIDC and Railway Crossings. 3) RoW Issues eg. farmers objections, local villagers, etc.
7 | Evacuation of Power from EHV Substation (Phase-III) | 155.81 | 155.81 | No cost overrun | 31.03.2024 | 31.09.2025 | Delay in financial tie up due to new prudential norms for lending to DISCOMs by Government of India.
8 | High Loss Feeder | 316.2 | 316.2 | No cost overrun | 31.03.2020 | 31.03.2022 | 1) Poor response to tenders 2) Restrictions on movement of manpower and materials due to COVID-19 1st & 2nd Wave 3) Opposition from consumers for replacement of meters 4) RoW Issues eg. space constraints in providing poles for AB cables. 5) Delay in receipt of Road Digging permissions from local authorities
9 | MIDC Network Strengthening | 267.37 | 267.37 | No cost overrun | 31.03.2022 | 31.09.2025 | 1) Delay in financial tie up for scheme as grants were not sanctioned by MIDC and Government of Maharashtra. 2) Delay in financial tie up due to new prudential norms for lending to DISCOMs by Government of India. 3) Long Term Interest free loan sanctioned by Government of India (GoI) under Special Assistance to States for Capital Investment Scheme FY 2022-23
10 | New consumers | 2738.79 | 2738.79 | No cost overrun | 31.03.2025 | 31.03.2025 | No time overrun
11 | RDSS-Loss Reduction Part B | 5494.2 |  | Scheme is ongoing | 31.03.2026 | 31.03.2027 | No time overrun
12 | RDSS-Raynagar Colony Solapur -PMAY | 57.9 | 57.9 | Scheme is ongoing | 31.03.2025 | 31.03.2025 | No time overrun
13 | Shet Tale | 749.72 | - | - | 27.02.2017 | N.A. | -
14 | System strengthening work in Metropolitain Area | 438 | 438 | No cost overrun | 31.03.2021 | 31.09.2025 | 1) Delay in acquisition of land for substations 2) Delay in receipt of RI permission from local authorities 3) RoW Issues due to objection from local people, etc 4) Restrictions on movement of manpower and material due to COVID-19 1st & 2nd Wave
15 | RDSS-Cyclone Resilient Network NCRMP Works |  |  | Scheme Ongoing; not applicable |  |  | Scheme Ongoing; not applicable
16 | P:IE | 187.8 | - | - | 31.03.2015 | - | -
17 | P:SI | 627.81 | - | - | 31.03.2015 | - | -
18 | RDSS (PMA) | 26.96 | - |  | 21.09.2026 | -
19 | SPA:PE | 2949 | - | - | 31.03.2015 | - | -
DPR Schemes- Approval in Process
20 | Evacuation of Power from EHV Substation (Phase-IV) | 155 | 155 | No cost overrun | 31.03.2028 | 31.03.2028 | No time overrun | Sukanu Samiti for 2019-20
21 | New Consumers 2025-2030 | 3750 | 3750 | No cost overrun | 31.03.2030 | 31.03.2030 | No time overrun
22 | RDSS-Dvp of Particular Vulnerable Tribal Grp(PVTG) | 30.5 | - | - | 31.03.2025 | - | -
23 | SIDBI Cluster Development Fund (CDF) | 250 | 250 | No cost overrun | 31.03.2026 | 31.03.2026 | No time overrun
24 | Special Assistance-Nagpur & Pune System Strengthening | 155.73 | 155.73 | No cost overrun | 31.03.2026 | 31.03.2026 | No time overrun
25 | Nagpur OH to UG | 537 | 537 | No cost overrun | 31.03.2030 | 31.03.2030 | No time overrun
26 | System Strengthening (MSKVY 2.0) | Debt=2004.37; Grant= 787.50 Total= 2791.87 | Debt=2004.37; Grant= 787.50 Total= 2791.88 | No cost overrun | 31.03.2029 | 31.03.2029 | No time overrun
27 | Underground works of extended area of Baramati Municipal Corporation | 103.62 | 103.62 | No cost overrun | 31.03.2023 | 31.03.2025 | Poor progress of contractor M/s Dhanlaxmi Electricals JV M/s leading to termination of contract
Non DPR Schemes
28 | Back log | 40 | - | - | - | - | -
29 | DDF/NON DDF | Ongoing | Ongoing | Not Applicable as scheme is ongoing | Ongoing | Ongoing | Not Applicable as scheme is ongoing
30 | MIDC Interest free Loan Scheme | 98.47 | 98.47 | No cost overrun | - | 06.04.2022 | 1) Delay in acquisition of land for substations 2) Delay in receipt of RI permission from local authorities 3) RoW Issues & standing crops due to objection from local people, etc
31 | Sukanu Samiti
32 | Agriculture metering
33 | DTC Metering phase III
34 | System Strengthening & Modernization
35 | System Improvement Scheme
36 | TSP Grant Substation Scheme
37 | Rural Electrification Scheme

## P-SI
Details of DPR PSI schemes apporved by MERC
Sr. No. | Scheme Code No. | Name of the Scheme | Approved Cost
1 | MSEDCL/FY 10/46 | New S/Stn. at Satana in Nashik District | 1.9502
|  | New S/Stn. at Kalikutti & Power House in Nashik District | 9.9179
2 | MSEDCL/FY 07/08 | Nanded City | 35
3 | MSEDCL/FY 07/08 | Augumentation of Sub-transmmision & distribution capacities (Krushi Vikas Yojana) in Nashik (R), Nashik (U), Jalgaon, Ahmednagar | 108.39
4 | MSEDCL/FY 10/20 | Reorientation of 22 kV & 11 kV feeders for power evacuation from 132/22/11 kV Rastapeth GIS & 220/22 kV Magarpatta EHV s/stn. | 51.74
5 | MSEDCL/FY 10/29 | Establishment of 6 nos. of new 33/11 kV s/stns. in Jalna district | 14.61
6 | MSEDCL/FY 10/42 | New 33/11 KV 8 Nos. of s/stn. in Beed | 21.1939
7 | MSEDCL/FY 10/47 | Establishment of 4 Nos. of S/stn. in Baramati District | 9.4988
|  | Establishment of new 33/11 kV s/stn. at Mandavgan in Ahmednagar district | 3.9258
8 | MSEDCL/FY 11/01 | Establishment of 4 nos.of new 33/11Kv s/s & 3 nos. of Addl. Power T/F at Baramati Circle | 20.8149
9 | MSEDCL/FY 11/02 | New 31 nos of 33/11 KV S/st & 20 nos of addl. power T/F in Solapur District | 97.8851
10 | MSEDCL/FY 11/04 | New 09 nos. of 33/11 kV S/stn, 02 nos. of additional power transformer in Buldhana District | 25.9894
11 | MSEDCL/FY 11/05 | New 08 nos. of 33/11 kV S/stn, 01 no. of Augmentation & 02 nos. of additional power transformer in Hingoli District | 34.7509
12 | MSEDCL/FY 11/07 | Swtiching Station at Ambadi, Kudus & Abhitghar in Wada District of Vasai Circle | 20.102
13 | MSEDCL/FY 11/09 | Establishment of 9 nos. of new 33/11kV s/stn. in Washim Dist. | 20.9615
14 | MSEDCL/FY 12/02 | Release of all type of connections and creating abckup infrastructure in Beed district. | 121.1012
15 | MSEDCL/FY 13/10 | In principel approval for laying of cable for incomer of 22/22 KV switching at Abhitghar & Kudus in Wada Taluka | 18.27
16 | MSEDCL/FY 14/01 | Establishment of new 22 KV feeders in Virar & Vasai | 11.713
Establishment of new S/stn in Buldhana
Establishment of new 1 S/stn in Beed
TOTAL |  |  | 627.8147

## P-IE
Details of DPR PIE schemes apporved by MERC
Sr. No. | Name of the Scheme | MERC Scheme Code no. | MERC approval Lr. No. and Date | Approved Cost (Rs in Crs)
1 | PIE Scheme for Raigad Dist | MSEDCL/FY 10/ 05 | 296/ 15.03.2010 | 18.6276
2 | PIE Scheme for Ahmednagar Dist | MSEDCL/FY 10/ 38 | 1245/ 05.10.10 | 82.9167
3 | PIE Scheme for Sindhudurg Dist | MSEDCL/FY 11/ 03 | 1384/ 18.10.10 | 3.3489
4 | PIE Scheme for Aurangabad Dist | MSEDCL/FY 11/ 03 | 1384/ 18.10.10 | 32.3351
5 | PIE Scheme for Ratnagiri Dist | MSEDCL/FY 10/ 37 | 1404/ 20.10.10 | 8.3187
6 | PIE Scheme for Jalna - I Dn. | MSEDCL/FY 10/ 37 | 1404/ 20.10.10 | 14.3221
7 | PIE Scheme for Jalna - II Dn. | MSEDCL/FY 10/ 37 | 1404/ 20.10.10 | 3.5188
8 | PIE Scheme for Parbhani Dn. | MSEDCL/FY 10/ 37 | 1404/ 20.10.10 | 8.9465
9 | PIE Scheme for Latur Dist. | MSEDCL/FY 11/ 10 | 1568 / 15.11.10 | 15.47
TOTAL |  |  |  | 187.8044

## SPA-PE
Details of DPR SPA schemes apporved by MERC
Sr. No. | Scheme Code No. | MERC approval Lr. No. and Date | Name of the Scheme | Approved Cost
1 | MSEDCL/FY10/02 | 993/25.05.09 | Ag pump scheme in Sangli District for 7000 pumps | 72
2 | MSEDCL/FY10/11 | 2574/11.11.09 | Ag pump scheme in Buldhana District for 10922 pumps | 62.57
3 | MSEDCL/FY10/17 | 2574/11.11.09 | Ag pump scheme in Satara District for 7653 pumps | 48.36
4 | MSEDCL/FY09/05 | 335 / 27.01.10 | Ag pump scheme in Ahmadnager District for 6918 pumps | 50.38
5 | MSEDCL/FY10/03 | 335 / 27.01.10 | Ag pump scheme in Solapur District for 16581 pumps | 77.94
6 | MSEDCL/FY10/06 | 335 / 27.01.10 | Ag pump scheme in Beed District for 10932 pumps | 67.62
7 | MSEDCL/FY10/21 | 335 / 27.01.10 | Ag pump scheme in Baramati circle for 7922 pumps | 76.3
8 | MSEDCL/FY10/07 | 340 / 28.01.10 | Ag pump scheme in Latur District for 3227 pumps | 28.83
9 | MSEDCL/FY10/16 | 340 / 28.01.10 | Ag pump scheme in Manmad Division of Nashik District | 10.31
10 | MSEDCL/FY10/28 | 340 / 28.01.10 | Ag pump scheme in Jalna District for 2300 pumps | 10.16
11 | MSEDCL/FY10/30 | 340 / 28.01.10 | Ag pump scheme in Hingoli District for 1913 pumps | 10.46
12 | MSEDCL/FY10/32 | 340 / 28.01.10 | Ag pump scheme in Nandurbar District for 2163 pumps | 13.49
13 | MSEDCL/FY10/34 | 340/ 28.01.10 | Ag pumps in Parbhani District for 1900 pumps | 10.22
14 | MSEDCL/FY10/36 | 340 / 28.01.10 | 1286 nos. of Ag pump energisation scheme in Jalgaon District | 8.76
15 |  |  | Ag pumps in Satana Division of Nashik District | 9.9
16 | MSEDCL/FY10/23 | 330/18.03.10 | Ag pump scheme in Amravati District for 6346 pumps | 31.43
17 | MSEDCL/FY10/24 | 330/18.03.10 | Ag pump scheme in Gondia District for 1496 pumps | 11.66
18 | MSEDCL/FY10/40 | 330/18.03.10 | Ag pump scheme in Buldhana District for 6155 pumps | 67.32
19 | MSEDCL/FY10/39 | 349/19.03.10 | Ag pump scheme in Bhandara District for 2292 pumps | 17.32
20 | MSEDCL/FY10/44 | 014/01.04.10 | Ag pumps in Akola District for 3560 pumps | 30.28
21 | MSEDCL/FY10/45 | 014/01.04.10 | Ag pumps in Washim District for 3500 pumps | 28.85
22 | MSEDCL/FY10/01 | 014/01.04.10 | Ag pump scheme in Pune Rural Circle for 7002 pumps | 56.22
23 | MSEDCL/FY10/04 | 014/01.04.10 | Ag pump scheme in Wardha District for 5964 pumps | 32.71
24 | MSEDCL/FY10/14 | 014/01.04.10 | Ag pump scheme in Nanded District for 12390 pumps | 74.89
25 | MSEDCL/FY10/35 | 014/01.04.10 | Ag pumps in Chandwad Division of Nashik District | 9.95
26 | MSEDCL/FY10/41 | 014/01.04.10 | Ag pumps in Nagpur District for 1700 pumps | 9.88
27 | MSEDCL/FY10/43 | 014/01.04.10 | Ag Pumps in Kannads & Aurangabad Rural division of Aurangabad Rural Circle for 25000 Pumps | 95.44
28 | MSEDCL/FY11/06 | 1429/22.10.10 | Ag pumps in Nagpur District for 3715 pumps | 30.3662
29 |  |  | Ag pumps in Dhule District for 1961 pumps | 9.671
30 | MSEDCL/FY10/33 |  | Ag pumps in Osmanabad District for 2000 pumps | 10.187
31 | MSEDCL/FY 11/15 | 1569/15.11.10 | Electrification of 91606 nos. of Ag. pumps in various districts of Maharashtra | 1388.57
32 | MSEDCL/FY12/07 | 07/31.07.12 | Release of 4450 numbers of Agricultural Pumps & 1623 Nos. of RCI connections in Wardha District | 34.4419
33 | MSEDCL/FY13/08 | 07/31.07.12 | Release of 81461 numbers of Agricultural Pumps connections in Dhule District | 75.0405
34 | MSEDCL/FY13/07 | 07/31.07.12 | Release of 4021 numbers of Agricultural Pumps in Buldhana District under Buldhana circle | 12.1485
35 | MSEDCL/FY13/06 | 07/31.07.12 | Release of 8227 numbers of Agricultural Pumps & 3132 Nos. of RCI connections in Osmanabad District | 54.3959
36 | MSEDCL/FY13/04 | 07/31.07.12 | Release of 19615 numbers of Agricultural Pumps & 6787 Nos. of RCI connections in Nashik District under Nashik Rural circle | 116.4945
37 | MSEDCL/FY13/05 | 07/31.07.12 | Release of 11247 numbers of Agricultural Pumps connections in Nanded District | 67.2499
38 | MSEDCL/FY14/03 | 1093/27.08.13 | Release of 6208 numbers of Agricultural Pumps in Beed District | 25.417
39 | MSEDCL/FY14/02 | 1092/27.08.13 | Release of 2312 numbers of Agricultural Pumps in Bhandara, Nagpur, Akola District | 15.28
40 | MSEDCL/FY13/12 | 469/23.05.13 | Release of Agricultural Pumps in Shrirampur (A''nagar) District | 22.05
41 | MSEDCL/FY13/13 | 469/23.05.13 | Release of Agricultural Pumps in Jalna District | 64.48
TOTAL |  |  |  | 2949.0424

## 4.1 Proj
Project Details
(Rs. Crore)
Sr.No | Project Code | Project Title | MERC Approval No. | MERC Approval Date | Project Purpose | Project Start Date |  |  | Project Completion date (Scheduled) |  |  | Capital Cost
[6 empty] | Original | Revised | Actual | Original | Revised | Actual | Approved | Actual Capital Cost Incurred | Deviation = Approved - Actual on account of
[14 empty] | Change in Scope of Work (a) | Material Cost (b) | IDC (c) | Others (d) | Total Deviation (a+b+c+d)
1 | DDUGJY | DDUGJY | MERC /CAPEX/2017-18/0152 | 31.01.2018 | System Strengethening | 2016-03-01 | - | 2016-11-01 | 2019-03-01 | Mar-2022 | Mar-2022 | 2164.15 | 2177 |  | - | - | - | 12.85
2 | Elimination of 66 KV Line | 66 KV Elimination | MERC/CAPEX/2009-10/238 | 10.03.2010 | 66 KV Elimination | Feb-2011 | - | 2011-02-01 | Feb-2013 | - | 2016-03-01 | 147.83 | 87.02 |  | - | - | - | Less Cost
3 | HVDS Scheme | HVDS Scheme | MERC/CAPEX/2018-19/1216 | 02.08.2018 | For Ag PP connections before 31.03.2018 | 2018-10-01 | - | 2018-10-01 | 31.03.2020 | 31.03.2024 | Completed | 5048.13 | 3763 |  | - | - | - | Less Cost
4 | Infra Plan Works - II | Infrastructure plan | MERC/CAPEX/20132014/00860 MERC/CAPEX/20132014/00260 MERC/CAPEX/20132014/00259 MERC/Desk III /CAPEX/20132014/01492 MERC/Desk III /CAPEX/2012201/02693 MERC/Desk III /CAPEX/20132014/01491 MERC/Desk III /CAPEX/20132014/00473 MERC/Desk III /CAPEX/20122013/02488 MERC/Desk III /CAPEX/20122013/02322 MERC/Desk III /CAPEX/20122013/02488 MERC/CAPEX/20132014/00472 MERC/CAPEX/20132014/00939 MERC/CAPEX/20132014/01363 MERC/CAPEX/20122013/00607 MERC/CAPEX/20122013/01362 MERC/Desk III /CAPEX/20132014/01800 MERC/Desk III /CAPEX/00967 MERC/Desk III /CAPEX/00878 MERC/Desk III /CAPEX/34 MERC/Desk III /CAPEX/01887 MERC/Desk III /CAPEX/20142015/00020 MERC/Desk III /CAPEX/01888 MERC/Desk III /CAPEX/20132014/0351 MERC/Desk III /CAPEX/02189 MERC/Desk III /CAPEX/00968 MERC/Desk III /CAPEX/20132014/01884 MERC/Desk III /CAPEX/20132014/01935 MERC/Desk III /CAPEX/02192 MERC/Desk III /CAPEX/20132014/01934 MERC/Desk III /CAPEX/00350 MERC/Desk III /CAPEX/02303 MERC/Desk III /CAPEX/20132014/02003 MERC/Desk III /CAPEX/20132014/02002 MERC/Desk III /CAPEX/20132014/02000 MERC/Desk III /CAPEX/2178 MERC/Desk III /CAPEX/2190 MERC/Desk III /CAPEX/2191 MERC/Desk III /CAPEX/2302 MERC/Desk III /CAPEX/1886 MERC/Desk III /CAPEX/1883 MERC/Desk III /CAPEX/1885 MERC/Desk III /CAPEX/20132014/00138 MERC/Desk III /CAPEX/20132014/00139 MERC/Desk III /CAPEX/20132014/01365 MERC/Desk III /CAPEX/20132014/01751 MERC/Desk III /CAPEX/00967 MERC/Desk III /CAPEX/00878 MERC/Desk III /CAPEX/34 MERC/Desk III /CAPEX/1887 MERC/Desk III /CAPEX/20142015/00020 MERC/Desk III /CAPEX/01888 MERC/Desk III /CAPEX/20132014/00351 MERC/Desk III /CAPEX/2189 MERC/Desk III /CAPEX/00968 MERC/Desk III /CAPEX/20132014/01876 MERC/Desk III /CAPEX/20142015/00021 MERC/Desk III /CAPEX/20122013/02654 MERC/Desk III /CAPEX/20122013/02648 MERC/Desk III /CAPEX/20132014/01823 MERC/Desk III /CAPEX/20122013/02487 MERC/Desk III /CAPEX/20122013/02351 MERC/Desk III /CAPEX/20132014/02193 MERC/Desk III /CAPEX/20132014/1365 MERC/Desk III /CAPEX/20132014/01492 MERC/Desk III /CAPEX/20122013/02693 MERC/Desk III /CAPEX/20122013/02322 MERC/Desk III /CAPEX/20132014/00472 MERC/Desk III /CAPEX/20132014/01363 MERC/Desk III /CAPEX/20132014/02179 MERC/Desk III /CAPEX/00795 MERC/Desk III /CAPEX/00794 MERC/Desk III /CAPEX/00140 MERC/Desk III /CAPEX/20142015/00376 MERC/Desk III /CAPEX/20142015/00375 MERC/Desk III /CAPEX/20142015/00377 | 12.07.2013 29.04.2013 29.04.2013 30.10.2013 22.02.2013 30.102013 23.05.2013 29.01.2013 11.01.2012 23.05.2013 24.07.2013 04.10.2013 07.06.2013 04.10.2013 18.12.2013 17.09.2014 20.08.2014 16.10.2014 31.12.2013 27.03.2014 31.12.2013 20.05.2014 11.02.2014 17.09.2014 30.12.2013 08.01.2014 11.02.2014 08.01.2014 20.05.2014 03.03.2014 17.01.2014 17.01.2014 17.01.2014 07.02.2014 11.02.2014 11.02.2014 03.03.2014 30.12.2013 30.12.2013 30.12.2013 21.04.2014 21.04.2014 04.10.2013 12.12.2013 17.09.2014 20.08.2014 16.10.2014 31.12.2013 27.03.2014 31.12.2013 20.05.2014 11.02.2014 17.09.2014 30.12.2013 27.03.2014 15.02.2013 15.02.2013 15.02.2012 20.12.2013 29.01.2012 15.01.2013 11.02.2014 04.10.2013 30.10.2013 22.02.2013 11.01.2012 23.05.2013 04.10.2013 07.02.2014 31.07.2014 31.07.2014 21.04.2014 21.05.2014 21.05.2014 21.05.2014 | System Strengethening | September 2013 to October 2015 in phased manner | - | - | September 2015 to October 2017 in phased manner | - | 2019-03-01 | 8304.32 | 7903.44 |  | - | - | - | Less Cost
5 | IPDS | IPDS IPDS RI | MERC /CAPEX/201516/1464 MERC /CAPEX/2018-19 /113 | dtd 10.02.2016 dtd 23.07.2018 | System Strengethening IPDS RI | 2016-03-01 | - | 2016-11-01 | 2019-09-01 | Mar-2022 | Mar-2022 | 3170 | 2251 |  | - | - | - | Less Cost
6 | RAPDRP B | RAPDRP Part B (36 Towns) RAPDRP Part B (28 Towns) RAPDRP Part B (28 Towns) RAPDRP Part B (30 Towns) Part B SCADA in 5 Towns Part B SCADA in 3Towns | MERC/CAPEX/20102011/01955 MERC/CAPEX/20112012/00071 MERC/CAPEX/20112012/1592 MERC/CAPEX/20102011/2158 MERC /CAPEX/20122013/00611 MERC /CAPEX/201516/1470 | dtd 12/1/2011 dtd 8/4/2011 dtd 5/10/2011 dtd 4/2/2011 dtd 07.06.2013 dtd 11.02.2016 | System Strengethening | Aug-2010 | - | Aug-2010 | Mar-2014 | Mar-2018 | Mar-2018 | 3591 | 2245.69 |  | - | - | - | Less Cost
7 | RDSS-Loss Reduction Part A Feeder Separation Works | RDSS Feeder seperation | MERC/CAPEX/MSEDCL/2023-24/0179 | 11.03.2024 | Loss Reduction | 2022-07-01 | 2023-04-01 | - | Mar-2026 | - | - | 7010.46 | 763.82 |  | - | - | - | Less Cost
8 | Reactive Power Management Scheme (PSDF) | PSDF RPM | MERC/CAPEX/MSEDCL/2023-24/101 | 05.02.2024 | Power Factor Improvement | 2023-04-01 | 2023-04-01 | 2023-04-01 | 2024-09-02 | 2024-09-02 | 2024-07-05 | 126.18 | 156.53 |  | - | - | - | 30.35
9 | Saubhagya Scheme | Saubhagya Scheme | MERC /CAPEX/2019-20 /115 | dtd 18.04.2019 | 100% electrification and last mile connectivity | 2017-09-25 | 2017-09-25 | 2017-09-25 | 31.03.2019 | 31.03.2019 | 31.03.2019 | 657.01 | 608.9 |  | - | - | - | Less Cost
10 | SCADA Part A | SCADA Part A | MERC/CAPEX/20112012/02426 | dtd 30.12.2011 | SCADA /DMS Automation | 2011-06-01 | - | Dec-2011 | June-2016 | 2021-12-01 | 2021-12-01 | 161.68 | 82.68 |  | - | - | - | Less Cost
11 | Underground works under System Strengthening in Gondia, Bhandara and Nagpur 1st Phase | Overhead to underground | MERC/CAPEX/2021-22 /052 | dtd 15.02.2022 | System Strengethening | 2023-04-01 | - | - | Nov-2024 | - | - | 432.84 | 22 |  | - | - | - | Less Cost
12 | MAHARASHTRA POWER DISTRIBUTION ENHANCEMENT PROGRAM FOR FACILITATING SOLARISATION AND EXPANDING AGRICULTURAL CONNECTIONS (Funded by ADB) | In process |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | -
13 | MSKVY 2.0 Under RDSS | Submitted to MERC for Inprinciple approval | Submitted to MERC for Inprinciple approval |  | System Strengethening | - | - | - | - | - | - | - | - | - | - | - | - | -
14 | OFF-GRID SOLAR PHOTOVOLTAIC WATER PUMPING SYSTEMS & AGRICULTURAL FEEDER SOLARISATION PROJECT WITH CONVENTIONAL AG CONNECTIONS. (Funded by AIIB) Component AA | Submitted to MERC for Inprinciple approval | Submitted to MERC for Inprinciple approval |  | System Strengethening | - | - | - | - | - | - | - | - | - | - | - | - | -
Financing Plan
(Rs. Crore)
Sr. No | Project Number | MERC Approval No. | MERC Approval Date | Source of Financing for Capital Expenditure
|  |  |  | Grant | Internal Accruals | GOM Equity | GOM/ GOI Grant | Debt
|  |  |  | Grant |  |  |  | Loan Amount | Interest Rate (% p.a.) | Tenure of Loan (years) | Moratorium Period (years) | Loan Source
1 | DDUGJY | MERC /CAPEX/2017-18/0152 | 31.01.2018 | 60% grant | - | - | - | 40 % Loan | 9.45 | 13 Years | 3 Years | REC
2 | Elimination of 66 KV Line | MERC/CAPEX/2009-10/238 | 10.03.2010 | - | - | - | - | 100 % loan | 10.25 | 13 Years | 3 Years | REC
3 | HVDS Scheme | MERC/CAPEX/2018-19/1216 | 02.08.2018 | Rs 2717.14 Crs Grant Rs 2017.47 Crs Loan | - | - | - | 1500 (PNB) & 1300 (PSB) for Rest of Maharashtra | 7.9 % (PNB) & 7.25% (PSB) | 13 Years | 3 Years | Punjab National Bank & Punjab & Sindh Bank
4 | Infra Plan Works - II | MERC/CAPEX/20132014/00860 MERC/CAPEX/20132014/00260 MERC/CAPEX/20132014/00259 MERC/Desk III /CAPEX/20132014/01492 MERC/Desk III /CAPEX/2012201/02693 MERC/Desk III /CAPEX/20132014/01491 MERC/Desk III /CAPEX/20132014/00473 MERC/Desk III /CAPEX/20122013/02488 MERC/Desk III /CAPEX/20122013/02322 MERC/Desk III /CAPEX/20122013/02488 MERC/CAPEX/20132014/00472 MERC/CAPEX/20132014/00939 MERC/CAPEX/20132014/01363 MERC/CAPEX/20122013/00607 MERC/CAPEX/20122013/01362 MERC/Desk III /CAPEX/20132014/01800 MERC/Desk III /CAPEX/00967 MERC/Desk III /CAPEX/00878 MERC/Desk III /CAPEX/34 MERC/Desk III /CAPEX/01887 MERC/Desk III /CAPEX/20142015/00020 MERC/Desk III /CAPEX/01888 MERC/Desk III /CAPEX/20132014/0351 MERC/Desk III /CAPEX/02189 MERC/Desk III /CAPEX/00968 MERC/Desk III /CAPEX/20132014/01884 MERC/Desk III /CAPEX/20132014/01935 MERC/Desk III /CAPEX/02192 MERC/Desk III /CAPEX/20132014/01934 MERC/Desk III /CAPEX/00350 MERC/Desk III /CAPEX/02303 MERC/Desk III /CAPEX/20132014/02003 MERC/Desk III /CAPEX/20132014/02002 MERC/Desk III /CAPEX/20132014/02000 MERC/Desk III /CAPEX/2178 MERC/Desk III /CAPEX/2190 MERC/Desk III /CAPEX/2191 MERC/Desk III /CAPEX/2302 MERC/Desk III /CAPEX/1886 MERC/Desk III /CAPEX/1883 MERC/Desk III /CAPEX/1885 MERC/Desk III /CAPEX/20132014/00138 MERC/Desk III /CAPEX/20132014/00139 MERC/Desk III /CAPEX/20132014/01365 MERC/Desk III /CAPEX/20132014/01751 MERC/Desk III /CAPEX/00967 MERC/Desk III /CAPEX/00878 MERC/Desk III /CAPEX/34 MERC/Desk III /CAPEX/1887 MERC/Desk III /CAPEX/20142015/00020 MERC/Desk III /CAPEX/01888 MERC/Desk III /CAPEX/20132014/00351 MERC/Desk III /CAPEX/2189 MERC/Desk III /CAPEX/00968 MERC/Desk III /CAPEX/20132014/01876 MERC/Desk III /CAPEX/20142015/00021 MERC/Desk III /CAPEX/20122013/02654 MERC/Desk III /CAPEX/20122013/02648 MERC/Desk III /CAPEX/20132014/01823 MERC/Desk III /CAPEX/20122013/02487 MERC/Desk III /CAPEX/20122013/02351 MERC/Desk III /CAPEX/20132014/02193 MERC/Desk III /CAPEX/20132014/1365 MERC/Desk III /CAPEX/20132014/01492 MERC/Desk III /CAPEX/20122013/02693 MERC/Desk III /CAPEX/20122013/02322 MERC/Desk III /CAPEX/20132014/00472 MERC/Desk III /CAPEX/20132014/01363 MERC/Desk III /CAPEX/20132014/02179 MERC/Desk III /CAPEX/00795 MERC/Desk III /CAPEX/00794 MERC/Desk III /CAPEX/00140 MERC/Desk III /CAPEX/20142015/00376 MERC/Desk III /CAPEX/20142015/00375 MERC/Desk III /CAPEX/20142015/00377 | 12.07.2013 29.04.2013 29.04.2013 30.10.2013 22.02.2013 30.102013 23.05.2013 29.01.2013 11.01.2012 23.05.2013 24.07.2013 04.10.2013 07.06.2013 04.10.2013 18.12.2013 17.09.2014 20.08.2014 16.10.2014 31.12.2013 27.03.2014 31.12.2013 20.05.2014 11.02.2014 17.09.2014 30.12.2013 08.01.2014 11.02.2014 08.01.2014 20.05.2014 03.03.2014 17.01.2014 17.01.2014 17.01.2014 07.02.2014 11.02.2014 11.02.2014 03.03.2014 30.12.2013 30.12.2013 30.12.2013 21.04.2014 21.04.2014 04.10.2013 12.12.2013 17.09.2014 20.08.2014 16.10.2014 31.12.2013 27.03.2014 31.12.2013 20.05.2014 11.02.2014 17.09.2014 30.12.2013 27.03.2014 15.02.2013 15.02.2013 15.02.2012 20.12.2013 29.01.2012 15.01.2013 11.02.2014 04.10.2013 30.10.2013 22.02.2013 11.01.2012 23.05.2013 04.10.2013 07.02.2014 31.07.2014 31.07.2014 21.04.2014 21.05.2014 21.05.2014 21.05.2014 | - | - | 20 % GoM ( Rs 1221.78 Crs) | - | 80 % Loan ( Rs 6339.35) | 11.07 11.54 | 13 Years 13 Years | 3 Years 3 Years | REC PFC
5 | IPDS | MERC /CAPEX/201516/1464 MERC /CAPEX/2018-19 /113 | dtd 10.02.2016 dtd 23.07.2018 | 60% grant | - | - | - | 40 % Loan | 9.45 to 9.72 % P.A. ( for 30% CP Loan ) 9.55 % P.A ( for 10 % Utility Contribution ) | 13 Years | 3 Years | PFC
6 | RAPDRP B | MERC/CAPEX/20102011/01955 MERC/CAPEX/20112012/00071 MERC/CAPEX/20112012/1592 MERC/CAPEX/20102011/2158 MERC /CAPEX/20122013/00611 MERC /CAPEX/201516/1470 | dtd 12/1/2011 dtd 8/4/2011 dtd 5/10/2011 dtd 4/2/2011 dtd 07.06.2013 dtd 11.02.2016 | Project completion cost is Rs 2245.69 Crs . Rs 235 Crs is recived as garnt | - | - | - | 100 % loan . Convertible into grant corresponding to reduction in losses | 7.8% 7.80 | 13 Years | 3 Years | PFC
7 | RDSS-Loss Reduction Part A Feeder Separation Works | MERC/CAPEX/MSEDCL/2023-24/0179 | 11.03.2024 | 60 % Grant | - | - | - | 40 % loan | - | - | - | PFC
8 | Reactive Power Management Scheme (PSDF) | MERC/CAPEX/MSEDCL/2023-24/101 | 05.02.2024 | 90% Grant | - | - | - | 10% loan | 1 year to 3 year 11% after 3years 11.25 % | 13 Years | 3 Years | REC
9 | Saubhagya Scheme | MERC /CAPEX/2019-20 /115 | 18.04.2019 | 60% Grant | - | - | 0.9 | 40% Loan | 0.11 | 13 Years | 3 | REC
10 | SCADA Part A | MERC/CAPEX/20112012/02426 | 30.12.2011 | 100 % Grant | - | - | - | - | - | - | - | -
11 | Underground works under System Strengthening in Gondia, Bhandara and Nagpur 1st Phase | MERC/CAPEX/2021-22 /052 | 15.02.2022 | - | - | 30% GoM Equity |  | 70 % Loan | 9.75% | 13 Years | 3 Years | REC
12 | MAHARASHTRA POWER DISTRIBUTION ENHANCEMENT PROGRAM FOR FACILITATING SOLARISATION AND EXPANDING AGRICULTURAL CONNECTIONS (Funded by ADB) | In process |  | - | - | - | - | - | - | - | - | -
13 | MSKVY 2.0 Under RDSS | Submitted to MERC for Inprinciple approval | Submitted to MERC for Inprinciple approval | - | - | - | - | - | - | - | - | -
14 | OFF-GRID SOLAR PHOTOVOLTAIC WATER PUMPING SYSTEMS & AGRICULTURAL FEEDER SOLARISATION PROJECT WITH CONVENTIONAL AG CONNECTIONS. (Funded by AIIB) Component AA | Submitted to MERC for Inprinciple approval | Submitted to MERC for Inprinciple approval | - | - | - | - | - | - | - | - | -
Note on N13: TRC: (2300.43 IPDS SS + 869.88 IPDS RI)

## 4.2 Proj
Project Details
[18 empty] | (Rs. Crore) | [14 empty] | (Rs. Crore)
Sr. No. | Project Code | Project Title | MERC Approval No. | MERC Approval Date | MERC Approved Cost | Debt Equity Ratio | Grant/Consumer Contribution | Approved Start Date | Actual Start Date | Approved Date of Completion | Actual Date of Completion | Benefits in Quantified Terms | Capital Expenditure | [6 empty] | Physical Progress (%) | [6 empty] | Capitalisation | [6 empty] | Reasons for Delay, if any
[13 empty] | Actual Capex till FY 2021-22 | Actual | Actual | Estimated | Projected | Projected | Projected | Actual Progress till FY 2021-22 | Actual | Actual | Estimated | Projected | Projected | Projected | Actual Capitalisation till FY 2021-22 | Actual | Actual | Estimated | Projected | Projected | Projected | Change in Scope of Work | Any other reason
[14 empty] | FY 2022-23 | FY 2023-24 | FY 2024-25 | FY 2025-26 | FY 2026-27 | FY 2027-28 |  | FY 2022-23 | FY 2023-24 | FY 2024-25 | FY 2025-26 | FY 2026-27 | FY 2027-28 |  | FY 2023-24 | FY 2023-24 | FY 2024-25 | FY 2025-26 | FY 2026-27 | FY 2027-28
1 | DDUGJY | DDUGJY | MERC /CAPEX/2017-18/0152 | 31.01.2018 | 2164.15 | 40 % Loan | 60% Grant | 2016-03-01 | 2016-11-01 | 2019-03-01 | 2022-03-01 | Appriasal of the scheme submitted to MERC attached herewith | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 % Completed | Scheme is alreadty closed | - | - | - | - | - | - | - | - | - | - | - | - | - | Project closed within the time line approved by MoP . Cost overrun Due to site conditions.
2 | Elimination of 66 KV Line | 66 KV Elimination | MERC/CAPEX/2009-10/238 | 10.03.2010 | 147.83 | 100 % Loan | - | Feb-2011 | Feb-2011 | Feb-2013 | March-16 | No direct monetary benefits are envisaged. It is necessary to implement the scheme in order to standardize the system voltages and ensure better quality and reliability of supply as the 66 kV system has become outdated. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 % Completed | Scheme is alreadty closed | - | - | - | - | - | - | - | - | - | - | - | - | - | Delay due to poor progress by Agency
3 | HVDS Scheme | HVDS | MERC/CAPEX/2018-19/1216 | 02.08.2018 | 5048.13 | - | 2717.14 | 2018-05-01 | 2018-10-01 | 31.03.2020 | Completed | Submitted letter to MERC (L.No-18276 Dt 30 July 2018) point no 5, Return on Investment in which it is clarified that “HVDS scheme is implemented for energisation of Ag paid pending pumps as on 31st march 2018 of farmers as per policy of GoM ,hence no return on investment is expected as it is under social obligation. It can be seen that by implementing HVDS, reliability and quality of power supply to AG consumers in the state will be improved to great extent, thereby securing the stable energy supply and improving the efficiency of Ag production as well as living standard of rural population in the state. Hence, the benefit of the scheme may not be calculated in terms of money, but it will be benefited to the farmers across the state in form of quality and reliable supply.” | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 % Completed | Scheme is alreadty completed | 92% | 99.84% | 100% | - | - | - | - | - | - | - | - | - | - | As concept of small capacity T/F was new, approvals for design and type tests was delayed. 2) Charging Permissions of DTs from Electrical Inspector were being delayed. However, with GoM notification this condition is now relaxed. 3) Heavy rains and standing crops in the field other natural calamities (Nisarg & Taukte Cyclones) hampered the progress of scheme. 4) Due to Lockdown of covid-19 from 20th Mar-20 progress was significantly hampered. 5) GOM vide G.R. dated 15.09.2021 has given approval to revised scheme cost (Rs.4734.61 Crs.) of HVDS scheme and further vide GoM G.R. dated 20.10.2023 has approved extension of scheme up to March 2024.
4 | Infra Plan Works - II | Infrastructure plan | MERC/CAPEX/20132014/00860 MERC/CAPEX/20132014/00260 MERC/CAPEX/20132014/00259 MERC/Desk III /CAPEX/20132014/01492 MERC/Desk III /CAPEX/2012201/02693 MERC/Desk III /CAPEX/20132014/01491 MERC/Desk III /CAPEX/20132014/00473 MERC/Desk III /CAPEX/20122013/02488 MERC/Desk III /CAPEX/20122013/02322 MERC/Desk III /CAPEX/20122013/02488 MERC/CAPEX/20132014/00472 MERC/CAPEX/20132014/00939 MERC/CAPEX/20132014/01363 MERC/CAPEX/20122013/00607 MERC/CAPEX/20122013/01362 MERC/Desk III /CAPEX/20132014/01800 MERC/Desk III /CAPEX/00967 MERC/Desk III /CAPEX/00878 MERC/Desk III /CAPEX/34 MERC/Desk III /CAPEX/01887 MERC/Desk III /CAPEX/20142015/00020 MERC/Desk III /CAPEX/01888 MERC/Desk III /CAPEX/20132014/0351 MERC/Desk III /CAPEX/02189 MERC/Desk III /CAPEX/00968 MERC/Desk III /CAPEX/20132014/01884 MERC/Desk III /CAPEX/20132014/01935 MERC/Desk III /CAPEX/02192 MERC/Desk III /CAPEX/20132014/01934 MERC/Desk III /CAPEX/00350 MERC/Desk III /CAPEX/02303 MERC/Desk III /CAPEX/20132014/02003 MERC/Desk III /CAPEX/20132014/02002 MERC/Desk III /CAPEX/20132014/02000 MERC/Desk III /CAPEX/2178 MERC/Desk III /CAPEX/2190 MERC/Desk III /CAPEX/2191 MERC/Desk III /CAPEX/2302 MERC/Desk III /CAPEX/1886 MERC/Desk III /CAPEX/1883 MERC/Desk III /CAPEX/1885 MERC/Desk III /CAPEX/20132014/00138 MERC/Desk III /CAPEX/20132014/00139 MERC/Desk III /CAPEX/20132014/01365 MERC/Desk III /CAPEX/20132014/01751 MERC/Desk III /CAPEX/00967 MERC/Desk III /CAPEX/00878 MERC/Desk III /CAPEX/34 MERC/Desk III /CAPEX/1887 MERC/Desk III /CAPEX/20142015/00020 MERC/Desk III /CAPEX/01888 MERC/Desk III /CAPEX/20132014/00351 MERC/Desk III /CAPEX/2189 MERC/Desk III /CAPEX/00968 MERC/Desk III /CAPEX/20132014/01876 MERC/Desk III /CAPEX/20142015/00021 MERC/Desk III /CAPEX/20122013/02654 MERC/Desk III /CAPEX/20122013/02648 MERC/Desk III /CAPEX/20132014/01823 MERC/Desk III /CAPEX/20122013/02487 MERC/Desk III /CAPEX/20122013/02351 MERC/Desk III /CAPEX/20132014/02193 MERC/Desk III /CAPEX/20132014/1365 MERC/Desk III /CAPEX/20132014/01492 MERC/Desk III /CAPEX/20122013/02693 MERC/Desk III /CAPEX/20122013/02322 MERC/Desk III /CAPEX/20132014/00472 MERC/Desk III /CAPEX/20132014/01363 MERC/Desk III /CAPEX/20132014/02179 MERC/Desk III /CAPEX/00795 MERC/Desk III /CAPEX/00794 MERC/Desk III /CAPEX/00140 MERC/Desk III /CAPEX/20142015/00376 MERC/Desk III /CAPEX/20142015/00375 MERC/Desk III /CAPEX/20142015/00377 | 12.07.2013 29.04.2013 29.04.2013 30.10.2013 22.02.2013 30.102013 23.05.2013 29.01.2013 11.01.2012 23.05.2013 24.07.2013 04.10.2013 07.06.2013 04.10.2013 18.12.2013 17.09.2014 20.08.2014 16.10.2014 31.12.2013 27.03.2014 31.12.2013 20.05.2014 11.02.2014 17.09.2014 30.12.2013 08.01.2014 11.02.2014 08.01.2014 20.05.2014 03.03.2014 17.01.2014 17.01.2014 17.01.2014 07.02.2014 11.02.2014 11.02.2014 03.03.2014 30.12.2013 30.12.2013 30.12.2013 21.04.2014 21.04.2014 04.10.2013 12.12.2013 17.09.2014 20.08.2014 16.10.2014 31.12.2013 27.03.2014 31.12.2013 20.05.2014 11.02.2014 17.09.2014 30.12.2013 27.03.2014 15.02.2013 15.02.2013 15.02.2012 20.12.2013 29.01.2012 15.01.2013 11.02.2014 04.10.2013 30.10.2013 22.02.2013 11.01.2012 23.05.2013 04.10.2013 07.02.2014 31.07.2014 31.07.2014 21.04.2014 21.05.2014 21.05.2014 21.05.2014 | 8304.32 | 20% GOM Equity 80 % Loan | - | September 2013 to October 2015 in phased manner | September 2013 to October 2015 in phased manner | September 2015 to October 2017 in phased manner | Mar-2019 | The CBA is attached herewith | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 % Completed | Scheme is alreadty closed | - | - | - | - | - | - | - | - | - | - | - | - | - | Land unavailability Delay in allocation of Land Time lapse while securing permissions from Forest Department, Railways at line crossings, National Highways Authority of India. Permissions from Municipal Corporations for laying of U/G cables.
5 | IPDS | IPDS IPDS RI | MERC /CAPEX/201516/1464 MERC /CAPEX/2018-19 /113 | dtd 10.02.2016 dtd 23.07.2018 | 3170 (2300.43 IPDS SS + 869.88 IPDS RI) | 40% loan | 60% Garnt | 2016-03-01 | 2016-11-01 | 2022-03-01 | 2022-03-01 | Appriasal of the scheme submitted to MERC attached herewith | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 % Completed | Scheme is alreadty closed | - | - | - | - | - | - | - | - | - | - | - | - | - | Project closed within the time line approved by MoP .
6 | RAPDRP B | RAPDRP Part B (36 Towns) RAPDRP Part B (28 Towns) RAPDRP Part B (28 Towns) RAPDRP Part B (30 Towns) Part B SCADA in 5 Towns Part B SCADA in 3Towns | MERC/CAPEX/20102011/01955 MERC/CAPEX/20112012/00071 MERC/CAPEX/20112012/1592 MERC/CAPEX/20102011/2158 MERC /CAPEX/20122013/00611 MERC /CAPEX/201516/1470 | dtd 12/1/2011 dtd 8/4/2011 dtd 5/10/2011 dtd 4/2/2011 dtd 07.06.2013 dtd 11.02.2016 | 3591 | 100 % loan . Convertible into grant corresponding to reduction in losses | - | 2010-08-01 | 2010-08-01 | 2018-03-01 | 2018-03-01 | The CBA is attached herewith | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 % Completed | Scheme is alreadty closed | - | - | - | - | - | - | - | - | - | - | - | - | - | Project closed within the time line approved by MoP ie March -2018
7 | RDSS-Loss Reduction Part A Feeder Separation Works | RDSS Feeder seperation | MERC/CAPEX/MSEDCL/2023-24/0179 | 11.03.2024 | 7010.46 | 40 % loan | 60% Grant | 2022-07-01 | 2022-07-01 | Mar-2026 | Scheme is ongoing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | - | - | 17% | 60% | 23% | - | - | - | - | - | - | - | - | - | -
8 | Reactive Power Management Scheme (PSDF) | PSDF RPM | MERC/CAPEX/MSEDCL/2023-24/101 | 05.02.2024 | 126.18 | 10 % Loan | 90 % Garnt | 2023-04-01 | 2023-04-01 | 2024-09-02 | 2024-07-05 | Scheme on going | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | - | 90% | 10% | - | - | - | - | - | - | - | - | - | - | - | Scheme ongoing. Cost over run will be finalized after completion of scheme
9 | Saubhagya Scheme | Saubhagya Scheme | MERC /CAPEX/2019-20 /115 | dtd 18.04.2019 | 657.01 | 40 % Loan | 60% Grant | 2017-09-25 | 2017-09-25 | 31.03.2019 | 31.03.2019 | Saubhagya Scheme was implemented for mile connectivity and electricity connections to all un-electrified households in rural areas and economically poor un-electrified households in urban areas , hence the benefits of the scheme are intangible. heme are intangible | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 % Completed | Scheme is alreadty closed | - | - | - | - | - | - | - | - | - | - | - | - | - | Scheme closed as on March-2019
10 | SCADA Part A | SCADA Part A | MERC/CAPEX/20112012/02426 | dtd 30.12.2011 | 161.68 | - | 100 % Grant | 2011-06-01 | 2011-12-01 | 2021-12-01 | 2021-12-01 | The Benefits of the SCADA scheme are intangible Major benefits of the SCADA project are as under i. Quicker fault location and restoration. Hence reduction in the down time. ii. Equipment health monitoring for longevity iii. Protection from overloading iv. Proper implementation of load shedding v. Operation monitoring for preventive maintenance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 % Completed | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
11 | Underground works under System Strengthening in Gondia, Bhandara and Nagpur 1st Phase | Overhead to underground | MERC/CAPEX/2021-22 /052 | dtd 15.02.2022 | 432.84 | 30 % GoM Equity 70% Loan | - | 2023-04-01 | - | Nov-2024 | - | Scheme on going | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | - | 15% | 85% | - | - | - | - | - | - | - | - | - | - | - | Scheme ongoing
12 | MAHARASHTRA POWER DISTRIBUTION ENHANCEMENT PROGRAM FOR FACILITATING SOLARISATION AND EXPANDING AGRICULTURAL CONNECTIONS (Funded by ADB) | In process | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
13 | MSKVY 2.0 Under RDSS | Submitted to MERC for Inprinciple approval | Submitted to MERC for Inprinciple approval | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
14 | OFF-GRID SOLAR PHOTOVOLTAIC WATER PUMPING SYSTEMS & AGRICULTURAL FEEDER SOLARISATION PROJECT WITH CONVENTIONAL AG CONNECTIONS. (Funded by AIIB) Component AA | Submitted to MERC for Inprinciple approval | Submitted to MERC for Inprinciple approval | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -

## CBA_PROJ
CAPEX SCHEME WISE DETAILS_ DATA GAP SET 1
Sr.No. | Name | Scheme Ref | Status of CBA Submission | Reference Letter
APPROVED DPR SCHEMES
1 | DDUGJY | MERC /CAPEX/2017-18/0152 | Appraisal Letter submitted to MERC Attached No. Director (Projects)/ 26986 dated 13th Oct 2022. | Director ( Projects)/26986 dtd 13.10.2022
2 | Elimination of 66 KV Line | MERC/CAPEX/2009-10/238 | Attached | CE(Proj)/66 KV elimination Sch/ 35127 dtd 21.12.2019
3 | HVDS Scheme | MERC/CAPEX/2018-19/1216 | Submitted letter to MERC (L.No-18276 Dt 30 July 2018) | CE(Dist)/HVDS /015171 dtd 22.06.2018
4 | Infra Plan Works - II | MERC/CAPEX/20132014/00860 MERC/CAPEX/20132014/00260 MERC/CAPEX/20132014/00259 MERC/Desk III /CAPEX/20132014/01492 MERC/Desk III /CAPEX/2012201/02693 MERC/Desk III /CAPEX/20132014/01491 MERC/Desk III /CAPEX/20132014/00473 MERC/Desk III /CAPEX/20122013/02488 MERC/Desk III /CAPEX/20122013/02322 MERC/Desk III /CAPEX/20122013/02488 MERC/CAPEX/20132014/00472 MERC/CAPEX/20132014/00939 MERC/CAPEX/20132014/01363 MERC/CAPEX/20122013/00607 MERC/CAPEX/20122013/01362 MERC/Desk III /CAPEX/20132014/01800 MERC/Desk III /CAPEX/00967 MERC/Desk III /CAPEX/00878 MERC/Desk III /CAPEX/34 MERC/Desk III /CAPEX/01887 MERC/Desk III /CAPEX/20142015/00020 MERC/Desk III /CAPEX/01888 MERC/Desk III /CAPEX/20132014/0351 MERC/Desk III /CAPEX/02189 MERC/Desk III /CAPEX/00968 MERC/Desk III /CAPEX/20132014/01884 MERC/Desk III /CAPEX/20132014/01935 MERC/Desk III /CAPEX/02192 MERC/Desk III /CAPEX/20132014/01934 MERC/Desk III /CAPEX/00350 MERC/Desk III /CAPEX/02303 MERC/Desk III /CAPEX/20132014/02003 MERC/Desk III /CAPEX/20132014/02002 MERC/Desk III /CAPEX/20132014/02000 MERC/Desk III /CAPEX/2178 MERC/Desk III /CAPEX/2190 MERC/Desk III /CAPEX/2191 MERC/Desk III /CAPEX/2302 MERC/Desk III /CAPEX/1886 MERC/Desk III /CAPEX/1883 MERC/Desk III /CAPEX/1885 MERC/Desk III /CAPEX/20132014/00138 MERC/Desk III /CAPEX/20132014/00139 MERC/Desk III /CAPEX/20132014/01365 MERC/Desk III /CAPEX/20132014/01751 MERC/Desk III /CAPEX/00967 MERC/Desk III /CAPEX/00878 MERC/Desk III /CAPEX/34 MERC/Desk III /CAPEX/1887 MERC/Desk III /CAPEX/20142015/00020 MERC/Desk III /CAPEX/01888 MERC/Desk III /CAPEX/20132014/00351 MERC/Desk III /CAPEX/2189 MERC/Desk III /CAPEX/00968 MERC/Desk III /CAPEX/20132014/01876 MERC/Desk III /CAPEX/20142015/00021 MERC/Desk III /CAPEX/20122013/02654 MERC/Desk III /CAPEX/20122013/02648 MERC/Desk III /CAPEX/20132014/01823 MERC/Desk III /CAPEX/20122013/02487 MERC/Desk III /CAPEX/20122013/02351 MERC/Desk III /CAPEX/20132014/02193 MERC/Desk III /CAPEX/20132014/1365 MERC/Desk III /CAPEX/20132014/01492 MERC/Desk III /CAPEX/20122013/02693 MERC/Desk III /CAPEX/20122013/02322 MERC/Desk III /CAPEX/20132014/00472 MERC/Desk III /CAPEX/20132014/01363 MERC/Desk III /CAPEX/20132014/02179 MERC/Desk III /CAPEX/00795 MERC/Desk III /CAPEX/00794 MERC/Desk III /CAPEX/00140 MERC/Desk III /CAPEX/20142015/00376 MERC/Desk III /CAPEX/20142015/00375 MERC/Desk III /CAPEX/20142015/00377 | Attached | No. CE(Projects)/Infra-II/ MYT/ 34769 dtd 17.12.2019
5 | IPDS | MERC /CAPEX/201516/1464 MERC /CAPEX/2018-19 /113 | Appraisal Letter submitted to MERC Attached | Director ( Projects)/26987 dtd 13.10.2022
6 | RAPDRP B | MERC/CAPEX/20102011/01955 MERC/CAPEX/20112012/00071 MERC/CAPEX/20112012/1592 MERC/CAPEX/20102011/2158 MERC /CAPEX/20122013/00611 MERC /CAPEX/201516/1470 | Attached | CE ( IPDS)/000751 dtd 10.01.2018 Further calculation of CBA for FY 2021-22 is attached herewith.
7 | RDSS-Loss Reduction Part A Feeder Separation Works | MERC/CAPEX/MSEDCL/2023-24/0179 | Ongoing | ongoing
8 | Reactive Power Management Scheme (PSDF) | MERC/CAPEX/MSEDCL/2023-24/101 | Ongoing | ongoing
9 | Saubhagya Scheme | MERC /CAPEX/2019-20 /115 | Saubhagya Scheme was implemented for last mile connectivity and electricity connections to all un-electrified households in rural areas and economically poor un-electrified households in urban areas , hence the benefits of the scheme are intangible. | Intangible benefits
10 | SCADA Part A | MERC/CAPEX/20112012/02426 | The Benefits of the SCADA scheme are intangible Major benefits of the SCADA project are as under i. Quicker fault location and restoration. Hence reduction in the down time. ii. Equipment health monitoring for longevity iii. Protection from overloading iv. Proper implementation of load shedding v. Operation monitoring for preventive maintenance | Intangible benefits
11 | Underground works under System Strengthening in Gondia, Bhandara and Nagpur 1st Phase | MERC/CAPEX/2021-22 /052 | Ongoing | ongoing
DPR SCHEMES- APPROVAL IN PROCESS
12 | Maharashtra Power Distribution Enhancement Program For Facilitating Solarisation And Expanding Agricultural Connections (Funded by ADB) | Scheme Not yet Sanctioned | Scheme Not yet Sanctioned | Scheme Not yet Sanctioned
13 | MSKVY 2.0 Under RDSS | Submitted to MERC for Inprinciple approval | Ongoing (Submitted to MERC for In principle apporval vide letter no ED (Projects)/AIIB/32556 dtd 15.10.2024) | Submitted to MERC for Inprinciple approval
14 | Off-Grid Solar Photovoltaic Water Pumping Systems & Agricultural Feeder Solarisation Project With Conventional Ag Connections. (Funded by AIIB) Component AA | Submitted to MERC for Inprinciple approval | Ongoing (Submitted to MERC for In principle apporval vide letter no ED (Projects)/AIIB/32556 dtd 15.10.2024) | Submitted to MERC for Inprinciple approval

## TOR COR_PROJ
CAPEX SCHEME WISE DETAILS_ DATA GAP SET 1
Sr.No. | Name | Details of Cost Over run if any |  |  | Details of Time Over run if any
|  | Approved Cost (Rs. Crs) | Revised Cost (Rs. Crs) | Justification for Cost Overrun | Original Completion | Revised Completion | Justification for Time Overrun etc.
APPROVED DPR SCHEMES
1 | DDUGJY | 2164.15 | 2177 | Scheme Executed as per the actual site conditions | Mar-2019 | Mar-2022 | Scheme completed within the timeline approved by MoP | Approval Letter of MoP will be submitted subsequently
2 | Elimination of 66 KV Line | 147.83 | 87.02 | No Cost Overrun | Feb-2013 | 01.03.2016 | Infra-II Scheme is closed in March-2019. (Physical Work completed). Expenditure has incurred during the FY 2020-21, 2021-22 and 2022-23 due to delay in closure of balance Main tenders. The main reasons for delay in financial closure are litigation and agency’s disputes.
3 | HVDS Scheme | 5048.13 | 4734.61 | No Cost Overrun | 31.03.2020 | 31.03.2024 | As concept of small capacity T/F was new, approvals for design and type tests was delayed. 2) Charging Permissions of DTs from Electrical Inspector were being delayed. However, with GoM notification this condition is now relaxed.
4 | Infra Plan Works - II | 8304.32 | 7903.44 | No Cost Overrun | September 2015 to October 2017 in phased manner | Mar-2019 | Land unavailability Delay in allocation of Land Time lapse while securing permissions from Forest Department, Railways at line crossings, National Highways Authority of India. Permissions from Municipal Corporations for laying of U/G cables.
5 | IPDS | 3170 | 2251 | No Cost Overrun | Sept-2019 | Mar-2022 | Scheme completed within the timeline approved by MoP
6 | RAPDRP B | 3591 | 2245.69 | No Cost Overrun | Mar-2014 | Mar-2018 | Scheme delayed due to ROW issues . Permissions from Various authorities etc. However the Scheme completed within the timeline approved by MoP
7 | RDSS-Loss Reduction Part A Feeder Separation Works | 7010.46 | 7010.46 | Ongoing | Mar-2026 |  | Ongoing
8 | Reactive Power Management Scheme (PSDF) | 126.18 | 156.53 | The cost over run is due to following 1) Offer rate recived is 9 % above hence escalation in the exceuted cost 2) The approved activity was for HVDS scheme considering new substation . However PSDF scheme is executed in existing substations and many items require as non BOQ to commission the APFC Hence cost escalation 3) The activity is carried out in existing substation in avaliable space of substtaion hence HT cable and control cable is excess quantity. Hence cost escalation. 4) DPR was submitted in 2018 and sanctioned in Year 2022. however only 9-10% of cost escalation in DPR cost was approved. 5) GST for Civil work is not sanctioned As such the sanctioned DPR cost is lower than the actual cost. | 2024-09-02 | . | Ongoing
9 | Saubhagya Scheme | 657.01 | 608.9 | No Cost Overrun | 31.03.2019 | 31.03.2019 | Completed within timelines
10 | SCADA Part A | 161.68 | 82.68 | No Cost Overrun | Jun-2016 | Physical completion date is March-2018 Financial closure submitted In Dec -2021 | Project was delayed due to network connectivity issues . Since the reason of link connectivity delay is beyond the control of utility & agency both , this delay is considered by MOP and accordingly the time limit is extended by monitoring committee, adhering to same the loan is converted into Grant Hence there is overrun of scheme only due to unavoidable reasons duly accepted by MoP
11 | Underground works under System Strengthening in Gondia, Bhandara and Nagpur 1st Phase | 432.84 | 432.84 | Ongoing | March-2025 |  | Ongoing
DPR SCHEMES- APPROVAL IN PROCESS
12 | Maharashtra Power Distribution Enhancement Program For Facilitating Solarisation And Expanding Agricultural Connections (Funded by ADB) | Scheme Not yet Sanctioned. Hence not submitted to MERC for In Principal Approval . The minutes of the screening committee meeting for cost approval is attached herewith | Scheme Not yet Sanctioned. Hence not submitted to MERC for In Principal Approval . The minutes of the screening committee meeting for cost approval is attached herewith | Scheme Not yet Sanctioned. Hence not submitted to MERC for In Principal Approval . The minutes of the screening committee meeting for cost approval is attached herewith | Scheme Not yet Sanctioned. Hence not submitted to MERC for In Principal Approval . The minutes of the screening committee meeting for cost approval is attached herewith | Scheme Not yet Sanctioned. Hence not submitted to MERC for In Principal Approval . The minutes of the screening committee meeting for cost approval is attached herewith | Scheme Not yet Sanctioned. Hence not submitted to MERC for In Principal Approval . The minutes of the screening committee meeting for cost approval is attached herewith
13 | MSKVY 2.0 Under RDSS | Submitted to MERC for In principle apporval vide letter no ED (Projects)/EE-III/MSKVY/32107 dtd 11.10.2024 | Submitted to MERC for In principle apporval vide letter no ED (Projects)/EE-III/MSKVY/32107 dtd 11.10.2024 | Submitted to MERC for In principle apporval vide letter no ED (Projects)/EE-III/MSKVY/32107 dtd 11.10.2024 | Submitted to MERC for In principle apporval vide letter no ED (Projects)/EE-III/MSKVY/32107 dtd 11.10.2024 | Submitted to MERC for In principle apporval vide letter no ED (Projects)/EE-III/MSKVY/32107 dtd 11.10.2024 | Submitted to MERC for In principle apporval vide letter no ED (Projects)/EE-III/MSKVY/32107 dtd 11.10.2024
14 | Off-Grid Solar Photovoltaic Water Pumping Systems & Agricultural Feeder Solarisation Project With Conventional Ag Connections. (Funded by AIIB) Component AA | Submitted to MERC for In principle apporval vide letter no ED (Projects)/AIIB/32556 dtd 15.10.2024 | Submitted to MERC for In principle apporval vide letter no ED (Projects)/AIIB/32556 dtd 15.10.2024 | Submitted to MERC for In principle apporval vide letter no ED (Projects)/AIIB/32556 dtd 15.10.2024 | Submitted to MERC for In principle apporval vide letter no ED (Projects)/AIIB/32556 dtd 15.10.2024 | Submitted to MERC for In principle apporval vide letter no ED (Projects)/AIIB/32556 dtd 15.10.2024 | Submitted to MERC for In principle apporval vide letter no ED (Projects)/AIIB/32556 dtd 15.10.2024

## CBA_RAPDRP B
RAPDRP Part B : Cost Benefit Analysis for FY 2021-22
Sr.No. | R-APDRP Towns | Project cost | Billing Eff. of Base lines | Inf for the period 2021-22 |  | 2021-22 |  |  |  |  | Inf for the period2018-19
|  |  |  | Billing Eff. for 18-19 | Total inputs for 18-19 (Mus) | Increase in billing eff. | Total units saved (MUs) | ARR in Rs (Gross Revenue / total Input) | Total cost saved (Rs Lakhs) |  | Billing Eff. for 18-19 | Total inputs for 18-19 | ARR in Rs (Gross Revenue / total Input)
1 | ACHALPUR | 23.17 | 57.0381 | 54.76 | 81.55 | -2.2781 | -1.8578 | 4.7137 | -87.5708 |  | 65.86 | 110217903 | 5.0105
2 | AHMADPUR | 13.34 | 43.552 | 43.1 | 35.34 | -0.45203 | -0.15975 | 3.6333 | -5.804 |  | 46.18 | 33205378 | 4.026
3 | AHMEDNAGAR | 55.9 | 73.1317 | 82.24 | 629.58 | 9.1083 | 57.344 | 7.9042 | 4532.5617 |  | 84.1 | 702356773 | 7.4186
4 | AKKALKOT | 4.12 | 70.9945 | 79.43 | 19.06 | 8.4355 | 1.6078 | 6.8888 | 110.7576 |  | 100 | 16193880 | 9.0778
5 | AKOLA | 107.65 | 76.0754 | 64.7 | 357.62 | -11.3754 | -40.6807 | 7.0094 | -2851.4679 |  | 70.79 | 303959015 | 7.3603
6 | AKOT | 6.45 | 57.9622 | 82.28 | 55.41 | 24.3178 | 13.4745 | 9.3936 | 1265.7407 |  | 83.37 | 49776913 | 6.7609
7 | AMALNER | 6.81 | 78.0159 | 75.46 | 49.63 | -2.5559 | -1.2685 | 7.0179 | -89.0216 |  | 93.14 | 42196334 | 7.8295
8 | AMBEJOGAI | 8.4 | 54.3352 | 77.01 | 41.54 | 22.6748 | 9.4191 | 8.7771 | 826.724 |  | 100 | 13176332 | 17.5048
9 | AMRAVATI | 40.23 | 81.7314 | 71.3 | 483.28 | -10.4314 | -50.4129 | 6.9821 | -3519.8715 |  | 73.94 | 485243510 | 6.471
10 | ANJANGAON | 5.19 | 57.1389 | 56.94 | 25.5 | -0.19888 | -0.050714 | 5.6549 | -2.8678 |  | 71.39 | 20419116 | 5.7953
11 | ARVI | 1.73 | 80.6474 | 91.13 | 19.72 | 10.4826 | 2.0672 | 8.7525 | 180.9296 |  | 90.75 | 19118953 | 7.1671
12 | ASHTA | 17.6 | 79.6988 | 97.46 | 47.59 | 17.7612 | 8.4526 | 7.5079 | 634.6084 |  | 100 | 50539016 | 7.7707
13 | AUSA | 4.97 | 74.3443 | 72.63 | 19.55 | -1.7143 | -0.33515 | 7.5754 | -25.3894 |  | 70.95 | 17990066 | 5.9509
14 | BALAPUR | 1 | 55.7892 | 63.83 | 14.21 | 8.0408 | 1.1426 | 5.4258 | 61.9947 |  | 97.61 | 6023227 | 9.5998
15 | BALLARPUR | 1.7 | 81.3834 | 92.08 | 53.15 | 10.6966 | 5.6853 | 9.3735 | 532.9056 |  | 100 | 45530554 | 9.3831
16 | BARAMATI | 49.6 | 82.8832 | 83.7 | 53.01 | 0.81681 | 0.43299 | 8.7682 | 37.9655 |  | 89.02 | 55800139 | 9.3732
17 | BARSHI | 8.02 | 81.4003 | 86.33 | 73.1 | 4.9297 | 3.6036 | 8.2257 | 296.4231 |  | 86.56 | 84831438 | 7.5442
18 | BASMATH | 6.47 | 57.0843 | 46.43 | 57.27 | -10.6543 | -6.1017 | 4.0492 | -247.0739 |  | 73.31 | 24731750 | 4.3519
19 | BEED | 56.23 | 56.9151 | 50.25 | 159.17 | -6.6651 | -10.6088 | 4.4676 | -473.9548 |  | 50.43 | 174699204 | 4.2913
20 | BHADRAWATI | 3.04 | 86.0974 | 87.37 | 46.41 | 1.2726 | 0.59063 | 6.9942 | 41.3095 |  | 100 | 36413159 | 7.9462
21 | BHANDARA | 5.74 | 74.7113 | 82.54 | 64.68 | 7.8287 | 5.0636 | 9.7913 | 495.7915 |  | 86.66 | 66524031 | 8.2092
22 | BHUSAWAL | 24.91 | 56.823 | 52.48 | 137.76 | -4.343 | -5.9829 | 4.992 | -298.6684 |  | 61.27 | 124644060 | 5.3893
23 | BRAHMAPURI | 2.4 | 72.7942 | 81.78 | 23.38 | 8.9858 | 2.1009 | 8.8024 | 184.9275 |  | 100 | 19763188 | 9.6159
24 | BULDHANA | 10.38 | 88.6447 | 64.58 | 57.7 | -24.0647 | -13.8853 | 6.0676 | -842.5044 |  | 85.48 | 41650813 | 7.0967
25 | CHALISGAON | 10.2 | 68.046 | 61.3 | 45.09 | -6.746 | -3.0418 | 6.8973 | -209.7999 |  | 11.82 | 302946355 | 1.0341
26 | CHANDRAPUR | 23.01 | 86.0337 | 93.24 | 625.63 | 7.2063 | 45.0845 | 8.2814 | 3733.6364 |  | 98.65 | 557145829 | 7.2437
27 | CHIKHLI | 8.87 | 69.3315 | 43.88 | 36.21 | -25.4515 | -9.216 | 4.6727 | -430.64 |  | 91.1 | 26416650 | 7.8208
28 | CHIPLUN | 22.81 | 79.6722 | 79.12 | 73.7 | -0.55219 | -0.40697 | 10.3501 | -42.1214 |  | 100 | 36411860 | 12.8092
29 | CHOPDA | 6.96 | 68.3709 | 60.93 | 43.31 | -7.4409 | -3.2226 | 6.913 | -222.7795 |  | 53.96 | 50647483 | 4.5805
30 | DAHANU | 15.95 | 80.6034 | 76.11 | 27.5 | -4.4934 | -1.2357 | 11.3164 | -139.8336 |  | 79.83 | 40279759 | 6.9397
31 | DARYAPUR | 7.41 | 60.3339 | 73.82 | 27.69 | 13.4861 | 3.7343 | 6.3778 | 238.164 |  | 100 | 16824669 | 8.9045
32 | DAUND | 10.71 | 70.5642 | 100 | 31.9 | 29.4358 | 9.39 | 10.9216 | 1025.5417 |  | 100 | 32253730 | 9.2652
33 | DEGLUR | 8.17 | 66.9391 | 92.85 | 20.71 | 25.9109 | 5.3662 | 8.4307 | 452.4047 |  | 93.07 | 20207276 | 6.9558
34 | DEOLALI | 10.25 | 85.2403 | 87.05 | 59.86 | 1.8097 | 1.0833 | 9.5439 | 103.3855 |  | 100 | 72407357 | 9.07
35 | DHARANGAON | 2.95 | 60.49 | 74.11 | 20.51 | 13.62 | 2.7935 | 4.1784 | 116.7234 |  | 56.85 | 15756695 | 4.5859
36 | DHULE | 26.09 | 69.3163 | 85.92 | 285.69 | 16.6037 | 47.435 | 8.0629 | 3824.6524 |  | 91.32 | 307649196 | 7.3216
37 | DIGRAS | 3.48 | 63.2885 | 67.74 | 21.05 | 4.4515 | 0.93703 | 5.8527 | 54.8421 |  | 68.65 | 18731005 | 5.601
38 | DONDAICHA | 7.52 | 73.9296 | 93.19 | 14.1 | 19.2604 | 2.7157 | 8.156 | 221.4951 |  | 83.8 | 25318406 | 6.9945
39 | ERANDOL | 2.53 | 60.1484 | 61.07 | 21.99 | 0.92157 | 0.20265 | 5.598 | 11.3445 |  | 79.41 | 17495010 | 6.9574
40 | GADCHIROLI | 8.99 | 81.6059 | 84.2 | 35.26 | 2.5941 | 0.91469 | 8.8117 | 80.5993 |  | 99.53 | 30257321 | 9.0524
41 | GANGAKHED | 5.23 | 65.3752 | 78.59 | 21.86 | 13.2148 | 2.8888 | 6.935 | 200.3365 |  | 48.6 | 32633552 | 4.0242
42 | GONDIA | 38.55 | 70.7914 | 75.17 | 86.84 | 4.3786 | 3.8024 | 8.4466 | 321.1691 |  | 100 | 46909594 | 16.3643
43 | GREATER MUMBAI | 1114.42 | 82.7893 | 100 | 5211.97 | 17.2107 | 897.0185 | 10.8301 | 97148.2516 |  | 82.54 | 7612384929 | 7.8399
44 | HINGANGHAT | 7.42 | 81.2405 | 84.84 | 81.51 | 3.5995 | 2.934 | 7.4764 | 219.3544 |  | 89.31 | 94389872 | 7.1207
45 | HINGOLI | 6.22 | 49.0601 | 63.38 | 45.52 | 14.3199 | 6.5184 | 8.0668 | 525.8251 |  | 69.09 | 59092046 | 3.9044
46 | ICHALKARANJI | 79.37 | 87.406 | 36.19 | 3159.75 | -51.216 | -1618.2983 | 3.3456 | -54141.994 |  | 91.94 | 1444734668 | 5.3025
47 | IGATPURI | 5.13 | 69.0233 | 81.4 | 23.82 | 12.3767 | 2.9481 | 9.173 | 270.4303 |  | 100 | 14763441 | 11.3369
48 | JAISINGPUR | 7.14 | 85.4943 | 91.56 | 70.23 | 6.0657 | 4.2599 | 8.6032 | 366.4896 |  | 100 | 79707121 | 8.6806
49 | JALNA | 87.62 | 53.5791 | 62.86 | 132.11 | 9.2809 | 12.2609 | 6.0798 | 745.4383 |  | 90.68 | 93404540 | 8.4326
50 | JINTUR | 4.56 | 46.8909 | 45.72 | 31.41 | -1.1709 | -0.36777 | 2.894 | -10.6431 |  | 100 | 8866626 | 10.4896
51 | KAMPTEE | 9.03 | 53.0227 | 72.44 | 85.19 | 19.4173 | 16.5416 | 8.5832 | 1419.7953 |  | 73.71 | 87917619 | 8.1074
52 | KANNAD | 11.03 | 40.9724 | 42.25 | 25.3 | 1.2776 | 0.32324 | 4.0198 | 12.9934 |  | 58.6 | 22986235 | 4.7453
53 | KARAD | 5.95 | 79.755 | 85.76 | 39.32 | 6.005 | 2.3612 | 9.2854 | 219.2419 |  | 89.86 | 42868668 | 9.195
54 | KARANJA | 7.6 | 79.9388 | 59.53 | 50.83 | -20.4088 | -10.3738 | 8.7724 | -910.0305 |  | 78.92 | 42953856 | 6.3676
55 | KATOL | 4.44 | 79.7812 | 79.03 | 21.75 | -0.75118 | -0.16338 | 8.6115 | -14.0697 |  | 88.25 | 21379980 | 7.7459
56 | KHAMGAON | 7.04 | 77.33 | 83.42 | 103.02 | 6.09 | 6.274 | 9.0905 | 570.3323 |  | 90.21 | 102450274 | 7.3712
57 | KHOPOLI | 20.5 | 82.4044 | 100 | 203.19 | 17.5956 | 35.7525 | 9.6068 | 3434.6642 |  | 95.51 | 305254856 | 7.4028
58 | KOPARGAON | 8.06 | 83.6049 | 85.57 | 42.75 | 1.9651 | 0.84008 | 8.3883 | 70.4689 |  | 85.03 | 49647374 | 7.61
59 | LATUR | 48.84 | 78.8525 | 84.19 | 261.61 | 5.3375 | 13.9634 | 9.3444 | 1304.8052 |  | 87.84 | 268757214 | 9.1666
60 | LONAVALA | 20.88 | 80.7074 | 89.46 | 90.51 | 8.7526 | 7.9219 | 11.7125 | 927.8585 |  | 100 | 75982614 | 17.2157
61 | MAJALGAON | 2.62 | 82.4405 | 29.5 | 37.97 | -52.9405 | -20.1015 | 2.9049 | -583.9341 |  | 59.04 | 18286263 | 4.8398
62 | MALEGAON | 21.72 | 44.4222 | 100 | 234.51 | 55.5778 | 130.3355 | 6.5183 | 8495.6227 |  | 34.11 | 994559054 | 1.8413
63 | MALKAPUR | 8.97 | 81.2801 | 92.34 | 38.9 | 11.0599 | 4.3023 | 10.9409 | 470.7111 |  | 100 | 33717926 | 8.6407
64 | MANMAD | 9.15 | 53.5746 | 74.09 | 47.86 | 20.5154 | 9.8186 | 6.9306 | 680.4942 |  | 62.79 | 63002351 | 5.5869
65 | MEHKAR | 3.71 | 55.981 | 88.92 | 16.42 | 32.939 | 5.4086 | 10.1949 | 551.3988 |  | 87.8 | 16007210 | 6.485
66 | MORSHI | 4.2 | 70.3053 | 71.57 | 18.29 | 1.2647 | 0.2313 | 6.6867 | 15.4667 |  | 86.5 | 16198649 | 7.2424
67 | MURTIJAPUR | 6.3 | 75.9154 | 71.88 | 32.22 | -4.0354 | -1.3002 | 6.6822 | -86.882 |  | 82.96 | 27800936 | 7.2077
68 | NALASOPARA | 27 | 88.4259 | 92.06 | 347.35 | 3.6341 | 12.623 | 9.2664 | 1169.7023 |  | 60.83 | 540496463 | 5.0549
69 | NANDED | 30.13 | 61.3141 | 58.29 | 522.76 | -3.0241 | -15.8088 | 6.8552 | -1083.7172 |  | 58.08 | 476892580 | 5.1053
70 | NANDURA | 2.66 | 76.4793 | 37.3 | 20.51 | -39.1793 | -8.0357 | 3.6275 | -291.4938 |  | 97.13 | 17989234 | 8.7654
71 | NANDURBAR | 10.28 | 78.104 | 67.2 | 73.9 | -10.904 | -8.0581 | 6.5535 | -528.0818 |  | 77.21 | 70902965 | 6.5845
72 | NILANGA | 4.49 | 66.1348 | 67.85 | 20.78 | 1.7152 | 0.35641 | 6.2705 | 22.3486 |  | 79.74 | 16182775 | 6.424
73 | OSMANABAD | 11.83 | 85.4922 | 77.76 | 68.47 | -7.7322 | -5.2943 | 6.8614 | -363.2599 |  | 93.22 | 59362780 | 7.3566
74 | PACHORA | 14.09 | 71.8637 | 71.95 | 38.71 | 0.086305 | 0.033409 | 7.1739 | 2.3967 |  | 75.72 | 36574364 | 6.2585
75 | PAITHAN | 5.51 | 75.9318 | 51.8 | 16.93 | -24.1318 | -4.0855 | 4.4359 | -181.2298 |  | 61.49 | 26819360 | 4.0407
76 | PALGHAR | 5.98 | 84.6226 | 100 | 107.58 | 15.3774 | 16.543 | 9.6142 | 1590.4837 |  | 100 | 83537427 | 14.2036
77 | PANDHARPUR | 30 | 87.392 | 88.73 | 52.51 | 1.338 | 0.70258 | 8.0461 | 56.5298 |  | 87.58 | 61747658 | 7.9542
78 | PARBHANI | 24.75 | 58.9774 | 65.73 | 164.21 | 6.7526 | 11.0885 | 7.365 | 816.6655 |  | 59.32 | 152947923 | 4.9371
79 | PARLI | 9.2 | 77.1379 | 42.55 | 75.12 | -34.5879 | -25.9825 | 4.3703 | -1135.5224 |  | 55.87 | 84377390 | 4.435
80 | PAROLA | 3.49 | 74.2834 | 65.56 | 22.68 | -8.7234 | -1.9785 | 6.3889 | -126.4021 |  | 80.09 | 18091727 | 7.2425
81 | PATHRI | 3.65 | 51.0699 | 55.41 | 24.4 | 4.3401 | 1.059 | 2.5451 | 26.9523 |  | 60.76 | 19057371 | 2.3232
82 | PEN | 9.24 | 83.8093 | 70.56 | 38.52 | -13.2493 | -5.1036 | 7.6402 | -389.926 |  | 100 | 30005749 | 9.3448
83 | PHALTAN | 2.58 | 79.4462 | 83.84 | 28.34 | 4.3938 | 1.2452 | 8.1757 | 101.8046 |  | 100 | 16766311 | 12.4739
84 | PULGAON | 2.14 | 73.4072 | 88.23 | 25.31 | 14.8228 | 3.7517 | 9.6405 | 361.6773 |  | 94.02 | 23236872 | 8.1744
85 | PURNA | 4.96 | 54.7222 | 59.83 | 13.07 | 5.1078 | 0.66759 | 5.6542 | 37.7469 |  | 59.99 | 12110472 | 3.9957
86 | PUSAD | 13.84 | 57.8449 | 89.46 | 32.83 | 31.6151 | 10.3792 | 8.4405 | 876.0547 |  | 100 | 26157337 | 8.2216
87 | RATNAGIRI | 17.24 | 83.5029 | 87.32 | 147.84 | 3.8171 | 5.6432 | 8.5883 | 484.6581 |  | 100 | 115858879 | 10.9349
88 | SAILU | 5.78 | 73.7435 | 67.28 | 47.5 | -6.4635 | -3.0702 | 6.0758 | -186.5372 |  | 20.64 | 136672551 | 1.7416
89 | SANGAMNER | 9.29 | 79.8479 | 64.96 | 74.11 | -14.8879 | -11.0335 | 5.925 | -653.7298 |  | 80.36 | 66285445 | 7.2743
90 | SANGLI | 32.98 | 71.7216 | 90.68 | 513.64 | 18.9584 | 97.3782 | 8.5772 | 8352.3339 |  | 87.7 | 601410910 | 7.5619
91 | SATANA | 5.78 | 68.9573 | 68.42 | 19.98 | -0.5373 | -0.10735 | 6.2763 | -6.7378 |  | 74.1 | 17004071 | 5.9845
92 | SATARA | 8 | 78.0081 | 88.41 | 346.81 | 10.4019 | 36.0747 | 9.3388 | 3368.9587 |  | 100 | 297725243 | 11.6994
93 | SHAHADA | 7.8 | 49.8306 | 64.97 | 37.4 | 15.1394 | 5.6621 | 9.4358 | 534.2697 |  | 73.5 | 34777316 | 6.0131
94 | SHEGAON | 4.18 | 79.9083 | 91.97 | 33.11 | 12.0617 | 3.9936 | 10.9091 | 435.6681 |  | 94.56 | 40045810 | 8.0131
95 | SHIRPUR | 6.51 | 67.4884 | 70.28 | 41.25 | 2.7916 | 1.1515 | 7.1224 | 82.0175 |  | 81.81 | 39944510 | 6.9088
96 | SILLOD | 11.85 | 44.5465 | 76.26 | 29.36 | 31.7135 | 9.3111 | 5.3781 | 500.7558 |  | 58.02 | 37965442 | 3.8945
97 | SOLAPUR | 106.57 | 79.3861 | 87.41 | 499.33 | 8.0239 | 40.066 | 8.5587 | 3429.114 |  | 86.11 | 529216656 | 7.6802
98 | TALEGAON | 25.1 | 82.3785 | 79.25 | 73.38 | -3.1285 | -2.2957 | 7.5811 | -174.0371 |  | 93.77 | 67509694 | 8.4675
99 | TASGAON | 3.95 | 79.0109 | 86.82 | 23.75 | 7.8091 | 1.8547 | 7.8653 | 145.8742 |  | 100 | 18005429 | 10.1672
100 | TULJAPUR | 5.37 | 77.4543 | 100 | 11.43 | 22.5457 | 2.577 | 8.3377 | 214.8605 |  | 67.8 | 20478457 | 5.7299
101 | TUMSAR | 5.58 | 83.2298 | 80.48 | 22.23 | -2.7498 | -0.61127 | 8.1916 | -50.0729 |  | 86.07 | 18455176 | 7.4128
102 | UDGIR | 13.6 | 76.1341 | 80.53 | 64.01 | 4.3959 | 2.8138 | 6.5599 | 184.5831 |  | 85.04 | 64251087 | 6.6474
103 | UMARGA | 2 | 57.0346 | 1.44 | 610.74 | -55.5946 | -339.5383 | 0.11167 | -379.155 |  | 83.6 | 19087768 | 6.2681
104 | UMARKHED | 3.68 | 63.7935 | 47.37 | 29.3 | -16.4235 | -4.8121 | 5.3311 | -256.5353 |  | 47.44 | 24190740 | 3.9086
105 | UMRED | 5.56 | 77.5913 | 96.08 | 22.97 | 18.4887 | 4.2469 | 9.6387 | 409.3401 |  | 89.01 | 25278112 | 7.3358
106 | URAN-ISLAMPUR | 25.88 | 76.4007 | 94.36 | 62.36 | 17.9593 | 11.1994 | 8.924 | 999.4333 |  | 97.58 | 69171140 | 8.8075
107 | VAIJAPUR | 3.96 | 57.2808 | 54.21 | 21.95 | -3.0708 | -0.67405 | 4.9021 | -33.0423 |  | 68.47 | 24995743 | 5.4236
108 | VASAI | 32.88 | 86.5625 | 43.49 | 207.74 | -43.0725 | -89.4789 | 4.5745 | -4093.1824 |  | 100 | 102229245 | 9.3377
109 | VIRAR | 59.15 | 84.8854 | 48.59 | 545.03 | -36.2954 | -197.8207 | 5.0298 | -9950.0166 |  | 93.6 | 301860864 | 8.4396
110 | VITA | 6.91 | 76.2877 | 73.17 | 35.74 | -3.1177 | -1.1143 | 5.7499 | -64.0681 |  | 100 | 20298344 | 13.5528
111 | WADGAON | 7 | 84.9319 | 68.28 | 66.01 | -16.6519 | -10.9919 | 10.7014 | -1176.2899 |  | 88.05 | 27057766 | 7.483
112 | WAI | 3.79 | 80.8309 | 91.14 | 98.81 | 10.3091 | 10.1865 | 8.1611 | 831.3288 |  | 91.48 | 104423674 | 7.4068
113 | WANI | 13.7 | 72.5122 | 80.36 | 61.8 | 7.8478 | 4.8499 | 7.9628 | 386.189 |  | 88.65 | 52257945 | 8.1429
114 | WARDHA | 25.67 | 76.3266 | 92.37 | 75.23 | 16.0434 | 12.0695 | 9.7687 | 1179.0326 |  | 88.47 | 91755687 | 7.9029
115 | WARORA | 2.59 | 76.9184 | 83.5 | 37.33 | 6.5816 | 2.4569 | 8.1034 | 199.094 |  | 98.98 | 32743645 | 8.2297
116 | WARUD | 3.75 | 65.5023 | 76.05 | 25.14 | 10.5477 | 2.6517 | 8.2259 | 218.1259 |  | 83.56 | 24598066 | 7.1341
117 | WASHIM | 7.72 | 56.2736 | 76.87 | 42.28 | 20.5964 | 8.7082 | 6.7148 | 584.732 |  | 100 | 31232797 | 8.817
118 | YAVATMAL | 25.02 | 63.0351 | 79.2 | 197.13 | 16.1649 | 31.8658 | 12.2807 | 3913.3531 |  | 78.15 | 234906562 | 11.0018
119 | YAWAL | 4.44 | 61.9223 | 59.66 | 15.27 | -2.2623 | -0.34545 | 5.5927 | -19.32 |  | 78.47 | 12429000 | 6.3339
120 | YEOLA | 6.68 | 68.1283 | 86.05 | 21.79 | 17.9217 | 3.9051 | 8.1689 | 319.0068 |  | 83.17 | 24216361 | 6.2116
Total |  | 2922.43 |  |  | 20065.8 |  |  |  | 82492.3881
[8 empty] | Total benefit : Rs | 824.9239 | Crs

## CBA_INFRA II
(A Govt. of Maharashtra Undertaking
CIN= U40109MH2005SGC153645)
------------------------------------------------------------------------------------------------------------------------------------------------------------------------
No. CE(Projects)/Infra-II/ MYT/ 34769 |  |  | Date: 17.12.2019
To,
The Secretary,
Maharashtra Electricity Regulatory Commission,
13th Floor, Centre No.1, World Trade Centre,
Cuffe Parade, Colaba, Mumbai-400 005
Sub:- The cost benefit analysis of Infra-II scheme for year FY 2017-18 & 2018-19.
Preabmle - Infrastructure Plan Part II i.e Infra-II scheme is basically formulated for various Capital works for releasing New connections during the period between FY 2012-13 and FY 2014-15. This New Infrastructure Plan scheme proposal have been selected for 3 years plan and care has been taken to ensure that the expected load Growth up to 2014-15 has been considered. Accordingly MSEDCL has prepared DPRs for 131 Dn. Infra Section has submitted the scheme of Infrastructure Plan Part – II and approved by the Board of Directors vide BR No: 53 dated 07.03.2012 for various capital works such as New substations, switching station, Augmentation of Power Transformers, additional power transformers, Distribution Transformers, associated lines and works etc. Further, for 7 Nos. of towns which were not included under RAPDRP –B Scheme, the Board of Directors, vide BR No. 161 Dt. 23/09/2013, have accorded approval for execution of Infra-II Town Scheme.
The cost benefit analysis of Infra-II Scheme for the year FY 2017-18 & 2018-19 is as follows -
Name of Scheme | Infra-II
MERC In-Principle Clearance Reference No. & Date | Sr. No. | In-Principle Approval Reference |  | Date | Approved Cost in Crs.
| 1 | MERC/Capex/2012-13/02654 |  | 15.02.2013 | 481.86
| 2 | MERC/Capex/20142015/0021 |  | 27.03.2014 | 85.37
| 3 | MERC/Desk-III/Capex/20122013/02351 |  | 15.01.2013 | 86.54
| 4 | MERC/Desk-III/Capex/20132014/02193 |  | 11.02.2014 | 533.69
| 5 | MERC/Desk-III/Capex/2012-13/02487 |  | 29.01.2013 | 101.88
| 6 | MERC/Desk-III/Capex/2012-2013/2648 |  | 15.02.2012 | 550.9
| 7 | MERC/DESK III/CAPEX/20132014/01823 |  | 20.12.2013 | 79.68
| 8 | MERC/Desk-III/Capex/2013-2014/1491 |  | 30.10.2013 | 460.15
| 9 | MERC/Desk-III/Capex/2013-2014/1492 |  | 30.10.2013 | 349.51
| 10 | MERC/Desk-III/Capex/2013-2014/2322 |  | 11.01.2013 | 216.04
| 11 | MERC/Desk-III/Capex/2012-2013/2693 |  | 22.02.2013 | 958.24
| 12 | MERC/Capex/2013-2014/00473 |  | 23.05.2013 | 256.08
| 13 | MERC/Capex/2013-2014/02488 |  | 29.01.2013 | 298.98
| 14 | MERC/Capex/2013-2014/00860 |  | 12.07.2013 | 325.67
| 15 | MERC/Capex/2013-2014/472 |  | 23.05.2013 | 470.23
| 16 | MERC/Capex/2012-2013/607 |  | 07.06.2013 | 491.9
| 17 | MERC/CAPEX/20122013/1362 |  | 04.10.2013 | 301.19
| 18 | MERC/Capex/2013-2014/939 |  | 24.07.2013 | 242.49
| 19 | MERC/Capex/2013-2014/00259 |  | 29.04.2013 | 206.04
| 20 | MERC/Capex/2013-2014/00260 |  | 29.04.2013 | 285.51
| 21 | MERC/Capex/2013-2014/861 |  | 12.07.2013 | 210.42
| 22 | MERC/CAPEX/20132014/1363 |  | 04.10.2013 | 420.4
| 23 | MERC/Desk III/CAPEX/967 |  | 17.09.2014 | 13.37
| 24 | MERC/Desk III/CAPEX/878 |  | 20.08.2014 | 15.05
| 25 | MERC/Desk III/CAPEX/34 |  | 16.10.2014 | 12.46
| 26 | MERC/Desk III/CAPEX/1887 |  | 31.12.2013 | 21.079
| 27 | MERC/Desk III/CAPEX/2014-15/20 |  | 27.03.2014 | 30.59
| 28 | MERC/Desk III/CAPEX/1888 |  | 31.12.2013 | 20.852
| 29 | MERC/Desk III/CAPEX/2013-14/351 |  | 20.05.2014 | 36.9
| 30 | MERC/Desk III/CAPEX/2189 |  | 11.02.2014 | 12.3
| 31 | MERC/Desk III/CAPEX/968 |  | 17.09.2014 | 11.97
| 32 | MERC/Desk III/CAPEX/2013-14/1884 |  | 31.12.2013 | 11.716
| 33 | MERC/Desk III/CAPEX/2013-14/1935 |  | 08.01.2014 | 16.56
| 34 | MERC/Desk III/CAPEX/2192 |  | 11.02.2014 | 25.28
| 35 | MERC/Desk III/CAPEX/2013-14/1934 |  | 08.01.2014 | 31.52
| 36 | MERC/Desk III/CAPEX/350 |  | 20.05.2014 | 25.24
| 37 | MERC/Desk III/CAPEX/2303 |  | 03.03.2014 | 29.96
| 38 | MERC/Desk III/CAPEX/2013-14/2003 |  | 17.01.2014 | 15.78
| 39 | MERC/Desk III/CAPEX/2013-14/2002 |  | 17.01.2014 | 52.62
| 40 | MERC/Desk III/CAPEX/2013-14/2000 |  | 17.01.2014 | 31.82
| 41 | MERC/Desk III/CAPEX/2178 |  | 07.02.2014 | 45.73
| 42 | MERC/Desk III/CAPEX/2190 |  | 11.02.2014 | 35.82
| 43 | MERC/Desk III/CAPEX/2191 |  | 11.02.2014 | 27.17
| 44 | MERC/Desk III/CAPEX/2302 |  | 03.03.2014 | 30
| 45 | MERC/Desk III/CAPEX/1886 |  | 30.12.2013 | 19.995
| 46 | MERC/Desk III/CAPEX/1883 |  | 30.12.2013 | 20.001
| 47 | MERC/Desk III/CAPEX/1885 |  | 30.12.2013 | 19.955
| 48 | MERC/Desk III/CAPEX/2013-14/138 |  | 21.04.2014 | 23.45
| 49 | MERC/Desk III/CAPEX/2013-14/139 |  | 21.04.2014 | 17.07
| 50 | MERC/Desk III/CAPEX/2013-14/365 |  | 21.04.2014 | 30.199
| 51 | MERC/Desk III/CAPEX/2013-14/1751 |  | 12.12.2013 | 22.58
| 52 | MERC/Desk III/CAPEX/2013-14/1752 |  | 12.12.2013 | 37.21
| 53 | MERC/Desk III/CAPEX/2013-14/2179 |  | 07.02.2014 | 21.33
| 54 | MERC/Desk III/CAPEX/795 |  | 31.07.2014 | 20.02
| 55 | MERC/Desk III/CAPEX/794 |  | 31.07.2014 | 25.06
| 56 | MERC/Desk III/CAPEX/140 |  | 21.04.2014 | 21.7
| 57 | MERC/Desk III/CAPEX/2014-15/376 |  | 21.05.2014 | 19.15
| 58 | MERC/Desk III/CAPEX/2014-15/375 |  | 21.05.2014 | 16.34
| 59 | MERC/Desk III/CAPEX/2014-15/377 |  | 21.05.2014 | 10.79
In-Principle Approved Cost Rs. Cr. | 8304.32
Brief Scope of Work | Various capital works such as Erection, Testing & Commissioning of New substations, switching station, Augmentation of Power Transformers, Additional power transformers, Distribution Transformers, Aug. of DTC and its associated lines and works
Objectives | i. Up-gradation of existing system ii. Meeting Load Growth iii. Providing reliable & quality supply iv. Releasing of New Connections R, C, I as well as Ag pumps v. Reduction in DTC Failure Rates vi. Reducing distribution loss
Cummulative Capitalization Rs. Crs. (18-19) | 7639.25 (Capitalization upto 2016-17 is Rs. 4246.34 Crs)
Year wise Capitalization Rs. Cr. | Financial Year |  | Capatilization (Amt. Rs. Cr.)
| 2015-16 |  | 2387.93
| 2016-17 |  | 1580.23
| 2017-18 |  | 1562.91
| 2018-19 |  | 1830
Funding arrangement | Equity | Loan | Grant | Total
| 20% | 80% | NA | 100%
| 1660.86 | 6643.46 | 0 | 8304.32
Time frame/phasing of expenditure | As Approved by MERC |  | Actual
| Year | Amount (Rs. Cr.) | Year | Amount (Rs. Cr.)
| 2015-16 | 302.01 | 2015-16 | 3553.48
| 2016-17 | 0 | 2016-17 | 1608.46
| 2017-18 | 0 | 2017-18 | 741.7343 | 2019-03-01 | 2018-03-01 | 2017-03-01
| 2018-19 | 0 | 2018-19 | 765.0785 | 7723.3068 | 6653.8 | 4974
Scheme completion date | Completed in March 2019 |  |  |  | 1069.5068 | 1679.8
Benefits achieved | 1. Reduction in Distribution Transformer Failure Rate – The Distribution transformer failure rate for FY 2013-14 is 9.18%
| Year | % DTC Failure Rate | Variation of DTC Failure Rate w.r.t FY 2013-14 |  | Submitted by Mr Gondhalekar, MM cell
| 2015-16 | 8.11% | Reduced by 1.07%
| 2016-17 | 7.95% | Reduced by 1.23% |  | 1.68
| 2017-18 | 7.5% | Reduced by 1.68% |  | 1.88
| 2018-19 | 7.3% | Reduced by 1.88%
2. Releasing of New Connections –
The New connections released during FY 2017-18 are 1141614 Nos. having total load of 2114192 KW & The New connections released during FY 2018-19 are 1556566 Nos. having total load of 2364908 KW
3. Increase in Power Handling Capacity – The Total Input Power for FY 2013-14 is 110458 MUs
| Year | Total Input Power in MU's | Variation of Input Power w.r.t FY 2013-14
| 2015-16 | 115076 | Increased by 4.18%
| 2016-17 | 116794 | Increased by 5.74%
| 2017-18 | 123872 | Increased by 12.14%
| 2018-19 | 132441 | Increased by 19.90%
4. Distribution Losses –
The Distribution Losses for FY 2013-14 is 14.00 %
| Year | % Distribution Loss | Variation of Distribution loss w.r.t FY 2013-14
| 2015-16 | 14.51% | Increase by 0.51%
| 2016-17 | 14.68% | Increase by 0.68% |  |  |  | 0.37
| 2017-18 | 13.9% | Decreased by 0.10%
| 2018-19 | 13.63% | Decreased by 0.37%
Chief Engineer (Projects)
M.S.E.D.C.L, Mumbai
Copy s.w.rs. to -
1. The Director (Projects), MSEDCL, Mumbai
2. The Executive Director -IV (Projects), MSEDCL, Mumbai
Copy to - 1. The Superintending Engineer(TRC), MSEDCL, Mumbai
Office of the Chief Engineer (Projects)
Maharashtra State Electricity Distribution Co. Ltd.
“Prakashgad”, 5th Floor, Station Road, Bandra (E),Mumbai-400 051
Tel.: (O) 022- 26474211 Ext.2205,
Email: ceprojects.msedcl@yahoo.com

## 4.1 OTHER
Project Details
Sr. No. | Project Code | Project Title | MERC Approval No. | MERC Approval Date | Project Purpose | Project Start Date |  |  | Project Completion date (Scheduled) |  |  | Capital Cost
[6 empty] | Original | Revised | Actual | Original | Revised | Actual | Approved | Actual Capital Cost Incurred | Deviation = Approved - Actual on account of
[14 empty] | Change in Scope of Work (a) | Material Cost (b) | IDC (c) | Others (d) | Total Deviation (a+b+c+d)
1 | Approval for installation of Rooftop solar at MSEDCL owened Building such as offices, substations, stores, Rest house and CFC's for total pf 50MW |  |  | Preperation of DPR is in process | 285 Crs | DPR for the scheme is to be submitted | DPR for the scheme is to be submitted | DPR for the scheme is to be submitted | DPR for the scheme is to be submitted | DPR for the scheme is to be submitted | DPR for the scheme is to be submitted | 285 Crs
2 | DELP | - | - | 29th May 2015 |  | schme is closed March 2018 | schme is closed March 2018 | schme is closed March 2018 | schme is closed March 2018 | schme is closed March 2018 | schme is closed March 2018 | 55393 lacs | schme is closed March 2018 | schme is closed March 2018 | schme is closed March 2018 | schme is closed March 2018 | schme is closed March 2018 | schme is closed March 2018
3 | Electric Vehicle Charging Stations | - | MERC/Capex/2021-22/548 dtd 15.12.2021 | 15.12.2021 | 8.47 | 25.02.2022 | 0 | 25.02.2022 | - | - | 2023-05-01 | 8.62 | 0.15 | - | - | - | - | 0.15
4 | Implementation of of solar Roof top project for the Prakashgad Building Bandra |  | Preperation of DPR is in process | Non-DPR |  | DPR for the scheme is to be submitted | DPR for the scheme is to be submitted | DPR for the scheme is to be submitted | DPR for the scheme is to be submitted | DPR for the scheme is to be submitted | DPR for the scheme is to be submitted | 0.71 crs
5 | Maharashtra Solar AG Pump Project | - | - | NA |  | Scheme is closed March 2022 | Scheme is closed March 2022 | Scheme is closed March 2022 | Scheme is closed March 2022 | Scheme is closed March 2022 | Scheme is closed March 2022 | 0 | Scheme is closed March 2022 | Scheme is closed March 2022 | Scheme is closed March 2022 | Scheme is closed March 2022 | Scheme is closed March 2022 | Scheme is closed March 2022
6 | Mukhyamantri Sour Krushi Pump Yojana | - | - | NA |  | Scheme is closed March 2022 | Scheme is closed March 2022 | Scheme is closed March 2022 | Scheme is closed March 2022 | Scheme is closed March 2022 | Scheme is closed March 2022 |  | Scheme is closed March 2022 | Scheme is closed March 2022 | Scheme is closed March 2022 | Scheme is closed March 2022 | Scheme is closed March 2022 | Scheme is closed March 2022
7 | OFF-GRID SOLAR PHOTOVOLTAIC WATER PUMPING SYSTEMS & AGRICULTURAL FEEDER SOLARISATION PROJECT WITH CONVENTIONAL AG CONNECTIONS. (Funded by AIIB) Component A: |  | Preperation of DPR is in process |  |  | DPR for the scheme is to be submitted | DPR for the scheme is to be submitted | DPR for the scheme is to be submitted | DPR for the scheme is to be submitted | DPR for the scheme is to be submitted | DPR for the scheme is to be submitted
8 | GIS network analysis | GIS network analysis | Proposal is in process of submission. | - | Network Planning software | 06.04.23 | - | - | 05.09.2028 |  | - | - | - | - | - | - | - | -
9 | Implementation of Electric Vehicle Chargeing Infrastructure operation Center (IT) | Implementation of Electric Vehicle Charging Infrastructure operation Center (IT) | Project Cost below 10 Crs | BR no 1119 dt. 06.01.2018 | EV charging stations Operation center solution at MSEDCL data center. | 04.04.2020 | - | 04.01.2022 | 04.04.2025 | 31.03.2027 | - | - | - | - | - | - | - | -
10 | substation monitoring (maharashtra) | substation monitoring | project is in process |  | Reduce the feeder interuption | 11.03.24 | - | - | 10.03.27 | - | - | -
11 | Implementation of SD WAN | implementation of SD WAN | MERC/Capex/MSEDCL/2023-24/0179 dt 11.03.2024. | 11.03.24 | Improve the performance of Connectivity | 31.10.23 | - | - | 30.10.28 | - | - | 30.42
12 | IT OT redevelopement | IT OT development | MERC/Capex/MSEDCL/2023-24/0179 dt 11.03.2024. | 11.03.24 | upgradation of the existing applications is essential to provide critical services to MSEDCL consumers smoothly. | 08.12.23 | - | - | 12.03.26 | - | - | 8.98
13 | Cloud Infrastructure | cloud | Proposal is in process of submission. |  | migrate all its applications over to Cloud & maintain as per MSEDCL’s requirement in the cloud environment | 23.09.24 | - | - | 23.09.27 | - | - | -
14 | SAP upgradation S4 hana | SAP upgradation | MERC/Capex/MSEDCL/2023-24/0179 dt 11.03.2024. | 11.03.24 | Execute Transction and Analyse Business Data | 11.06.24 | - | - | 10.06.29 | - | - | 74.32
15 | Business anaytics and demand forcasting | Business analytics and demand forecasting | MERC/Capex/MSEDCL/2023-24/0179 dt 11.03.2024. | 11.03.24 | Demand Forecasting and scenario analysis | 16.10.23 | - | - | 15.10.28 | - | - | 30.03
16 | NBSP SIM services | NBSP | Project in process | - | - | 04.07.2023 | - | 04.07.2023 | - | 03.07.2026 | - | - | - | - | - | - | - | -
17 | Procurement of IT infra | Procurement of IT Infra | LOA cost below the 10 crs. | - | supply and installation of Infra (Laptop printer) | Tender is in process | - | - | - | - | In process | - | - | - | - | - | - | -
18 | Mukhyamantri Saur Vahini Yojana Phase I |  | Capex no/18-19/035 | 29.09.2019. | Solar Power Projects on spare land of MSEDCL/MSETCL | 20.01.2018. | - | 20.01.2018 |  |  |  | 92.77 | - | - | - | - | - | -
19 | Incomer Metering-IM | SUBSTATION INCOMER METERING | MERC /CAPEX/2019-20/801 | 2019-09-27 | Providing Metering to Substation Incomer feeders | 2019-11-18 | - | 2020-05-01 | 2020-08-18 | 2021-12-01 | - | 30.08 | 10.50 | - | - | - | - | -
Financing Plan
| Project Number | MERC Approval No. | MERC Approval Date | Project Purpose | Source of Financing for Capital Expenditure
[5 empty] | Internal Accruals | GOM Equity | GOM/ GOI Grant | Debt
[8 empty] | Loan Amount | Interest Rate (% p.a.) | Tenure of Loan (years) | Moratorium Period (years) | Loan Source
| Approval for installation of Rooftop solar at MSEDCL owened Building such as offices, substations, stores, Rest house and CFC's for total pf 50MW | Preperation of DPR is in process | 285 Crs |  | Yes
| DELP | 29th May 2015 | 55393 lacs |  |  |  | Conusmer contribution* | *DELP scheme is revenue neutral scheme. EMI collected from Consumer is passed to M/s EESL
| Electric Vehicle Charging Stations | MERC/Capex/2021-22/548 dtd 15.12.2021 | 15.12.2021 |  | Yes |  |  | - | - | - | - | -
| Implementation of of solar Roof top project for the Prakashgad Building Bandra | Non-DPR | 0.71 crs | Yes |  |  |  | - | - | - | - | -
| Maharashtra Solar AG Pump Project | NA |  |  |  |  | Govt Grant | - | - | - | - | -
| Mukhyamantri Sour Krushi Pump Yojana | NA | 1814 Crs |  |  |  | Govt Grant | - | - | - | - | -
| OFF-GRID SOLAR PHOTOVOLTAIC WATER PUMPING SYSTEMS & AGRICULTURAL FEEDER SOLARISATION PROJECT WITH CONVENTIONAL AG CONNECTIONS. (Funded by AIIB) Component A: | Preperation of DPR is in process | 13493.55 Crs |  |  |  | Govt Grant | - | - | - | - | -
| GIS network analyasis | Proposal is in process of submission. |  | Network Planning software | 20.34 | - | - | - | - | - | - | -
| Business anaytics and demand forcasting | MERC/Capex/MSEDCL/2023-24/0179 dt 11.03.2024. | 11.03.24 | Demand Forecasting and scenario analysis | 9.8288 |  | 14.7431 | - | - | - | - | -
| substation monitoring (maharashtra) | Proposal is in process of submission. |  | Reduce the feeder interuption |  | 93.18 |  | 217.42 | floating @6%
| SAP upgradation S4 hana | MERC/Capex/MSEDCL/2023-24/0179 dt 11.03.2024. | 11.03.24 | Execute Transction and Analyse Business Data | 3.52 |  | 5.2802 | - | - | - | - | -
| Implementation of SD WAN | MERC/Capex/MSEDCL/2023-24/0179 dt 11.03.2024. | 11.03.24 | Improve the performance of Connectivity | 19.2231 |  | 28.8347 | - | - | - | - | -
| Cloud Infrastructure | Proposal is in process of submission. |  | migrate all its applications over to Cloud & maintain as per MSEDCL’s requirement in the cloud environment | 98.52 |  |  | - | - | - | - | -
| IT OT redevelopement | MERC/Capex/MSEDCL/2023-24/0179 dt 11.03.2024. | 11.03.24 | upgradation of the existing applications is essential to provide critical services to MSEDCL consumers smoothly. | 2.93 |  | 4.4006 | - | - | - | - | -
| Implementation of Electric Vehicle Chargeing Infrastructure operation Center (IT) | Project Cost below 10 Crs | BR no 1119 dt. 06.01.2018 | EV charging stations Operation center solution at MSEDCL data center. | 0.87 | - | - | - | - | - | - | -
| NBSP SIM services | Proposal is in process of submission. |  | enable network connectivity for AMR activities | 32.98 | - | - | - | - | - | - | -
| Procurement of IT infra | LOA cost below the 10 crs. |  | supply and installation of Infra (Laptop printer) | 12.8 | - | - | - | - | - | - | -
| Mukhyamantri Saur Vahini Yojana Phase I | Capex no/18-19/035 | 29.09.2019. | Solar Power Projects on spare land of MSEDCL/MSETCL |  |  | 92.77 Cr | - | - | - | - | -
| Incomer Metering-IM | MERC /CAPEX/2019-20/801 | 2019-09-27 | Providing Metering to Substation Incomer feeders | - | - | - | 24.08 | 10.9% | 13 | 3 | REC

## 4.2 OTHER
Project Details
Sr. No. | Project Code | Project Title | MERC Approval No. | MERC Approval Date | MERC Approved Cost | Debt Equity Ratio | Grant/Consumer Contribution | Approved Start Date | Actual Start Date | Approved Date of Completion | Actual Date of Completion | Benefits in Quantified Terms | [7 empty] | Reasons for Delay, if any
[13 empty] | Actual Progress till FY 2021-22 | Actual | Actual | Estimated | Projected | Projected | Projected | Change in Scope of Work | Any other reason
[14 empty] | FY 2022-23 | FY 2023-24 | FY 2024-25 | FY 2025-26 | FY 2026-27 | FY 2027-28
1 | Approval for installation of Rooftop solar at MSEDCL owened Building such as offices, substations, stores, Rest house and CFC's for total pf 50MW | Preperation of DPR is in process |  | Preperation of DPR is in process | 285 Crs | 100% |  | DPR for the scheme is to be submitted | DPR for the scheme is to be submitted | DPR for the scheme is to be submitted | DPR for the scheme is to be submitted | DPR for the scheme is to be submitted | DPR for the scheme is to be submitted | DPR for the scheme is to be submitted | DPR for the scheme is to be submitted | DPR for the scheme is to be submitted | DPR for the scheme is to be submitted | DPR for the scheme is to be submitted | DPR for the scheme is to be submitted
2 | DELP | - |  | 29th May 2015 | 55393 lacs |  | Consumer Contribution | schme is closed March 2018 | schme is closed March 2019 | schme is closed March 2020 | schme is closed March 2021 | schme is closed March 2022 | schme is closed March 2023 | schme is closed March 2024 | schme is closed March 2025 | schme is closed March 2026 | schme is closed March 2027 | schme is closed March 2028 | schme is closed March 2029 |  | -
3 | Electric Vehicle Charging Stations | Implementation of Electric Vehicle Charging Infrastructure operation Center (IT) | MERC/Capex/2021-22/548 dtd 15.12.2021 | 15.12.2021 | 8.47 | 100 % Equity |  | 25.02.2022 | 25.02.2022 |  | 2023-05-01 |  | - | - | - | - | - | - | - | - | -
4 | Implementation of of solar Roof top project for the Prakashgad Building Bandra | Non-DPR | Non-DPR | Non-DPR | 0.71 crs | 100% equity |  | DPR for the scheme is to be submitted | DPR for the scheme is to be submitted | DPR for the scheme is to be submitted | DPR for the scheme is to be submitted | DPR for the scheme is to be submitted | DPR for the scheme is to be submitted | DPR for the scheme is to be submitted | DPR for the scheme is to be submitted | DPR for the scheme is to be submitted | DPR for the scheme is to be submitted | DPR for the scheme is to be submitted | DPR for the scheme is to be submitted
5 | Maharashtra Solar AG Pump Project | - | - | NA | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
6 | Mukhyamantri Sour Krushi Pump Yojana | - | - | NA | 1814 Crs | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
7 | OFF-GRID SOLAR PHOTOVOLTAIC WATER PUMPING SYSTEMS & AGRICULTURAL FEEDER SOLARISATION PROJECT WITH CONVENTIONAL AG CONNECTIONS. (Funded by AIIB) Component A: | Preperation of DPR is in process |  | Preperation of DPR is in process | 13493.55 Crs |  | Grant | DPR for the scheme is to be submitted | DPR for the scheme is to be submitted | DPR for the scheme is to be submitted | DPR for the scheme is to be submitted | DPR for the scheme is to be submitted | DPR for the scheme is to be submitted | DPR for the scheme is to be submitted | DPR for the scheme is to be submitted | DPR for the scheme is to be submitted | DPR for the scheme is to be submitted | DPR for the scheme is to be submitted | DPR for the scheme is to be submitted
8 | GIS network analyasis | GIS network analyasis | Proposal is in process of submission. | - | - | Internal resources | - | 06.04.23 | - | 05.09.28 | - | · Reliability and Performance Indices • Network System behavior and response to disturbances | - | - | - | - | - | - | - | - | -
9 | Implementation of Electric Vehicle Chargeing Infrastructure operation Center (IT) | Implementation of Electric Vehicle Charging Infrastructure operation Center (IT) | Project Cost below 10 Crs | BR no 1119 dt. 06.01.2018 | - | Internal resources | - | 04.04.20 | 04.01.22 | 04.04.2025 | 31.03.27 | Electrical vehicle charging infrastructure Operation Centre to facilitate monitoring, data logging and data analysis of charging stations across Maharashtra. | 100% | 100% | 100% | 100% | 100% | 100% | 100% | MAP Me' functionality & non MSEDCL EV charger data added | Covid 19, Dependancy on various factors like Payment Gateway, SMS, Email, SAP etc integration, Charging rate fixation, EV chargers installation.
10 | substation monitoring (maharashtra) | substation monitoring | Proposal is in process of submission. |  | - | 30%equity | 70% loan | 11.03.24 |  | 10.03.27 |  | Ø Improved monitoring and situational awareness of remote substations  Monitoring of substation data in real-time
11 | Implementation of SD WAN | implementation of SD WAN | MERC/Capex/MSEDCL/2023-24/0179 dt 11.03.2024. |  | 30.42 | 40% loan | 60% grant |  |  |  |  | improve performance of connectivity by using link optimization ,create full mesh connectivity among all the MSEDCL remote offices and integrated with existing network.
12 | Cloud Infrastructure | cloud | Proposal is in process of submission. |  | - | Internal resources | [5 empty] | Less operational issues:: • Security- Cloud Service Provider is usually backed by top class security professionals
13 | SAP upgradation S4 hana | SAP upgradation | MERC/Capex/MSEDCL/2023-24/0179 dt 11.03.2024. | 11.03.2024 | 74.32 | 40% loan | 60% grant | 11.06.24 |  | 10.06.29 |  | · The SAP HANA in-memory database helps organizations to execute transactions and analyse business data in real-time.
14 | Business anaytics and demand forcasting | Business analytics and demand forecasting | MERC/Capex/MSEDCL/2023-24/0179 dt 11.03.2024. | 11.03.2024 | 30.03 | 40% loan | 60% grant | 16.10.23 |  | 15.10.23 |  | · Scenario Analysis • Power Portfolio Management• Enterprise Visualization
15 | IT OT redevelopement | IT OT development | MERC/Capex/MSEDCL/2023-24/0179 dt 11.03.2024. | 11.03.24 | 8.98 | 40% loan | 60% grant | 08.12.23 |  | 12.03.26 |  | Upgradation, Design, Development, Implementation, and Commissioning of new web applications such as Consumer Self-service and Employee Self Service
16 | NBSP SIM services | NBSP SIM Services | Proposal is in process of submission. | - | - | Internal resources | 0 | 04.07.23 | 04.07.23 | 03.07.26 | 0 | help in building comprehensive, transparent, system based, truly automatic metering reading system without any scope of manual intervention. | - | - | - | - | - | - | - | - | -
17 | Procurement of IT infra | Procurement of IT Infra | LOA cost below the 10 crs. | BR no 1119 dt. 06.01.2018 | - | Internal resources | 0 | 04.04.2020 | 04.01.2022 | 04.04.2025 | 31.03.27 | ·To establish cost effective structure for life cycle of ICTE items and optimum resource utilization & reutilization. | - | - | - | - | - | - | - | - | -
18 | Mukhyamantri Saur Vahini Yojana Phase I |  | Capex no/18-19/035 | 29.09.2019. | 92.77 Cr |  | 92.77Crs Grant | 20.01.2018 | 20.01.2018 |  |  |  | 55% | 27% | 7% | 7% | 3%
19 | Incomer Metering-IM | SUBSTATION INCOMER METERING | MERC /CAPEX/2019-20/801 | 2019-09-27 | 30.08 | - | - | 2019-11-18 | 2020-05-01 | 2020-08-18 | - | Benefits of the incomer metering Scheme are as below: 1.There will be accurate measurement of incoming units to MSEDCL Substation. 2.Accuracy in substation Energy audit. | 49% | 15% | 11% | 5% | 20% | - | - | - | Due to covid-19 the scheme work was delayed. Initially there was poor response to the tender at various Zones. Due to no response at Chandrapur zone work cannot be executed. Also due to non completion of works by agency the Tender under Akola zone and Amravati zone (Yavatmal circle) were re-floated at the risk and cost of old agency who had not completed the works.

## CBA_OTHER
CAPEX SCHEME WISE DETAILS_ DATA GAP SET 1
| Sr.No. | Name | Scheme Ref | Status of CBA Submission | Reference Letter
DPR Schemes
| 1 | DELP | MERC Approval Letter MERC/Cell No 6/DSM/MSEDCL/204 dated 29 May 2025 | Approx per year savings in energy: 422.75 per year Cost in saving in Average variable cost Rs 3.38 per unit: Rs 142.88 Crs
| 2 | Implementation of SD WAN | MERC/Capex/MSEDCL/2023-24/0179 dt 11.03.2024. | • SD-WAN solution improved performance of connectivity by using link optimization. The solution has also manage the Link Load on available paths and auto failover for better performance of links. • SD-WAN Solution have inbuilt QoS mechanism which is having application recognition and provide the bandwidth priority for most critical applications. This includes dynamic path selection, sending an application on faster link or even splitting an application between two paths to improve performance by delivering it faster. • SD-WAN solution improved the MSEDCL Video Conferencing ( Data/Voice/Video traffic ) by using polices, performance of the links such as jitter, latency, packet loss, etc and features like Video stream splitting ,de-duplications and automatic traffic diversion for better link performance for MSEDCL video Conferencing Solution. • SD-WAN solution has created full mesh connectivity among all the MSEDCL remote offices and integrated with existing network. | MERC/Capex/MSEDCL/2023-24/0179 dt 11.03.2024.
| 3 | IT OT redevelopement | MERC/Capex/MSEDCL/2023-24/0179 dt 11.03.2024. | • Though there is no direct cost benefit, the upgradation of the above existing applications is essential to provide critical services to MSEDCL consumers smoothly. Also, the scheme has following benefits: 1. Strengthen the availability and responsiveness of existing applications. 2. Simplify IT infrastructure management by making workloads independent of hardware resources, thereby enabling business-driven strategies like strengthening its flexibility over Security and Redundancy policies. 3. Strengthen agility, scalability, multi-tenancy and governance of the entire Application Architecture on the industry lines and maintain these for the foreseeable future. 4. Utilization of the modern technologies evolved in software and database systems to improve the scalability, availability, maintainability, and performance. | MERC/Capex/MSEDCL/2023-24/0179 dt 11.03.2024.
| 4 | SAP upgradation S4 hana | MERC/Capex/MSEDCL/2023-24/0179 dt 11.03.2024. | Benefits of SAP S4 HANA: • The SAP HANA in-memory database helps organizations to execute transactions and analyse business data in real-time. • User experience is powered by Fiori – browser based and convenient to use. • Embedded real-time analytics, and HANA powered in-memory processing to handle large data volumes of operational and transactional business data. Benefits of SAP Treasury and Risk Module (TRM) • With the SAP Treasury and Risk Management application, one can integrate cash flows, transactions, loan, grant and optimize straight-through processing with full-view and real-time analysis, audit trails, and compliance reporting. | MERC/Capex/MSEDCL/2023-24/0179 dt 11.03.2024.
| 5 | Business anaytics and demand forcasting | MERC/Capex/MSEDCL/2023-24/0179 dt 11.03.2024. | The Scheme has enabled measurable improvements including: • Demand Forecasting • Scenario Analysis • Demand Supply Position Map (Load Generation Balance) • Power Portfolio Management • Scheduling Optimization • Trade Optimization • Enterprise Visualization | MERC/Capex/MSEDCL/2023-24/0179 dt 11.03.2024.
RE | 6 | Mukhyamantri Saur Vahini Yojana Phase I | Capex no/18-19/035 | • Max solar capacity to be generated is 200MW. Considering CUF 17.5% for solar power purchase and 6% losses in transmission & distribution, the cost benefit analysis resulting in Saving of Rs 44.19 Crs. Tentative Cost of line evacuation including civil works Rs 92.77Crs Detailed CBA is submitted as CBA_4
TESTING | 7 | Incomer Metering-IM | MERC /CAPEX/2019-20/801 DTD.27.09.2019 | • Substations are the transfer points for energy flows within the electrical grid. The source of power to MSEDCL substation comes from MSETCL’s substation at 33/22KV level (i.e. Incoming line to MSEDCL Substation). • For proper energy audit of substation i.e. for calculating energy loss, accurate measurement of incoming units and outgoing units is important. • After completion of the Metering infrastructure works at balance feeders, the accurate accountng of units and Substation loss will be possible. For proper energy audit of substation i.e. for calculating energy loss, accurate measurement of incoming units and outgoing units dedicated metering is required. • Impact on Tariff of proposed works amounting to 30.10 Crs is in the range of 0.04 Paise/Unit to 0.01 Paise/Unit.
DPR Schemes - Approval in Process
SPD | 8 | Approval for installation of Rooftop solar at MSEDCL owened Building such as offices, substations, stores, Rest house and CFC's for total pf 50MW | DPR to be submitted | Details of CBA is submitted as CBA_1
| 9 | OFF-GRID SOLAR PHOTOVOLTAIC WATER PUMPING SYSTEMS & AGRICULTURAL FEEDER SOLARISATION PROJECT WITH CONVENTIONAL AG CONNECTIONS. (Funded by AIIB) Component A: | Preperation of DPR is in process | Details of CBA is submitted as CBA_3
| 10 | Substation Monitoring (Maharashtra) | Scheme approval is in process | • Improved monitoring and situational awareness of remote substations • Monitoring of substation data in real-time • Reducing the work of operators like taking hourly data, recording the tripping, etc. • Substation equipment health monitoring • Feeder Interruption analysis and computation of reliability indices such as SAIDI, SAIFI, etc. • Monitoring failures and breakdowns, Feeder load profiling, Load growth planning, and management • Feeder demand monitoring, Energy Accounting • Reporting of violations/exceptional values of different equipment in substations • Analysis and diagnosis of the condition of the substation equipment • Load balancing, Data for Load forecasting • Data for Strategic, Managerial, and Operational decisions | Submission in process
Non DPR Schemes
| 11 | Electric Vehicle Charging Stations | MERC/Capex/2021-22/548 dtd 15.12.2021 | • No of unit sale in this business up to 13.11.2024: 665859 Units • Income from Ev charging station business up to 13.11.2024: Rs 0.87 Crs • Total Capex expenditure: Rs 8.67 Crs
| 12 | Implementation of of solar Roof top project for the Prakashgad Building Bandra | Preperation of DPR is in process | Details of CBA is submitted as CBA_2
IT | 13 | GIS network analyasis | Proposal is in process of submission. | The has enabled measurable improvements including: • GIS Implementation at Enterprise Level • Reliability and Performance Indices • Network System behavior and response to disturbances • Optimization of asset utilization and operating efficiency of the electric power system. | In process
| 14 | Implementation of Electric Vehicle Chargeing Infrastructure operation Center (IT) | Project Cost below 10 Crs | Electrical vehicle charging infrastructure Operation Centre to facilitate monitoring, data logging and data analysis of charging stations across Maharashtra. | In process
| 15 | Cloud Infrastructure | Proposal is in process of submission. | • Lower Total Cost of Ownership: MSEDCL’s On-premise IT-infrastructure estimated cost for 5 years (2018-19 to 2022-23) is approx. Rs. 205.79 Crores i.e. approx. Rs. 41.15 Crores per year. Whereas for cost of Cloud Computing (as per recent LOA awarded by MSEDCL) for availing same type of services is approx. Rs. 17.90 Crs per year (thus saving Rs. 23.25 Crs per year). | In process
| 16 | NBSP SIM services | Project in process | • The has enabled network connectivity for AMR activities by appointing different network bandwidth service providers (NBSP contract) for SIM and backhaul link services. This will in turn help in building comprehensive, transparent, system based, truly automatic metering reading system without any scope of manual intervention. • The data enabled SIMs will be utilized in various MSEDCL projects such as: i. Smart Prepaid Meters of Ag Consumers ii. Substation Monitoring System for all substations in Maharashtra iii. Other IoT projects planned under RDSS scheme such as DT Health Monitoring system, communicable FPI etc. iv. LT connections above 20 kW, HT connections, feeders and DTCs | In process
| 17 | Procurement of IT infra | LOA cost below the 10 crs. | • The IT infra equipment is procured across various offices for similar specifications. • It is ensured whether adequate security policies are taken care at the time of Installation & Commissioning of the IT infra. • Best practices are introduced for Refreshment-Disposal of ICTE resources (Hardware/Software) of MSEDCL. • Cost effective structure for life cycle of ICTE items and optimum resource utilization & reutilization. | In process

## TOR COR_OTHER
CAPEX SCHEME WISE DETAILS_ DATA GAP SET 1
Sr.No. | Name | Details of Cost Over run if any |  |  | Details of Time Over run if any
|  | Approved Cost (Rs. Crs) | Revised Cost (Rs. Crs) | Justification for Cost Overrun | Original Completion | Revised Completion | Justification for Time Overrun etc.
DPR Schemes
1 | DELP | 553.93 | 211.55 | No Cost Overrun | 31.03.2018 | 2018-11-01 | Scheme is closed but Delay in release of payment due to late claim by implemneting agency which on account of agency.
2 | Implementation of SD WAN | 30.42 | - | Scheme is ongoing | 30.10.2028 | - | Scheme is ongoing
3 | IT OT redevelopement | 9.98 | - | Scheme is ongoing | 12.03.2026 | - | Scheme is ongoing
4 | SAP upgradation S4 hana | 74.32 | - | Scheme is ongoing | 10.06.2029 | - | Scheme is ongoing
5 | Business anaytics and demand forcasting | 30.03 | - | Scheme is ongoing | 15.10.2028 | - | Scheme is ongoing
6 | Mukhyamantri Saur Vahini Yojana Phase I |  |  | - |  |  | -
7 | Incomer Metering-IM | 30.08 | - | No Cost Overrun | 18.11.2019 | 31-03-2025. | 1. Due to covid-19 the scheme work was delayed. 2. Initially there was poor response to the tender at various Zones. Due to no response at Chandrapur zone work cannot be executed. 3. Also due to non completion of works by agency the Tender under Akola zone and Amravati zone (Yavatmal circle) were re-floated at the risk and cost of old agency who had not completed the works.
DPR Schemes - Approval in Process
8 | Approval for installation of Rooftop solar at MSEDCL owened Building such as offices, substations, stores, Rest house and CFC's for total pf 50MW |  |  | DPR to be submitted |  |  | DPR to be submitted
9 | OFF-GRID SOLAR PHOTOVOLTAIC WATER PUMPING SYSTEMS & AGRICULTURAL FEEDER SOLARISATION PROJECT WITH CONVENTIONAL AG CONNECTIONS. (Funded by AIIB) Component A: |  |  | DPR to be submitted |  |  | DPR to be submitted
10 | Substation Monitoring (Maharashtra) | 382 | - | - | 10.03.2027 | - | Scheme approval is in process
Non DPR Schemes
11 | Electric Vehicle Charging Stations | 8.62 | 8.62 | No Cost Overrun | 2023-05-01 | 2023-05-01 | EVCS is delicensed activity and henece the capital exependiture by Distribution licensee to engage cnnot allowed to be recovred through tariff by including it in licensed business. Maintain sepaerate account for such business of setting up of EV public CS and the capaex exependiture on the same shall not be recovered through ARR
12 | Implementation of of solar Roof top project for the Prakashgad Building Bandra |  |  | - |  |  | This is Non DPR scheme. This is yet to be started
13 | GIS network analyasis | - | - | - | 05.09.2028 | - | Proposal is in process of submission.
14 | Implementation of Electric Vehicle Chargeing Infrastructure operation Center (IT) | - | - | - | 04.12.2024 | - | Project Cost below 10 Crs
15 | Cloud Infrastructure | - | - | - | 23.09.2027 | - | Proposal is in process of submission.
16 | NBSP SIM services | - | - | - | 03.07.2026 | - | Project in process
17 | Procurement of IT infra | - | - | - | In process | - | LOA cost below the 10 crs.

## CBA_1
Approval for installation of Rooftop solar at MSEDCL owened Building such as offices, substations, stores, Rest house and CFC's for total pf 50MW
COST BENEFIT ANALYSIS
Sr. No. | Particular | Unit | MSEDCL
1 | Number of locations/connections | Nos | 123299
2 | Sanctioned load | MW | 35.78
3 | Annual Consumption | MUs | 45.92
4 | Avg Monthly Consumption | MUs | 3.83
5 | Assessed PV Capacity as per consumption | MWp | 49.63
6 | Shadow free area required as per assessed PV capacity | Lakh SqFt | 49
7 | Shadow free area available | Lakh SqFt | 95
8 | Applicable PV capacity as per shadow free area | MWp | 49
9 | Project DPR Cost considering MNRE Benchmark cost Rs 50,000/ KW | Rs. Cr | 327.18
10 | Annual Energy bill saving (For 25 Years) | Rs. Cr | 21
11 | Annual Energy Export in terms of Amount (For 25 Years ) | Rs. Cr | 8
12 | IRR after 25 years | % | 13
13 | NPV | Rs. Cr | 66
14 | Payback Period | Year | 8

## CBA_2
Implementation of of solar Roof top project for the Prakashgad Building Bandra
COST BENEFIT ANALYSIS
Total capacity kWp | 280
Gross energy production kWp/Annum | 1350
Total estimated generation KWh/Annum | 378000
Existing average per unit rate (Rs/unit) | 8
Annual saving Rs by net metering | 3024000
Approx expenditure | 1.41 Crs
Payback period | 5 Years

## CBA_3
Off-Grid Solar Photovoltaic Water Pumping Systems & Agricultural Feeder Solarisation Project With Conventional Ag Connections. (Funded by AIIB) Component A:
COST BENEFIT ANALYSIS
Total Solar nos. of pump | 500000
Total Solar Units Generated by solar pump Kwh/Year (MUs) | 1477.8
Actual Units Required after adding Loss Units/Year (MUs) | 1738.69
Power Purchse Cost with T&D Loss Units/Year @ Rs.5.68/Kwh (Rs. In Crs) | 987.52
Saving in Cross Subsidy/Year @ Rs.3.65/Kwh (Rs. Cr.) | 604.42
Saving in Farmer Energy Bill as per MERC Rate per year (Rs. Cr.) as per MERC Rate, EC+WC @ Rs. 4.17/unit | 754.37
Saving in Govt. Subsidy/Year | 312.11
(Rs. Cr.) as per Govt Subsidy Rate, EC+WC @ Rs. 2.03/unit
Saving in Farmer Energy Bill as per Pay Rate per year | 442.26
(Rs. Cr.) As per Consumer Rate, EC+WC @ Rs. 2.14/unit for 3 HP and Rs. 2.44/unit for 5 HP & 7.5 HP.
REC cost saving for RPO @ Rs. 1 Per Unit (Rs. Cr.) | 147.28

## CBA_4
Mukhyamantri Saur Vahini Yojana Phase I
Year wise Cost Benefit Analysis for Projects under 200 MW PPA with EESL
Year | FY 2019-20 | FY 2020-21 | FY 2021-22 | FY 2022-23 | FY 2023-24
Solar capacity to be generated | 11.795 MW | 54.796 MW | 109.546 MW | 151.623 MW | 173.708 MW
Total Energy generated (A) in MUs | 18.08 Mus | 84.00 Mus | 167.93 Mus | 232.43 Mus | 266.29 Mus
Losses for 33KV level ( 6%) | 19.16 Mus | 89.04 Mus | 178.01 Mus | 246.38 Mus | 282.27 Mus
Avoided generation (B)=(A)*1.06
(Considering 6% loss of 33KV level)
Approved power purchase rate for solar generation by Hon. MERC order 195 of 2017 dtd 12.09.2018 (Rs. 4.19 per unit) | 8.03 Cr | 37.30 Cr | 74.58 Cr | 103.23 Cr | 118.27 Cr
Cost of avoided generation ©=(B)*4.19
Rate of Power purchase offered by M/S EESL for 25 years | Rs. 3.00 | Rs. 3.00 | Rs. 3.00 | Rs. 3.00 | Rs. 3.00
Cost of Power generation to be paid by MSEDCL to M/S EESL (D)=(A)*3 | 5.42 Cr | 25.20 Cr | 50.38 Cr | 69.73 Cr | 79.88 Cr
Saving (C-D) | 2.60 Cr | 12.10 Cr | 24.20 Cr | 33.50 cr | 38.38 Cr